## Risk template
Occupational Health and Safety Baseline risk assessment template
Business/Operating unit: | NATIONAL TRANSMISSION COMPANY SOUTH AFRICA (NTCSA) | [7 empty] | Department: | Power Delivery: H&S | [9 empty] | Next Review Date (every 2 years): | 20260409 | Template identifier: | 240-70044602
| PROJECT: Civil Panel Works | [7 empty] | Prepared by: | D.Kotlolo |  | Authorised by: |  | Name: Vusi Mthimunye | [7 empty] | Document identifier | [8 empty] | R | Safety | 1 | A | Fully effective | I
[14 empty] | Designation: Construction Health and Safety Agent | [7 empty] | Revision number: | 1 | [7 empty] | N | Health | 2 | B | Mostly effective | II
[14 empty] | Signed: | [7 empty] | Revision date: | 2024-05-31 | [9 empty] | 3 | C | Mostly ineffective | III
[14 empty] | Date: 26 Nov 2024 | [18 empty] | 4 | D | None | IV
Refer to Occupational Health and Safety Risk assessment procedure 32-520 | [32 empty] | 5 | E
List activity | Activity type (Routine/Non-routine) | Hazard nr | Hazard Identification | Risk Nr | Associated risk | Risk type | Cause(s) of the risk | Exposed group/employees | Risk Owner | Exposure patterns | What are the possible consequences? | Existing Controls |  |  | Risk Priority Rating |  | Additional Controls or Tasks Aimed at improving Existing Controls | Monitoring Mechanisms | Control Owner | Legal and Other Requirements | Target Date | Current Status | Integrated Risk Management (IRM) reference number | [9 empty] | 6
List specific activities to be performed taking into consideration the equipment to be used, the personnel involved in the task. | Indicate R or N 1. Routine activities and situations create hazards through day-to-day operations and normal work activities; 2. Non-routine activities and situations are occasional or unplanned; | # | Anything with potential to cause of harm. Note: A hazard can pose more than one risk. | # | A chance that injury , ill health or damage could occur as a result of uncontrolled hazard. | Safety or health | What causes the risk to come into effect? | Who is exposed to the hazard i.e. visitors, members of the public, etc. | Who is accountable for making sure the controls and monitors are: - in place, - implemented, - regularly reviewed for effectiveness. | The frequency and duration the person/group is exposed to the hazard e.g. Daily for 3 hrs. | Consider the worse case scenario without controls? | Include: - Preventative Controls (controls implemented to eliminate hazards or reduce the likelihood of the risk occurring), and - Reactive Controls (controls implemented to reduce the immediate impact of the risk occurring) Elimination Substitution Engineering controls Administrative controls Personal protective equipment (PPE) | Consequence | Likelihood |  | RCE Risk Control Effectiveness | Include: - Preventative Controls (controls implemented to eliminate hazards or reduce the likelihood of the risk occurring), and - Reactive Controls (controls implemented to reduce the immediate impact of the risk occurring) Elimination Substitution Engineering controls Administrative controls Personal protective equipment (PPE) | How we know if we are succeeding. Include comments on effectiveness. This may include i.e. measurements, inspections, supervision where necessary. | Person allocated the responsibility for implementing the agreed controls | Where relevant, list the relevant legislative and or Eskom requirements that prescribe the control. | Once a date has been agreed to, this can not be changed | Pending, In Progress, Complete | Where applicable, add IRM system reference number for tracking of treatment actions. | Consequences | 6 | III | II | I | I | I
Identification and demarcation of protected and/or listed vegetation at the identified construction location. | R | 1 | Uneven surfaces (rocks, tree stumps, etc) | 1.1 | Slips, trips and falls | Safety | Obstacles on the surface; Poor housekeeping; Lack of concentartion; Slippery surfaces (loose stones and wet surface) | Surveyors; Environmental and Health and Safety personnel | PM | 8 hours | Medical injury | Awareness training during inductions for employees and visitors tobe aware of their surroundings, i.e tree stumps, loose rock material, and other obstacles. | 3 | B | III | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act; Construction Regulations 7(6); | TBA | Pending, |  |  | 5 | III | II | II | I | I
|  | 2 | Biological Hazards (snakes, bees, scorpions etc) | 2.1 | Snake bites and bee and scorpion stings | Safety | Coming into contact with snakes,bees, scorpions, spiders etc | Surveyors; Environmental personnel Health and Safety personnel | PM | 8 hours | LTI | Awareness training on snakes, bees, scorpions etc; Appoint snake handlers and persons with knowledge of bees and similar insects. | 3 | B | III | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act Section 8 | TBA | Pending, |  |  | 4 | IV | III | II | I | I
|  | 3 | Extreme weather conditions (heat , cold) | 3.1 | Dehydration / Frost bite / hypo and hyperthermia | Health | Exposure to extreme weather conditions; Inadequate rehydration / water/fluid intake; Inadequate or failure to provide suitable PPE | Surveyors; Environmental personnel Health and Safety personnel | PM | 8 hours | Medical injury | Ensure adequate water supply on site; Work rotation, Regular work breaks; Overalls with long sleevs, safety boots; Warm thermal jackets for winter; | 3 | B | III | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act; Environmental Regulations for Workplaces 2; Eskom's Personal Protective Equipment Specification 240-44175132 | TBA | Pending, |  |  | 3 | IV | III | II | II | I
Bush & shrub clearing and tree felling | R | 4 | Biological hazards; | 4.1 | Snake bites and bee and scorpion stings | Health | Contact with snakes, bees, scorpions, spiders etc | Bush clearing team | PM | 8 hours | LTI | Site specific SHE induction; Appoint snake handlers and persons with knowledge of bees and similar insects; Awareness training on how to react when faced with snakes, bees, scorpions etc; | 4 | B | III | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act; Eskom's Personal Protective Equipment Specification 240-44175132 | TBA | Pending, |  |  | 2 | IV | IV | III | II | II
|  | 5 | Uneven surfaces (rocks, tree stumps, etc) | 5.1 | Slips, trips and falls | Safety | Mis-stepping; Obstacles on the surface; poor housekeeping; Inattention while walking; Slippery surfaces (loose stones and wet surface) | Bush clearing team | PM | 8 hours | Medical injury | Remove obstacles on the surface; Practice good housekeeping; Awareness training Regular inspection of workplace. | 3 | B | III | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act Section 8 | TBA | Pending, |  |  | 1 | IV | IV | III | III | III
|  | 6 | Hand/Power tools e.g. chain saw, hand saws and other cutting tools | 6.1 | Injuries | Safety | Lack of training; incorrect use of equipment Use of defective equipment Poor supervision; Failure to follow procedures | Bush clearing team | PM | 8 hours | Medical injury | Operators shall be trained / Awareness training; Work rotation / regular breaks; Develop a maintenance schedule for all machinery; Provide general supervision; Develop safe work procedures, and communicate to all employees. | 4 | B | III | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act Section 8 | TBA | Pending, |  |  |  | A | B | C | D | E
|  | 7 | Cutting of trees | 7.1 | Injuries | Safety | Lack of training; Lack of concentration; Poor supervision; Failure to follow procedures; Failure to put on correct PPE | Bush clearing team | PM | 8 hours | Medical injury | Operators shall be trained / Awareness training; Work rotation / regular breaks; Develop a maintenance schedule for all machinery; Provide general supervision; Develop safe work procedures, and communicate to all employees. | 4 | B | III | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act Section 8 | TBA | Pending, |  |  |  | Likelihood
|  | 8 | Moving machinery (eg TLB); | 8.1 | Struck by | Safety | Lack of warning alarm on machinery e.g. reverse hooter/alarm; Lack of observation operating TLB Failure to demarcate walk areas; Failure to appoint competent flagmen | Bush clearing team | PM | 8 hours | Fatality | Operators shall be trained; Awareness training; Develop a site specific traffic plan; Provide trained flagmen and give them high visibility vests. | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act Section 8 CR 22-1-d | TBA | Pending,
|  | 9 | Noise & dust from bush/tree/branch shredder (wood chipper) | 9.1 | Noise induced hearing loss; Lung/respiratory diseases; | Health | Exposure to noise level above 85dB; Exposure to or inhalation of wood/saw dust. | Bush clearing team | PM | 8 hours | LTI | Provide and train employees on use of PPE (ear protection); Conduct health risk assessment and surveys; Communicate survey results / recommendations to employees; Provide supervision. | 4 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | NHLR; Eskom's Medical Surveillance Procedure 240-84733329. | TBA | Pending,
|  | 10 | Extreme weather conditions (heat , cold, dust) | 10.1 | Frost bite / hypo and hyperthermia | Health | Faillure to conduct health risk assessment; Failure to provide PPE ( thermal gloves and jackets, wide brim hats etc) | Bush clearing team | PM | 8 hours | Medical injury | Provide and train employees on use of PPE; Conduct health risk assessment and surveys; Communicate survey results / recommendations to employees; Provide supervision. | 3 | B | III | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | Environmental Regulations for Workplaces 2; Eskom's Personal Protective Equipment Specification 240-44175132 | TBA | Pending,
Access road/offloading pad construction | N | 11 | Ground/earth grading equipment i.e graders | 11.1 | Struck by; Noise; Dust; Equipment vibration; Accidents e.g. overturning (capsizing) | Safety or health | Failure to develop / inadequate site traffic plan; Untrained / inexperience operator; Failure to appoint competent flagmen; Failure to follow instructions; Failure to conduct Occupation Hygiene surveys; Failure to enforce the recommendations of the OH surveys/risk assessment on the correct PPE to use. | Civil team | PM | 8 hours | Fatality | Contractor shall develop a site specific traffic plan, as per Section 49 of SHE Specification Form 74 (Construction Vehicles and Mobile Plant); Construction Regulations 23 (1)(d): Construction Vehicles & Mobile Plant; Contractor shall appoint a competent person as flagman, as per Section 49 of SHE Specification Form 74 (Construction Vehicles and Mobile Plant); Contractor to ensure that contractor supervisors and employees are trained in safe work procedures; Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50, Section 4.4.2.1 on Medical Surveillance; | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act Section 8 Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50, Section 4.4.2.1 on Medical Surveillance CR 23 (1)(d): Construction Vehicles & Mobile Plant; | TBA | Pending,
|  | 12 | Excavating equipment e.g. TLB | 12.1 | Overturning/capsizing (Accidents) | Safety | Failure to develop / inadequate site traffic plan; Untrained / inexperience operator; Failure to appoint competent flagmen; Failure to follow instructions; Failure to conduct Occupation Hygiene surveys; Failure to provide PPE and enforce the recommendations of the OH surveys & relevant risk assessment | Civil team | PM | 8 hours | Fatality | Contractor shall develop a site specific traffic plan, as per Section 49 of SHE Specification Form 74 (Construction Vehicles and Mobile Plant); Construction Regulations 23 (1)(d): Construction Vehicles & Mobile Plant; Contractor shall appoint a competent person as flagman, as per Section 49 of SHE Specification Form 74 (Construction Vehicles and Mobile Plant); Contractor to ensure that contractor supervisors and employees are trained in safe work procedures; Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50, Section 4.4.2.1 on Medical Surveillance; | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act Section 8 Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50, Section 4.4.2.1 on Medical Surveillance CR 23 (1)(d): Construction Vehicles & Mobile Plant; | TBA | Pending,
Site Establishment | R | 13 | Mobile Plant, e.g. TLB | 13.1 | Struck by; Noise; Dust; Whole body vibrations | Safety or health | Failure to develop / inadequate site traffic plan; Untrained / inexperience operator; Failure to appoint competent flagmen; Failure to follow instructions; Failure to conduct Occupation Hygiene surveys; Failure to provide PPE and enforce the recommendations of the OH surveys/risk assessment | Site establishment team | PM | 8 hours | Fatality | Contractor shall develop a site specific traffic plan, as per Section 49 of SHE Specification Form 74 (Construction Vehicles and Mobile Plant); Construction Regulations 23 (1)(d): Construction Vehicles & Mobile Plant; Contractor shall appoint a competent person as flagman, as per Section 49 of SHE Specification Form 74 (Construction Vehicles and Mobile Plant); Contractor to ensure that contractor supervisors and employees are trained in safe work procedures; Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50, Section 4.4.2.1 on Medical Surveillance; | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act Section 8 Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50, Section 4.4.2.1 on Medical Surveillance CR 23 (1)(d): Construction Vehicles & Mobile Plant; | TBA | Pending,
|  | 14 | Electrical connections to prefabricated offices | 14.1 | Electrocution | Safety | Incorrect wiring; Lack of or inadequate Log-Out-Tag-Out system; Lack of supervision; Failure to test before touching; Unskilled / untrained electrician; | Site establishment team | PM | 8 hours | Fatality | Eskom's Life Saving Rules, Rule 1: Open, isolate, earth, test, bond, before touch; Electrical Installation Regulations 2, 5 and 6; Training and supervision | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act EIR Eskom's Life Saving Rules | TBA | Pending,
|  | 15 | Lifting operations (e.g. Offloading of Prefrabricated office) | 15.1 | Failure of the lifting equipment/ dislodgement of object | Safety | Use of underated / defective lifting equipment; Failure to maintain lifting equipment; Failure to follow safe work procedures; Lack of training of operator; Poor lifting methods/techniques Inadequate supervision | Site establishment team | PM | 8 hours | Fatality | Appoint competent slinger (SANS 12480-1 Section 5.4 (slinger); Appoint competent crane operator (SANS 12480-1 Section 5.3: Crane driver & Section 5.3.3: Training of crane driver); Develop a maintenance schedule as per manufacturer's manual; Train supervisors, operators, employees on safe work procedures. | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act SANS 12480-1 | TBA | Pending,
Surveying & Pegging | R | 16 | Hand tools, eg. Hammer ; | 16.1 | Hand / Finger struck by hand tools | Safety | Lack of attention; Incorrect work position; Defective tools. | Surveying Team | PM | 8 hours | Medical injury | Awareness training of employees in the use of hand tools like hammers, spanners, chisels etc; Inspection of tools before use; Supervision. | 3 | B | III | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act | TBA | Pending,
|  | 17 | Extreme weather conditions | 17.1 | Dehydration / Frost bite / hypo and hyperthermia | Health | Inadequate water supply, inadequate or failure to provide suitable PPE (thermal gloves and jackets, wide brim hats etc); ensure good ergonomic regime | Surveying Team | PM | 8 hours | Medical injury | Work rotation, Regular work breaks; Overalls with long sleevs, safety boots; Warm thermal jackets for winter. | 3 | B | III | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | Environmental Regulations for Workplaces 2; Eskom's Personal Protective Equipment Specification 240-44175132 | TBA | Pending,
|  | 18 | Biological hazards (snakes, bees, scorpions); Wild animals | 18.1 | Snake & spider bites, bee stings, etc; Animal attacks | Health | Contact with snakes, bees, scorpions, spiders etc Contact with wild animals | Surveying Team | PM | 8 hours | Fatality | Awareness training; Induction training; Appointment of trained snake handlers; Awareness training on how to react when faced with wild animals; Fence off animals and prevent contact with workers. | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act | TBA | Pending,
Platform / Terrace Earthworks | R | 19 | Mobile Plant, e.g. TLB | 19.1 | Struck by; Noise; Dust; Equipment vibrations | Safety or health | Failure to develop / inadequate site traffic plan; Untrained / inexperience operator; Failure to appoint competent flagmen; Failure to follow instructions; Failure to conduct Occupation Hygiene surveys; Failure to provide PPE and enforce the recommendations of the OH surveys/risk assessment | Earthworks Team | PM | 8 hours | Fatality | Contractor shall develop a site specific traffic plan, as per Section 49 of SHE Specification Form 74 (Construction Vehicles and Mobile Plant); Construction Regulations 23 (1)(d): Construction Vehicles & Mobile Plant; Contractor shall appoint a competent person as flagman, as per Section 49 of SHE Specification Form 74 (Construction Vehicles and Mobile Plant); Contractor to ensure that contractor supervisors and employees are trained in safe work procedures; Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50, Section 4.4.2.1 on Medical Surveillance / Continuous occupational hygiene surverys; Enforce the recommendations of the OH surveys ( eg wearing of PPE like dust masks, ear protection, etc); | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act Section 8 Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50, Section 4.4.2.1 on Medical Surveillance CR 23 (1)(d): Construction Vehicles & Mobile Plant; | TBA | Pending,
|  | 20 | Noise | 20.1 | Noise induced hearing loss | Safety | Failure to provide and train and use hearing protection; Failure to supervise use of ear protection | Earthworks Team | PM | 8 hours | LTI | Provide and train employees on use of PPE (ear protection); Conduct health risk assessment and communicate to employees; Provide supervision. | 4 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | NHLR; Eskom's Medical Surveillance Procedure 240-84733329. | TBA | Pending,
|  | 21 | Oils and other petroleum material from mobile plant | 21.1 | Oil spillage leading to ground water contamination | Health | Failure to maintain & service equipment Failure to provide adequate drip trays Failure to perform regular inspection | Earthworks Team | PM | 8 hours | LTI | Train / inform employees on the handling of HCS; Conduct continuous occupational hygiene surverys; Provide MSDS for all chemicals in use; Provide adequate storage facilities; Provide suitable PPE (respirators, PVC suits, depending on the HCS in question) | 4 | B | III | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act HCSR Eskom's Personal Protective Equipment Specification 240-44175132 | TBA | Pending,
Excavation / trenching | R | 22 | Collapse of excavation walls (cave-in); | 22.1 | Entrapment/engulfment of persons inside the excavation | Safety | Unstable excavation; Unstabilized or unsupported excavation; | Excavation team; Members of the Public; Animals | PM | 8 hours | Fatality | The Contractor to submit the proposed foundation and soil type nomination schedules to the Design Engineer as per Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 6.5.1; Contractor to ensure excavation is adequately shored and braced as per Construction Regulations 13 | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 6.5.1 (Excavations); Construction Regulations 13 | TBA | Pending,
|  | 23 | Underground services (services pipes, eletrical & telecoms cables etc); | 23.1 | Damage to underground services; Electric shocks | Safety | Failure to perform or conduct correct underground scan; Failure to communicate results of tests for underground services to operator; Unavailability of plans for underground services. | Excavation team; Members of the Public; Animals | PM | 8 hours | Fatality | Use underground services detector (eg cable detector) to identify / trace underground services; Obtain and use underground service plan; Identification of signs for underground services; Communicate the results of the tests to all employees. | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act CR 13(2-g); | TBA | Pending,
|  | 24 | Material / people/ animals falling into excavation | 24.1 | Injuries to employees / animals; | Safety | Failure to barricade the excavation area; Failure to warn of danger. | Excavation team; Members of the Public; Animals | PM | 8 hours | LTI | Provide warning signs & barricading to warn and prevent people and animals from falling onto excavation. | 4 | B | III | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act CR 13 (2-i) | TBA | Pending,
|  | 25 | Moving machinery (e.g. TLB); | 25.1 | struck by | Safety | Lack of reverse alarm on machinery; Failure to train and provide a flagman; Untrained flagman; Inadequate supervision; No log-out-tag-out system in place leading to operation of machine by incompetent person. | Excavation team; Visitors; | PM | 8 hours | Fatality | Ensure operators are competent; Provide trained flagmen; Supervision (ensure the moving machinery is at a safe distance from the excavation); Erect barricading around excavation. | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act; CR 13 (2-d) | TBA | Pending,
|  | 26 | Oxygen deficiency in the excavation | 26.1 | Asphyxiation to operators in the excavation | Safety | Entering the excavation without performing oxygen tests. | Excavation team operators; | PM | 8 hours | Fatality | Operators must be competent to operate the machinery; Ensure there are trained flagmen during operations; Provide adequate supervision; Provide high visibility PPE. | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act; CR 23 (1-d-i); Eskom Procedure 39-98 Section 2.6 & 2.18 | TBA | Pending,
|  | 27 | Dust from excavation process/activity | 27.1 | Dust inhalation leading to (lung) respiratory health diseases | Health | Exposure to dust without using respiratory protection equipment (RPE); | Excavation team; | PM | 8 hours | Medical | Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50, Section 4.4.2.1 on Medical Surveillance; Conduct health risk assessment and communicate hazards to employees; Provide hearing and respiratory protection, and supervise their use. | 4 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act; NHLR; Eskom's Medical Surveillance Procedure 240-84733329. | TBA | Pending,
|  | 28 | Possible collection of water (damming) | 28.1 | Drowning | Safety | Rain water and/or damage to under-surface services e.g. water line | Excavation team; Project team members; Visitors; animals; members of the public | PM | 8 hours | Fatality | Solid barricading as per the Health and Safety specification. | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act Sec 8; Eskom Personal Protective Equipment Specification 240-44175132;Eskom Medical Surveillance Procedure 240-84733329. | TBA | Pending,
Working with Cement | R | 29 | Dust/ Wet Cement; | 29.1 | Mesothelioma, Cement burns and Dermatitis | Health | Faillure to conduct health risk assessment and surveys; Failure to inform employees of survey results; Failure to inform employees of hazard; Failure to provide suitable PPE | Construction team | PM | 8 hours | LTI | Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50, Section 4.4.2.1 on Medical Surveillance; Conduct health risk assessment and surveys; Communicate survey results and hazards to employees; Provide awareness training for cement work; Job rotation; Persons mixing concrete to use proper PPE including gumboots, safety gogggles, long PVC gloves, respiratory protection etc; | 4 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act Section 8; HCSR; Eskom's Personal Protective Equipment Specification 240-44175132; Eskom's Medical Surveillance Procedure 240-84733329. | TBA | Pending,
|  | 30 | Ergonomics hazards | 30.1 | Body aches, muscles injuries, sprains, etc | Health | Inadequate workplace risk assessment to identify egornomic risks e.g. awkward positions, overexertion, working in high temperatures, etc | Construction team | PM | 8 hours |  | Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50, Section 4.4.2.1 on Medical Surveillance; Conduct health risk assessment surveys; Communicate survey results to employees; Communicate hazards to employees; Awareness training on correct posture techniques; Job rotation and work rest periods | 3 | C | III | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act; Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50. | TBA | Pending,
Yardworks | R | 31 | Open excavation | 31.1 | Fall into | Safety | Failure to post warning signs; Failure to barricade excavation; Failure to make aware. | Yardworks Team | PM | 8 hours | Medical injury | OHS Act Sec 8, Construction Regulations 13, the project Health and Safety Specification; this Baseline Risk Assessment | 3 | C | III | Mostly effective | Contractor to develop excavation procedure; Contractor to appoint excavation supervisor to inspect the excavations on regular basis; Contractor to protect the excavations with solid barricading accompanied by warning signs. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act; CR 13(2-j) | TBA | Pending,
|  | 32 | Mobile Plant (e.g. graders, TLB etc); | 32.1 | Struck by; Noise; Dust; Whole body vibrations | Safety or health | Failure to develop / inadequate site traffic plan; Untrained / inexperience operator; Failure to appoint competent flagmen; Failure to follow instructions; Failure to conduct Occupation Hygiene surveys; Failure to provide PPE and enforce the recommendations of the OH surveys | Yardworks Team | PM | 8 hours | Fatality | Construction Regulations 23 (1)(d): Health and Safety Specification Form 74 (Construction Vehicles and Mobile Plant); Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50, Section 4.4.2.1 on Medical Surveillance; this Baseline Risk Assessment; Construction Regulations 13; | 5 | C | II | Mostly effective | Contractor shall appoint competent operator; Contractors shall ensure reverse hooter is installed on the machinery; Contractor shall ensure a flagman is designated; Contractor shall ensure effective traffic management plan; Contractoe to ensure Log-Out-Tag-Out procedure is in place and adhered to; Contractor shall conduct a risk assessment and communicate the results & controls thereof to workers; Contractor shall enforce the use of Hearing and Respiratory Protective Devices/Equipment. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act Health & Safety Specification Form 74; Construction Regulations 23 | TBA | Pending,
|  | 33 | Roller / wacker (during compaction of filling material) | 33.1 | Struck by; | Safety | Use of equipment by incompetent operator; Incorrect use of equipment; Failure to conduct risk assessment; | Yardworks Team | PM | 8 hours | LTI | OHS Act Sec 8; Construction Regulations 24; the project Health and Safety Specification; this Baseline Risk Assessment | 4 | C | II | Mostly effective | Contractor shall appoint a competent operator; Contractor to conduct equipment risk assessment and communicate results & recommended controls thereof to the operator. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act | TBA | Pending,
|  |  |  | 33.2 | Repetitive strain injuries | Safety | Prolonged use of wacker machine; Inadequate training for operators; Use of compaction equipment without suitable and adequate PPE | Wacker operators | PM | 8 hours | LTI | OHS Act Sec 8; General safety Regulations 2; the project Health and Safety Specification; this Baseline Risk Assessment | 4 | C | II |  | Contractor shall develop and implement additional controls and rating post implementation of these additional controls.
|  | 34 | Troxler Machine | 34.1 | Exposure to radiation | Health | Failure to train / inform; Failure to dermacate no-go zone for unauthorised personnel; Failure to provide adequate storage facilities; Inadequate supervision. | Yardworks Team | PM | 8 hours | LTI | Contractor shall procure the services of a competent person to operate troxler; Contractor shall determine the level of radiation emitted by the troxler; Post signage and demarcate the area where the troxler is being used; Provide direct supervision; Work rotation; Provide awareness on the troxler during toolbox talks. | 4 | B | III | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act HCSR | TBA | Pending,
Foundations Works (e.g. Main bases, equipment bases, busbar support foundations, floodlights and earthwire supports) | R | 35 | Open Excavations | 35.1 | Collapse of excavation walls | Safety | Soft and unstable excavation walls Unsupported or unstabilized weak excavation walls. | Foundation and other relevant teams | PM | 8 hours | Fatality | OHS Act Sec 8, Construction Regulations 9, Health and Safety Specification and this Baseline Risk Assessment | 5 | C | II | Mostly effective | Contractor shall ensure soil study before excavation activity; Contractor shall ensure that weak and soft excavation is effectively stabibilized and supported e.g. bracing, shoring, battering, etc | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act; Construction Regulations 13; this Baseline Risk Assessment; the project Health and Safety Specification | TBA | Pending,
|  |  |  | 35.2 | Falling into | Safety | Unbarricaded open excavation; Failure to warn of danger | Foundation team; visitors and other project team memmbers | PM | 8 hours | LTI | OHS Act Sec 8, Health and Safety Specification, this Baseline Risk Assessment | 4 | C | II | Mostly effective | Contractor shall ensure that solid barricadings accompanied by warning signs are installed around the excavations. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act; Construction Regulations 13; this Baseline Risk Assessment; the project Health and Safety Specification | TBA | Pending,
|  |  |  | 35.3 | Accumulation of natural gasses leading to asphyxiation to operators | Safety | Failure to perform Oxygen tests in the excavation | Foundation team; visitors and other project team memmbers | PM | 8 hours | Fatality | OHS Act Sec 8, Health and Safety Specification, this Baseline Risk Assessment | 4 | C | II | Mostly effective | Contractor shall ensure that continuous oxygen tests are performed before and during works in the excavation | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act; Construction Regulations 13; this Baseline Risk Assessment; the project Health and Safety Specification | TBA | Pending,
|  | 36 | Wet Concrete/cement | 36.1 | Concrete burns | Safety | Failure to train / warn of hazards; Lack of supervision; Lack of knowledge; Lack of/Inadequate PPE. | Foundation and other relevant teams | PM | 8 hours | LTI | Persons mixing concrete to use proper PPE including gumboots safety gogggles, long PVC gloves, respiratory protection etc; Training of supervisors, and awareness training of relevant employees on Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 6.6 Concrete Foundations; Supervisor to be present during delivery to ensure that raw material deliverd to site is up to specifications. | 4 | B | III | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act Eskom's Personal Protective Equipment Specification 240-44175132 Eskom's Medical Surveillance Procedure 240-84733329. | TBA | Pending,
|  | 37 | Dry Cement (dust) | 37.1 | Lung/respiratory infections/diseases | Health | Inadequate risk assessment; Failure to warn of danger Lack of supervision; Failure to use appropriate respiratory protective equipment. | Foundation and other relevant teams | PM | 8 hours | LTI | Contractor to conduct a health risk assessment; Inform employees of hazards caused by concrete; Provide direct supervision; Provide suitable PPE (dust masks, full body PVC suit). | 4 | B | III | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act GSR 2 Eskom's Personal Protective Equipment Specification 240-44175132 | TBA | Pending,
|  | 38 | Pinch points from Formwork/shuttering | 38.1 | hand/finger injuries | Safety | Inadequate/ineffective risk assessment; Failure to warn and inform workers of risks at hand; Failure to wear correct PPE recommended by the relevant risk assessment; Poor supervision. | Foundation and other relevant teams | PM | 8 hours | LTI | OHS Act Section 8; General Safety Regulations 2; the project Health and Safety Specification; this Baseline Risk Assessment | 4 | C | III | Mostly effective | Contractor shall conduct risk assessment from which control and PPE shall be recommended and communicated with workers; Contractor shall ensure effective supervision. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act CR 13-2-i | TBA | Pending,
|  | 39 | Flying objects and particles from Blasting | 39.1 | Injuries to persons and damage to property, | Safety | Failure by Contrator / blasting service provider to determine the danger area, as well as authorised entry / exit points; Failure to ensure that the safe distances are applied for the relevant explosive category; Failure to use the services of a competent service provider for blasting, and appoint competent and certificated person. Failure to communicate blasting information/warning. | Foundation and other relevant teams | PM | 8 hours | Fatality | Contractor / blasting service provider shall determine the danger area, as well as authorised entry / exit points; Contractor shall only use the services of a competent service provider for blasting; Contractor to ensure that the safe distances are applied for the relevant explosive category; Contractor to ensure warning/information is communicated to those who may be affected; Explosives Regulations 6, 11 and 12 | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act; Explosives Regulations 6, 11 and 12 | TBA | Pending,
Erection/loading/off-loading/ installation of Fire Protection (fire walls) Manholes & sumps; piping; oil holding dams; transformer / Reactor bay; | R | 40 | Use of crane (mechanical lifting)for loading/offloading/installation/ erection of materials and equipment | 40.1 | Lifting equipment failure; | Safety | Indequate maintenance of lifting equipment; Using underated lifting equipment (due to lack of training of rigger); Untrained / inexperienced operator. | Fire fighting team | PM | 8 hours | Fatality | Appoint competent slinger (SANS 12480-1 Section 5.4 (slinger); Appoint competent crane operator (SANS 12480-1 Section 5.3: Crane driver & Section 5.3.3: Training of crane driver); Develop a maintenance schedule as per manufacturer's manual; Obtain the services of a competent person to test / maintain lifting equipment; Train supervisors, operators, employees on safe work procedures. | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act SANS 12480-1 | TBA | Pending,
|  | 41 | Open excavation | 41.1 | Collapse; Fall into; Engulfment | Safety | Type of soil structure; Failure to batter sides and ends; Failure to support with timber, sheeting or other support systems; Inadequate / No shoring; Inadequate safety signage | Fire fighting team | PM | 8 hours | Fatality | The Contractor to submit the proposed foundation and soil type nomination schedules to the Design Engineer as per Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 6.5.1; Contractor to ensure excavation is adequately shored and braced as per Construction Regulations 13 | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 6.5.1 CR 13 | TBA | Pending,
|  | 42 | Moving machinery (graders, TLB etc) | 42.1 | Struck by; Noise; Dust; Whole body vibrations | Safety or health | Failure to develop / inadequate site traffic plan; Untrained / inexperience operator; Failure to appoint competent flagmen; Failure to conduct Occupation Hygiene surveys; Failure to provide PPE and enforce the recommendations of the OH surveys | Fire fighting team | PM | 8 hours | Fatality | Contractor shall develop a site specific traffic plan, as per Section 49 of SHE Specification Form 74 (Construction Vehicles and Mobile Plant); Constraction vehicle operators shall be trained Construction Regulations 23 (1)(d): Construction Vehicles & Mobile Plant; Contractor shall appoint a competent person as flagman, as per Section 49 of SHE Specification Form 74 (Construction Vehicles and Mobile Plant); Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50, Section 4.4.2.1 on Medical Surveillance; Contractor to ensure that contractor supervisors and employees are trained in safe work procedures; Provide adequate PPE, including dust masks and hearing protection; Work rotation to reduce exposure to vibration. | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act; SHE Specification Form 74 ; Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50; CR | TBA | Pending,
Drainage system erection | R | 43 | Trenching | 43.1 | Collapse of trench; Fall into; Engulfment | Safety | Type of soil structure; Failure to batter sides and ends; Failure to or inadquate shoring. | Excavation team | PM | 8 hours | Fatality | The Contractor to submit the proposed foundation and soil type nomination schedules to the Design Engineer as per Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 6.5.1; Contractor to ensure excavation is adequately shored and braced as per Construction Regulations 13 | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 6.5.1 CR 13 | TBA | Pending,
|  | 44 | Storm water pipe laying/storage | 44.1 | Pipe roll and crush employees | Safety | Inadequate risk assessment; Failure to train / inform employees to put stoppers underneath pipes. | Excavation team | PM | 8 hours | LTI | Contractor shall develop a safe work procedure; Contractor shall instruct employees to put stoppers underneath pipes, as per risk assessment. | 4 | B | III | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act CR 9 | TBA | Pending,
|  | 45 | Roller / wacker during compacting of filling material. | 45.1 | Crushing | Safety | Untrained operator; Lack of attention. | Excavation team | PM | 8 hours | LTI | User of wacker shall be trained and competent to use it; Regular breaks and job rotation. | 4 | B | III | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act | TBA | Pending,
Construction of Transformer / Reactor Plinths | R | 46 | Moving machinery (Cranes, construction vehicles, etc) | 46.1 | Struck by; Failure of lifting equipment | Safety | Failure to develop / inadequate site traffic plan; Untrained / inexperience operator; Failure to appoint competent flagmen; Indequate maintenance of lifting equipment; Using underated lifting equipment. | Reactor Plinth team | PM | 8 hours | Fatality | Contractor shall develop a site specific traffic plan, as per Section 49 of SHE Specification Form 74 (Construction Vehicles and Mobile Plant); Constraction vehicle operators shall be trained Construction Regulations 23 (1)(d): Construction Vehicles & Mobile Plant; Contractor shall appoint a competent person as flagman, as per Section 49 of SHE Specification Form 74 (Construction Vehicles and Mobile Plant); Contractor to ensure that contractor supervisors and employees are trained in safe work procedures; . | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act SHE Specification Form 74 CR 23 (1)(d) | TBA | Pending,
|  | 47 | Offloading material using lifting equipment | 47.1 | Struck by; Failure of lifting equipment; | Safety | Untrained / inexperience operator; Failure to appoint competent flagmen; Indequate maintenance of lifting equipment; Using underated lifting equipment. | Reactor Plinth team | PM | 8 hours | Fatality | Appoint competent slinger (SANS 12480-1 Section 5.4 (slinger); Appoint competent crane operator (SANS 12480-1 Section 5.3: Crane driver & Section 5.3.3: Training of crane driver); Develop a maintenance schedule as per manufacturer's manual; Obtain the services of a competent person to test / maintain lifting equipment; Train supervisors, operators, employees on safe work procedures. | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act SANS 12480-1 | TBA | Pending,
|  | 48 | Ergonomics (during assembly of steel structure) | 48.1 | Muscular skeletal disorders | Safety | Awkward body position Repetitive body motion caused by bending and twisting actions Inadequate training and underlying medical conditions | Reactor Plinth team | PM | 8 hours | LTI | Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50, Section 4.4.2.1 on Medical Surveillance; Conduct health risk assessment and communicate hazards to employees; Awareness training on correct lifting techniques; Job rotation and work rest periods | 4 | B | III | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50, Section 4.4.2.1 on Medical Surveillance CR 9 | TBA | Pending,
Digging cable trenches, ducts, junctions and ramps | R | 49 | Picks, shovels, etc | 49.1 | Struck by | Safety | Lack of attention / concentration; Awkward position Inadequate hand tool inspection / maintanance | Trenching team | PM | 8 hours | LTI | Supervision; Job rotation and regular work rest periods. | 4 | B | III | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act | TBA | Pending,
Installation of support steel | R | 50 | Moving machinery (Cranes, construction vehicles, etc) | 50.1 | Struck by | Safety | Failure to develop / inadequate site traffic plan; Untrained / inexperience operator; Failure to appoint competent flagmen; Lack of operator training; Lack of concentration; Failure to demarcate walk areas. | Installation team | PM | 8 hours | Fatality | Contractor shall develop a site specific traffic plan, as per Section 49 of SHE Specification Form 74 (Construction Vehicles and Mobile Plant); Constraction vehicle operators shall be trained Construction Regulations 23 (1)(d): Construction Vehicles & Mobile Plant; Contractor shall appoint a competent person as flagman, as per Section 49 of SHE Specification Form 74 (Construction Vehicles and Mobile Plant); Contractor to ensure that contractor supervisors and employees are trained in safe work procedures; | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act CR 23-1-d SHE Specification Form 74 | TBA | Pending,
|  | 51 | Offloading material using lifting equipment | 51.1 | Struck by; Failure of lifting equipment | Safety | Untrained / inexperience operator; Failure to appoint competent flagmen; Indequate maintenance of lifting equipment; Using underated lifting equipment. | Installation team | PM | 8 hours | Fatality | Appoint competent slinger (SANS 12480-1 Section 5.4 (slinger); Appoint competent crane operator (SANS 12480-1 Section 5.3: Crane driver & Section 5.3.3: Training of crane driver); Train and appoint competent flagmen; Develop a maintenance schedule as per manufacturer's manual; Train supervisors, operators, employees on safe work procedures. | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act SANS 12480-1 | TBA | Pending,
|  | 52 | Ergonomics (during assembly of steel structure) | 52.1 | Musculor skeletal disorders | Health | Awkward body position; Repetitive body motion caused by bending and twisting actions; Inadequate training and underlying medical conditions. | Installation team | PM | 8 hours | LTI | Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50, Section 4.4.2.1 on Medical Surveillance; Conduct health risk assessment and communicate hazards to employees; Awareness training on correct lifting techniques; Job rotation and work rest periods | 4 | B | III | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50 | TBA | Pending,
|  | 53 | Lifting equipment eg cranes (during erection of support steel | 53.1 | Failure of lifting equipment | Safety | Untrained / inexperience operator; Indequate maintenance of lifting equipment; Failure to follow or inadequate safe work procedures; Using underated lifting equipment (due to untrained rigger). | Installation team | PM | 8 hours | Fatality | Appoint competent slinger (SANS 12480-1 Section 5.4 (slinger); Appoint competent crane operator (SANS 12480-1 Section 5.3: Crane driver & Section 5.3.3: Training of crane driver); Train and appoint competent flagmen; Develop a maintenance schedule as per manufacturer's manual; Train supervisors, operators, employees on safe work procedures. | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act SANS 12480-1 | TBA | Pending,
Erection/installation of light mast | R | 54 | Moving machinery (Cranes, construction vehicles, etc) | 54.1 | Struck by | Safety | Failure to develop / inadequate site traffic plan; Untrained / inexperience operator; Failure to appoint competent flagmen; Failure to demarcate walk areas; Lack of attention / concentration; Failure to comply with the site traffic plan. | Erection team | PM | 8 hours | Fatality | Contractor shall develop a site specific traffic plan, as per Section 49 of SHE Specification Form 74 (Construction Vehicles and Mobile Plant); Constraction vehicle operators shall be trained Construction Regulations 23 (1)(d): Construction Vehicles & Mobile Plant; Contractor shall appoint a competent person as flagman, as per Section 49 of SHE Specification Form 74 (Construction Vehicles and Mobile Plant); Contractor to ensure that contractor supervisors and employees are trained in safe work procedures. | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act SHE Specification Form 74 CR 23 (1)(d) | TBA | Pending,
|  | 55 | Offloading of material | 55.1 | Material falls onto employees, resulting in injuries | Safety | Use of underated / defective lifting equipment; Failure to maintain lifting equipment; Failure to follow written safe work procedures; Lack of training of operator. | Erection team | PM | 8 hours | Fatality | Appointment of trained and competent riggers and operators; Ensure lifting equipment is tested and maintained by an accredited entity; Traning of supervisors and employees on safe work procedures; Ensure machine operators are adequately trained. | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act SANS 12480-1 Eskom Procedure 39-98 | TBA | Pending,
|  | 56 | Ergonomics (during assembling of steel structure) | 56.1 | Musculor skeletal disorders | Health | Awkward body position Repetitive body motion caused by bending and twisting actions Inadequate training and underlying medical conditions | Erection team | PM | 8 hours | LTI | Awareness training on correct lifting techniques; Job rotation and work rest periods | 4 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act | TBA | Pending,
Installation of lighting and power reticulation | R | 57 | Working at height | 57.1 | Fall from height | Safety | Failure to identify suitable anchor points; Failure to inspect safety harnesses before use; Failure to secure properly ( persons and objects) Lack of training | Erection team | PM | 8 hours | Fatality | Eskom's Life Saving Rules, Rule 1: Open, isolate, earth, test, bond, before touch; Electrical Installation Regulations 2, 5 and 6 | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act CR 10 Eskom Procedure 32-418 | TBA | Pending,
|  | 58 | Electrical reticulation | 58.1 | Electric shocks | Safety | Failure to test before touching; Unskilled / untrained electrician; | Erection team | PM | 8 hours | Fatality | The Contractor to submit the proposed foundation and soil type nomination schedules to the Design Engineer as per Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 6.5.1; Contractor to ensure excavation is adequately shored and braced as per Comstruction Regulations 13 | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act EIR Eskom's Life Saving Rules | TBA | Pending,
Erection of fencing (inner and outer security fences) | R | 59 | Digging/Excavating (manual/mechanical) | 59.1` | Physical injuries e.g. muscle sprains | Safety | Incorrect use of digging/excavating equipment/tool; | Fence erection team | PM | 8 hours | Fatality | OHS Act Section 8; General Safety Regulations 2; the project Health and Safety Specification; this Baseline Risk Assessment | 4 | C | II | Mostly effective | Contractor shall develop a Health and Safety Plan and submit it to the Client for evaluation/vetting. Contractor to conduct effective risk assessment which among others will give guidance on correct training and PPE required or to be provided to workers. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act Health & Safety Specification; this Baseline Risk Assessment; CR 13 | TBA | Pending,
|  | 60 | Wet Concrete | 60.1 | Concrete burns; | Safety | Direct skin contact with wet concrete; Failure to train / warn of hazards; Lack of supervision; Lack of knowledge; Failure to put on correct PPE. | Fence erection team | PM | 8 hours | LTI | OHS Act Section 8; General Safety Regulations 2; the project Health and Safety Specification; this Baseline Risk Assessment | 4 | C | II | Mostly effective | Contractor shall develop a risk assessment and communicate its results and controls to workers; Correct PPE shall be provided to workers by the contractor; | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50 Eskom's Personal Protective Equipment Specification 240-44175132 | TBA | Pending,
|  | 61 | Planting of fence poles | 61.1 | Struck by swinging pole | Safety | Failure to ensure a controlled planting of poles; Poor communication; Incorrect method of planting poles; Lack of attention / concentration. | Fence erection team | PM | 8 hours | Medical Injury | OHS Act Section 8; General Safety Regulations 2; the project Health and Safety Specification; this Baseline Risk Assessment | 3 | C | II | Mostly effective | Contractor shall develop a Health and Safety Plan in which correct methods of planting poles/fence erection shall be outlined; Effective risk assessment for the activity shall be developed and communicated with workers; | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act; Health & Safety Specification Form 74; this Baseline Risk Assessment | TBA | Pending,
|  | 62 | Handtools, e.g. pliers | 62.1 | Caught-in between | Safety | Lack of attention / concentration; Awkward position; Inadequate hand tool inspection / maintanance | Erection team | PM | 8 hours | LTI | Supervision; Job rotation and regular work rest periods; Supervisor to ensure that tools being used are properly maintained; Ensure proper work design to eliminate awkward positions. | 4 | B | III | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act | TBA | Pending,
|  | 63 | Ergonomic hazards | 63.1 | Musculoskeletal disorders | Health | Awkward body position Repetitive body motion caused by bending and twisting actions; Inadequate training and underlying medical conditions; lncorrect lifting techniques; Overexertion. | Construction team | PM | 8 hours | LTI | OHS Act Section 8; General Safety Regulations 2; the project Health and Safety Specification; this Baseline Risk Assessment | 4 | B | III | Mostly effective | Contractor shall develop egornomic risk assessment and communicate its results and recommendations with workers; Contractor shall adopt good egornomic regimes such as job rotation; | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act Health and safety Specification Form 74 Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50 This Baseline Risk Assessment; Eskom's Personal Protective Equipment Specification 240-44175132 | TBA | Pending,
Building works | R | 64 | Offloading of equipment / material | 64.1 | Equipment / material dislodged and fall onto employees | Safety | Failure to secure equipment / material properly; Untrained / inexperienced lifting equipment operator; Failure to follow safe work procedure. | Construction team | PM | 8 hours | Fatality | Supervisor shall ensure that pipes are properly secured before lifting; Only trained and experienced lifting equipment operators shall do the lifting, under direct supervision; Contractor shall develop safe work procedures for lifting, and train / inform employees accordingly. | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act SANS 12480-1 | TBA | Pending,
|  | 65 | Working at heights | 65.1 | Fall from height | Safety | Failure to identify suitable anchor points; Failure to inspect safety harnesses before use; Failure to secure proprely ( persons and objects) Lack of / inadequate training | Construction team | PM | 8 hours | Fatality | Ensure direct competent supervision for work at height activities; Supervisor shall identify suitable anchor points; Appoint competent gear controller to manage all safety harnesses and ensure they are inspected before use; Ensure all climbers are trained by an accredited service provider. | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act Eskom Working at Heights Procedure 32-418 | TBA | Pending,
|  | 66 | Moving machinery (Cranes, construction vehicles, etc) | 66.1 | Struck by; Dust; Noise | Safety | Failure to develop / inadequate site traffic plan; Untrained / inexperience operator; Failure to appoint competent flagmen; Failure to follow instructions; Failure to conduct Occupation Hygiene surveys; Failure to provide PPE and enforce the recommendations of the OH surveys | Construction team | PM | 8 hours | Fatality | Contractor shall develop a site specific traffic plan, as per Section 49 of SHE Specification Form 74 (Construction Vehicles and Mobile Plant); Constraction vehicle operators shall be trained Construction Regulations 23 (1)(d): Construction Vehicles & Mobile Plant; Contractor shall appoint a competent person as flagman, as per Section 49 of SHE Specification Form 74 (Construction Vehicles and Mobile Plant); Contractor to ensure that contractor supervisors and employees are trained in safe work procedures; Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50, Section 4.4.2.1 on Medical Surveillance, to determine any underlying medical conditions; Conduct health risk assessment and communicate hazards to employees; provide PPE and enforce the recommendations of the OH surveys | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act SHE Specification Form 74 CR 23 (1)(d) Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50 | TBA | Pending,
|  | 67 | Ergonomics | 67.1 | Musculoskeletal disorders | Health | Awkward body position; Repetitive body motion caused by bending and twisting actions; Inadequate training and underlying medical conditions; lncorrect lifting techniques; Overexertion. | Construction team | PM | 8 hours | LTI | Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50, Section 4.4.2.1 on Medical Surveillance, to determine any underlying medical conditions; Conduct health risk assessment and communicate hazards to employees; Train / inform employees on good ergonomics; Provide supervision and awareness training for cement work; Job rotation; Persons mixing concrete to use proper PPE including gumboots, safety gogggles, long PVC gloves, respiratory protection etc; | 4 | B | III | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act SHE Specification Form 74 CR 23 (1)(d) Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-51 | TBA | Pending,
External works | R | 68 | Offloading of equipment | 68.1 | Equipment dislodged and fall onto employees | Safety | Failure to secure equipment / material properly; Untrained / inexperienced lifting equipment operator; Failure to follow safe work procedure. | Construction team | PM | 8 hours | Fatality | Awareness training on use of HCS; Provide MSDS for all HCS used on site; Provide HCS with adequate storage facilities; Provide suitable PPE (respirators, PVC suits, as may be applicable. | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act SANS 12480-1 | TBA | Pending,
|  | 69 | Ergonomic hazards | 69.1 | Musculoskeletal disorders | Health | Awkward body position; Repetitive body motion caused by bending and twisting actions; Inadequate training and underlying medical conditions; lncorrect lifting techniques; Overexertion. | Construction team | PM | 8 hours | LTI | Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50, Section 4.4.2.1 on Medical Surveillance, to determine any underlying medical conditions; Conduct health risk assessment and communicate hazards to employees; Train / inform employees on good ergonomics; Provide supervision and awareness training for cement work; Job rotation; Persons mixing concrete to use proper PPE including gumboots, safety gogggles, long PVC gloves, respiratory protection etc; | 4 | B | III | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act SHE Specification Form 74 CR 23 (1)(d) Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50 | TBA | Pending,
|  | 70 | Weedkillers under yardstone | 70.1 | Chemical poisoning | Health | Failure to train / inform; Failure to provide MSDS; Failure to provide adequate storage facilities; Failure to provide PPE | Construction team | PM | 8 hours | LTI | Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50, Section 4.4.2.1 on Medical Surveillance, to determine any underlying medical conditions; Conduct health risk assessment and communicate hazards to employees; Provide supervision during disc cutting operations; Job rotation; Employees using disc cutters shall be provided with suitable PPE (hearing protection, etc) | 4 | B | III | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act HCSR Eskom's Personal Protective Equipment Specification 240-44175132 | TBA | Pending,
Laying of kerbs and channels | R | 71 | Kerb Works/Handling/carrying | 71.1 | Muscle injuries/backaches | Safety | Awkward body position; lncorrect lifting techniques; Overexertion. | Construction team | PM | 8 hours | LTI | Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50, Section 4.4.2.1 on Medical Surveillance; OHS Act Sec 8; Good lifting/carrying techniques. | 4 | B | III | Mostly effective | Contractor shall ensure good ergonomic regimes e.g. job rotation, regular breaks etc; Contractor to ensure good lifting/carrying techniques training to his employees. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50 Eskom's Personal Protective Equipment Specification 240-44175132 | TBA | Pending,
|  | 72 | Cutting/breaking kerbs | 72.1 | Noise induced hearing loss; Lung/respiratory diseases; | Health | Exposure to equipment noise over 85dB; Inhalation of dust silica. | Construction team | PM | 8 hours | SI | Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50, Section 4.4.2.1 on Medical Surveillance; OHS Act Sec 8; the project Health and Safety Specification; | 4 | B | III | Mostly effective | Contractor shall develop adequate risk assessment and communicate the results and controls thereof to his workers. Training on the correct use of cutting/breaking equipment shall be provided; Contractor shall provide to his workers training on the correct use and maintenance of both hearing and respiratory Protective device/equipment (HPD/RPE) | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50 Eskom's Personal Protective Equipment Specification 240-44175132 | TBA | Pending,
Reinforcement (rebar) installation | R | 73 | Rebar works (Manual work/handling) | 73.1 | Injury to hands/fingers (cuts & pinches) | Safety | Sharp ends of the rebars; Wires; cutting tools e.g. plier | Construction team | PM | 8 hours | LTI | OHS Act Sec 8; the project Health and Safety Specification | 4 | B | III | Mostly effective | Contractor shall conduct adequate risk assessment to identify all hazards & Inform employees of the associated risks and how to control/mitigate them | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act Sec 8; Construction Regulations 9; Eskom's Personal Protective Equipment Specification 240-44175132 | TBA | Pending,
|  |  |  | 73.2 | Trips | Safety | Bad housekeeping for rebars | Construction team | PM | 8 hours | LTI | OHS Act Sec 8, General Safety Regulations 8, Construction Regulations 28 and the project Health and Safety Specification | 4 | B | III | Mostly effective | Contractor shall adopt and maintain good housekeeping practice. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act Sec 8; Construction Regulations 9; Eskom's Personal Protective Equipment Specification 240-44175132 | TBA | Pending,
|  |  |  | 73.3 | Muscle injuries/backaches | Safety | Awkward body position e.g. body bending; carrying heavy rebar system/sets e.g. rebar cage or bundle | Construction team | PM | 8 hours | LTI | OHS Act Sec 8; the project Health and Safety Specification; Good lifting/carrying techniques | 4 | C | III | Mostly effective | Contractor shall adopt and practice good ergonomic regimes; Contractor shall use mechanical means for carrying/lifting heavy rebars; Contractor shall provide training to his employees on good lifting/carrying techniques. | Eskom Inspections and Audits on Contractor | PM/Construction manager/supervisor | OHS Act Sec 8; Eskom Occupational Hygiene Management Guideline PDPMAN-GL-50 Eskom Personal Protective Equipment Specification 240-44175132 | TBA | Pending,
Interaction between persons | R | 74 | COVID 19 (Corona Virus) | 74.1 | Cross infection | Health | Coming into contact with an infected person / contaminated surface; Contact with airborne particles; Lack of awareness on the disease; Poor hygiene practices | Construction team | Responsible Managers & all employees | 8 hours | Epidiomological treatment case | Tactical Command Centre (TCC) Eskom Emergency Protocols activated; Work from home; Home / hospital quarantine; Restrict unnecessary visits / contacts; Awareness campaigns; Practice good hygiene; Wear appropriate risk based PPE (respiratory masks, gloves); | 4 | C | III | Mostly effective | External medical services (Public and private); Hand and surface sanitisers | Statistics from Health and Wellness; NCID- National Centre for Infectious Diseases | Responsible Managers | 240-100092892 Outbreak, Pandemic or Epidemic Disaster Response Plan; Disaster Management Act 57 of 2002 | TBA | Pending,
Voltage transformers
Check for equipment manual | N | 19 | Improper assembly | 19.1 | Defective equipment | Safety | Lack of concentration Non-compliance to procedures Inadequate supervision Inadequate inspection | Civil team | PM | 8 hours daily | Fatality | SHE Specification Form 74 | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Connect Sterm | N | 20 | Hand tools | 20.1 | Contact with | Safety | Lack of concentration Non-compliance to procedures Inadequate supervision Inadequate inspection PPE not worn Inadequate experience/training | Civil Team | PM | 8 hours daily | Medical Incident | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) SANS 1200 ALL PARTS Project specific drawings | 3 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Sling first part of the CVT, Lift up, Connect to middle part, Lift complete CVT, connect to base and secure | N | 21 | Deviation from approved lifting methodology | 21.1 | Falling material Load shifting Failure of equipment / tackle | Safety | Incorrect slinging Exceeding load limits Inadequate inspection Inadequate training Lack of supervision | Operators Riggers Erection team Bystanders | PM | 8 hours daily | Fatality | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Safe use of lifting machines and lifting tackles (39-98) Employee’s right of refusal to work in an unsafe situation Procedure (240-43848327) | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Inexperienced equipment operator(s)(Applicable to all substation work) | 21.2 | Lose control of equipment Falling material | Safety | Inadequate training / experience Lack of supervision Underlying medical condition | (Applicable to all substation work) | PM | 8 hours daily | Fatality | SHE Specification Form 74 Medical Surveillance Procedure (32-282) Safe use of lifting machines and lifting tackles (39-98) Project specific drawings SANS 1200 ALL PARTS Employee’s right of refusal to work in an unsafe situation Procedure (240-43848327) | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Suspended load | 21.3 | Exposure to falling objects Falling from height | Safety | Failure of lifting equipment Improperly secured load Elevated position Not following procedures Inadequate training | Erection Team Bystanders | PM | 8 hours daily | Fatality | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Safe use of lifting machines and lifting tackles (39-98) Project specific drawings SANS 1200 ALL PARTS Employee’s right of refusal to work in an unsafe situation Procedure (240-43848327) | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Unstable terrace / platform | 21.4 | Crane overturn | Safety | Sinking terrace Poor compaction Fill material used not according to specification Inadequate method statement or Noncompliance to method statement | Operator Riggers Bystanders | PM | 8 hours daily | Fatality | Mandatory SHE Specification to be met by contractors and suppliers during refurbishment and construction (PDPMAN-ST-001) SANS 1200 ALL PARTS Project specific drawings | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Earth wire
Drums placement and storage | N | 32 | Rotten Drums | 32.1 | Collapsed drums | Safety | Untreated wood Wood rot Improper storage | Installers Bystanders Crane operators | PM | 8 hours daily | LTI | SHE Specification Form 74 Safe use of lifting machines and lifting tackles (39-98) | 4 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Unsecured Drums | 32.2 | Drums may roll over | Safety | Stop blocks/ Wedge / Chocks not in place Uneven surface | Installers Bystanders | PM | 8 hours daily | Fatality | SHE Specification Form 74 Safe use of lifting machines and lifting tackles (39-98) | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Place drums on cable Jacks | N | 33 | Unsecured Drums | 33.1 | Drums may fall from jacks | Safety | Incorrect Lifting techniques Uneven surface | Installers | PM | 8 hours daily | LTI | SHE Specification Form 74 Safe use of lifting machines and lifting tackles (39-98) | 4 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Jack Failure | 33.2 | Jack and drum collapse | Safety | Exceeding safe workload Lack of Inspections / maintenance Uneven surface Incorrect Lifting techniques Defective Jacks | Installers Bystanders | PM | 8 hours daily | LTI | SHE Specification Form 74 Safe use of lifting machines and lifting tackles (39-98) | 4 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Remove cover material (Wood) | N | 34 | Fragmented Wood splinters | 34.1 | Contact with splinters | Safety | Lack of PPE; Lack of concentration | Installer | PM | 8 hours daily | Medical Incident | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Safe use of lifting machines and lifting tackles (39-98) | 3 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Protruding nails | 34.2 | Stepping on nails | Safety | Incorrect PPE Lack of concentration Poor housekeeping Non- Compliance to Procedure Inadequate Risk assessment | Installer | PM | 8 hours daily | Medical Incident | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) | 3 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Dismantling old busbars and insatll new busbars / isolators/ breakers | N | 41 | Cherry Picker | 41.1 | Equipment failure | Safety | Improper maintenance; Failure to train operator; Inadequate supervision; Inadequate safe work procedute; Inadequate risk assessment; | Installation team | PM | 8 hours daily | Fatality | Eskom Work ar Height Procedure; Proper training of operators; Aduquate supervison; Develop adequate safe work procedute; Conduct adequate risk assessment; | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Working in close proximity to live equipment | 41.2 | Electrical contact | Safety | Failure to identify and observe safety clearance; Failure to barricade; Inadequate earthing; Inadequate communication between PDP Project Team and Distribution / Transmission; Inadequate PPE; Inadequate training; Deviation from permit to work process; Inadequate formal risk assessment and failure to communicate effectively prior to work commencement; Unauthorised / responsible persons permitted to apply and remove a portable working earth; Improper positioning of portable earths relevant to the work not scrutinised and if they interfere with the work area, be reported to the authorised/ responsible person, prior to commencement of work. Only the Engineering Assistant (EA) may remove / relocate the control earths. Be your brother’s keeper | Installation team | PM | 8 hours daily | Fatality | Identify and observe safety clearance; Erect effective barricing; Install adequate earthing; Ensure adequate communication between PDP Project Team and Distribution / Transmission; Provide adequate PPE; Provide adequate training on Eskom's ORHVS and provide adequate supervision; Inadequate safe work procedute; Inadequate risk assessment; Training on permit to work process; Adequate formal risk assessment and communication prior to work commencement; Authorised / responsible persons only to apply and remove a portable working earth; Proper positioning of portable earths relevant to the work area, be reported to the authorised/ responsible person, prior to commencement of work; Only the Engineering Assistant (EA) may remove / relocate the control earths. Be your brother’s keeper | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations

## Contractor Baseline template
Occupational Health and Safety Baseline risk assessment template
Business/Operating unit: | [9 empty] | Next Review Date (every 2 years): | Template identifier:
Date: |  |  |  |  | Authorised by: |  | Name: |  |  | Document identifier | [8 empty] | R | Safety | 1 | A | Fully effective | I
[7 empty] | Designation: |  |  | Revision number: | 1 | [7 empty] | N | Health | 2 | B | Mostly effective | II
[7 empty] | Signed: |  |  | Revision date: | 2024-05-31 | [9 empty] | 3 | C | Mostly ineffective | III
[7 empty] | Date: | [13 empty] | 4 | D | None | IV
Refer to Occupational Health and Safety Risk assessment procedure 32-520 | [20 empty] | 5 | E
List activity | Hazard Identification | Associated risk | Risk type | What are the possible consequences? | Existing Controls |  |  | Risk Priority Rating |  | Control Owner | Legal and Other Requirements | [9 empty] | 6
List specific activities to be performed taking into consideration the equipment to be used, the personnel involved in the task. | Anything with potential to cause of harm. Note: A hazard can pose more than one risk. | A chance that injury , ill health or damage could occur as a result of uncontrolled hazard. | Safety or health | Consider the worse case scenario without controls? | Include: - Preventative Controls (controls implemented to eliminate hazards or reduce the likelihood of the risk occurring), and - Reactive Controls (controls implemented to reduce the immediate impact of the risk occurring) Elimination Substitution Engineering controls Administrative controls Personal protective equipment (PPE) | Consequence | Likelihood |  | RCE Risk Control Effectiveness | Person allocated the responsibility for implementing the agreed controls | Where relevant, list the relevant legislative and or Eskom requirements that prescribe the control. | Consequences | 6 | III | II | I | I | I
Identification and demarcation of protected and/or listed vegetation at the identified construction location. | Uneven surfaces (rocks, tree stumps, etc) | Slips, trips and falls | Safety | Medical injury | Awareness training during inductions for employees and visitors tobe aware of their surroundings, i.e tree stumps, loose rock material, and other obstacles. | 3 | B | III | Mostly effective | PM/Construction manager/supervisor | OHS Act; Construction Regulations 7(6); |  | 5 | III | II | II | I | I
[13 empty] | 4 | IV | III | II | I | I
[13 empty] | 3 | IV | III | II | II | I
Bush & shrub clearing and tree felling | Biological hazards; | Snake bites and bee and scorpion stings | Health | LTI | Site specific SHE induction; Appoint snake handlers and persons with knowledge of bees and similar insects; Awareness training on how to react when faced with snakes, bees, scorpions etc; | 4 | B | III | Mostly effective | PM/Construction manager/supervisor | OHS Act; Eskom's Personal Protective Equipment Specification 240-44175132 |  | 2 | IV | IV | III | II | II
[13 empty] | 1 | IV | IV | III | III | III
[14 empty] | A | B | C | D | E
Likelihood
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Access road/offloading pad construction | Ground/earth grading equipment i.e graders | Struck by; Noise; Dust; Equipment vibration; Accidents e.g. overturning (capsizing) | Safety or health | Fatality | Contractor shall develop a site specific traffic plan, as per Section 49 of SHE Specification Form 74 (Construction Vehicles and Mobile Plant); Construction Regulations 23 (1)(d): Construction Vehicles & Mobile Plant; Contractor shall appoint a competent person as flagman, as per Section 49 of SHE Specification Form 74 (Construction Vehicles and Mobile Plant); Contractor to ensure that contractor supervisors and employees are trained in safe work procedures; Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50, Section 4.4.2.1 on Medical Surveillance; | 5 | C | II | Mostly effective | PM/Construction manager/supervisor | OHS Act Section 8 Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50, Section 4.4.2.1 on Medical Surveillance CR 23 (1)(d): Construction Vehicles & Mobile Plant;
Site Establishment | Mobile Plant, e.g. TLB | Struck by; Noise; Dust; Whole body vibrations | Safety or health | Fatality | Contractor shall develop a site specific traffic plan, as per Section 49 of SHE Specification Form 74 (Construction Vehicles and Mobile Plant); Construction Regulations 23 (1)(d): Construction Vehicles & Mobile Plant; Contractor shall appoint a competent person as flagman, as per Section 49 of SHE Specification Form 74 (Construction Vehicles and Mobile Plant); Contractor to ensure that contractor supervisors and employees are trained in safe work procedures; Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50, Section 4.4.2.1 on Medical Surveillance; | 5 | B | II | Mostly effective | PM/Construction manager/supervisor | OHS Act Section 8 Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50, Section 4.4.2.1 on Medical Surveillance CR 23 (1)(d): Construction Vehicles & Mobile Plant;
Surveying & Pegging | Hand tools, eg. Hammer ; | Lack of attention; Incorrect work position; Defective tools. | Safety | Medical injury | Awareness training of employees in the use of hand tools like hammers, spanners, chisels etc; Inspection of tools before use; Supervision. | 3 | B | III | Mostly effective | PM/Construction manager/supervisor | OHS Act
Platform / Terrace Earthworks | Mobile Plant, e.g. TLB | Struck by; Noise; Dust; Equipment vibrations | Safety or health | Fatality | Contractor shall develop a site specific traffic plan, as per Section 49 of SHE Specification Form 74 (Construction Vehicles and Mobile Plant); Construction Regulations 23 (1)(d): Construction Vehicles & Mobile Plant; Contractor shall appoint a competent person as flagman, as per Section 49 of SHE Specification Form 74 (Construction Vehicles and Mobile Plant); Contractor to ensure that contractor supervisors and employees are trained in safe work procedures; Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50, Section 4.4.2.1 on Medical Surveillance / Continuous occupational hygiene surverys; Enforce the recommendations of the OH surveys ( eg wearing of PPE like dust masks, ear protection, etc); | 5 | B | II | Mostly effective | PM/Construction manager/supervisor | OHS Act Section 8 Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50, Section 4.4.2.1 on Medical Surveillance CR 23 (1)(d): Construction Vehicles & Mobile Plant;
Excavation / trenching | Collapse of excavation walls (cave-in); | #REF! | Safety | Fatality | The Contractor to submit the proposed foundation and soil type nomination schedules to the Design Engineer as per Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 6.5.1; Contractor to ensure excavation is adequately shored and braced as per Construction Regulations 13 | 5 | B | II | Mostly effective | PM/Construction manager/supervisor | OHS Act Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 6.5.1 (Excavations); Construction Regulations 13
Working with Cement | #REF! | Mesothelioma, Cement burns and Dermatitis | Health | LTI | Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50, Section 4.4.2.1 on Medical Surveillance; Conduct health risk assessment and surveys; Communicate survey results and hazards to employees; Provide awareness training for cement work; Job rotation; Persons mixing concrete to use proper PPE including gumboots, safety gogggles, long PVC gloves, respiratory protection etc; | 4 | C | II | Mostly effective | PM/Construction manager/supervisor | OHS Act Section 8; HCSR; Eskom's Personal Protective Equipment Specification 240-44175132; Eskom's Medical Surveillance Procedure 240-84733329.
Yardworks | Open excavation | Fall into | Safety | Medical injury | OHS Act Sec 8, Construction Regulations 13, the project Health and Safety Specification; this Baseline Risk Assessment | 3 | C | III | Mostly effective | PM/Construction manager/supervisor | OHS Act; CR 13(2-j)
Foundations Works (e.g. Main bases, equipment bases, busbar support foundations, floodlights and earthwire supports) | Open Excavations | Collapse of excavation walls | Safety | Fatality | OHS Act Sec 8, Construction Regulations 9, Health and Safety Specification and this Baseline Risk Assessment | 4 | C | II | Mostly effective | PM/Construction manager/supervisor | OHS Act; Construction Regulations 13; this Baseline Risk Assessment; the project Health and Safety Specification
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Erection/loading/off-loading/ installation of Fire Protection (fire walls) Manholes & sumps; piping; oil holding dams; transformer / Reactor bay; | Use of crane (mechanical lifting)for loading/offloading/installation/ erection of materials and equipment | Lifting equipment failure; | Safety | Fatality | Appoint competent slinger (SANS 12480-1 Section 5.4 (slinger); Appoint competent crane operator (SANS 12480-1 Section 5.3: Crane driver & Section 5.3.3: Training of crane driver); Develop a maintenance schedule as per manufacturer's manual; Obtain the services of a competent person to test / maintain lifting equipment; Train supervisors, operators, employees on safe work procedures. | 5 | B | II | Mostly effective | PM/Construction manager/supervisor | OHS Act SANS 12480-1
Drainage system erection | Trenching | Collapse of trench; Fall into; Engulfment | Safety | Fatality | The Contractor to submit the proposed foundation and soil type nomination schedules to the Design Engineer as per Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 6.5.1; Contractor to ensure excavation is adequately shored and braced as per Construction Regulations 13 | 5 | B | II | Mostly effective | PM/Construction manager/supervisor | OHS Act Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 6.5.1 CR 13
Construction of Transformer / Reactor Plinths | Moving machinery (Cranes, construction vehicles, etc) | Struck by; Failure of lifting equipment | Safety | Fatality | Contractor shall develop a site specific traffic plan, as per Section 49 of SHE Specification Form 74 (Construction Vehicles and Mobile Plant); Constraction vehicle operators shall be trained Construction Regulations 23 (1)(d): Construction Vehicles & Mobile Plant; Contractor shall appoint a competent person as flagman, as per Section 49 of SHE Specification Form 74 (Construction Vehicles and Mobile Plant); Contractor to ensure that contractor supervisors and employees are trained in safe work procedures; . | 5 | B | II | Mostly effective | PM/Construction manager/supervisor | OHS Act SHE Specification Form 74 CR 23 (1)(d)
Digging cable trenches, ducts, junctions and ramps | Picks, shovels, etc | Struck by | Safety | LTI | Supervision; Job rotation and regular work rest periods. | 4 | B | III | Mostly effective | PM/Construction manager/supervisor | OHS Act
Installation of support steel | Moving machinery (Cranes, construction vehicles, etc) | Struck by | Safety | Fatality | Contractor shall develop a site specific traffic plan, as per Section 49 of SHE Specification Form 74 (Construction Vehicles and Mobile Plant); Constraction vehicle operators shall be trained Construction Regulations 23 (1)(d): Construction Vehicles & Mobile Plant; Contractor shall appoint a competent person as flagman, as per Section 49 of SHE Specification Form 74 (Construction Vehicles and Mobile Plant); Contractor to ensure that contractor supervisors and employees are trained in safe work procedures; | 5 | B | II | Mostly effective | PM/Construction manager/supervisor | OHS Act CR 23-1-d SHE Specification Form 74
Erection/installation of light mast | Moving machinery (Cranes, construction vehicles, etc) | Struck by | Erection team | Fatality | Contractor shall develop a site specific traffic plan, as per Section 49 of SHE Specification Form 74 (Construction Vehicles and Mobile Plant); Constraction vehicle operators shall be trained Construction Regulations 23 (1)(d): Construction Vehicles & Mobile Plant; Contractor shall appoint a competent person as flagman, as per Section 49 of SHE Specification Form 74 (Construction Vehicles and Mobile Plant); Contractor to ensure that contractor supervisors and employees are trained in safe work procedures. | 5 | B | II | Mostly effective | PM/Construction manager/supervisor | OHS Act SHE Specification Form 74 CR 23 (1)(d)
Installation of lighting and power reticulation | Working at height | Fall from height | Safety | Fatality | Eskom's Life Saving Rules, Rule 1: Open, isolate, earth, test, bond, before touch; Electrical Installation Regulations 2, 5 and 6 | 5 | B | II | Mostly effective | PM/Construction manager/supervisor | OHS Act CR 10 Eskom Procedure 32-418
Erection of fencing (inner and outer security fences) | Digging/Excavating (manual/mechanical) | Physical injuries e.g. muscle sprains | Safety | Fatality | OHS Act Section 8; General Safety Regulations 2; the project Health and Safety Specification; this Baseline Risk Assessment | 4 | C | II | Mostly effective | PM/Construction manager/supervisor | OHS Act Health & Safety Specification; this Baseline Risk Assessment; CR 13
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
s | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Building works | Offloading of equipment / material | Equipment / material dislodged and fall onto employees | Safety | Fatality | Supervisor shall ensure that pipes are properly secured before lifting; Only trained and experienced lifting equipment operators shall do the lifting, under direct supervision; Contractor shall develop safe work procedures for lifting, and train / inform employees accordingly. | 5 | B | II | Mostly effective | PM/Construction manager/supervisor | OHS Act SANS 12480-1
External works | #REF! | Safety | #REF! | Fatality | Awareness training on use of HCS; Provide MSDS for all HCS used on site; Provide HCS with adequate storage facilities; Provide suitable PPE (respirators, PVC suits, as may be applicable. | 5 | B | II | Mostly effective | PM/Construction manager/supervisor | OHS Act SANS 12480-1
Laying of kerbs and channels | Kerb Works/Handling/carrying | Muscle injuries/backaches | Safety | LTI | Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50, Section 4.4.2.1 on Medical Surveillance; OHS Act Sec 8; Good lifting/carrying techniques. | 4 | B | III | Mostly effective | PM/Construction manager/supervisor | OHS Act Eskom's Occupational Hygiene Management Guideline PDPMAN-GL-50 Eskom's Personal Protective Equipment Specification 240-44175132
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Reinforcement (rebar) installation | #REF! | Injury to hands/fingers (cuts & pinches) | Safety | LTI | Contractor shall conduct adequate risk assessment to identify all hazards & Inform employees of the associated risks and how to control/mitigate them | 4 | B | III | Mostly effective | PM/Construction manager/supervisor | OHS Act Sec 8; Construction Regulations 9; Eskom's Personal Protective Equipment Specification 240-44175132
Interaction between persons | COVID 19 (Corona Virus) | Cross infection | Health | Epidiomological treatment case | Tactical Command Centre (TCC) Eskom Emergency Protocols activated; Work from home; Home / hospital quarantine; Restrict unnecessary visits / contacts; Awareness campaigns; Practice good hygiene; Wear appropriate risk based PPE (respiratory masks, gloves); | 4 | C | III | Mostly effective | Responsible Managers | 240-100092892 Outbreak, Pandemic or Epidemic Disaster Response Plan; Disaster Management Act 57 of 2002
Voltage transformers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Check for equipment manual | Improper assembly | Defective equipment | Safety | Fatality | SHE Specification Form 74 | 5 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
Connect Sterm | Hand tools | Contact with | Safety | Medical Incident | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) SANS 1200 ALL PARTS Project specific drawings | 3 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
Sling first part of the CVT, Lift up, Connect to middle part, Lift complete CVT, connect to base and secure | Deviation from approved lifting methodology | Falling material Load shifting Failure of equipment / tackle | Safety | Fatality | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Safe use of lifting machines and lifting tackles (39-98) Employee’s right of refusal to work in an unsafe situation Procedure (240-43848327) | 5 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
Earth wire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drums placement and storage | Rotten Drums | Collapsed drums | Safety | LTI | SHE Specification Form 74 Safe use of lifting machines and lifting tackles (39-98) | 4 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
Place drums on cable Jacks | Unsecured Drums | Drums may fall from jacks | Safety | LTI | SHE Specification Form 74 Safe use of lifting machines and lifting tackles (39-98) | 4 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
Remove cover material (Wood) | Fragmented Wood splinters | Contact with splinters | Safety | Medical Incident | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Safe use of lifting machines and lifting tackles (39-98) | 3 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
Dismantling old busbars and insatll new busbars / isolators/ breakers | Cherry Picker | Equipment failure | Safety | Fatality | Eskom Work ar Height Procedure; Proper training of operators; Aduquate supervison; Develop adequate safe work procedute; Conduct adequate risk assessment; | 5 | B | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations

## Consequence rating
Consequence criteria
Consequence rating | Description
Health and Safety
1 | No injuries or health effects(near misses)
2 | First-aid treatment case, and temporary discomfort case
3 | Medical treatment case; occupational disease with reversible/non-permanent effect
4 | Lost Time Injury. Irreversible health effects/occupational disease with permanent consequence
5 | Fatality or life threatening health effects
6 | Multiple fatalities

## Likelihood rating
Likelihood criteria
| Score | Descriptor | Safety | Occupational hygiene
|  |  |  | Exposure | Probability of exceeding OEL
| A | Highly unlikely | § More than a “100 year event” | Rare (once a year) | No exposure (or exposure < 10% of OEL)
§ Exceptionally unlikely, even in the long-term future
§ < 5% probability.
| B | Unlikely | § Could occur in “years to decades” | Short periods of time, a few times per day/ intermittent (once in six months, three months, or a month) | Low exposure (< 50% of OEL)
§ May occur but not anticipated
§ ≥ 5% and < 20% probability.
| C | Possible | § Could occur within “months to years” | Continuous for between one and two hours (often/ weekly) | Moderate exposure (chronic exposure > 50% of OEL or acute exposure ≥ OEL)
§ May occur shortly but a distinct probability it will not, or ≥ 20% and < 70% probability.
| D | Likely | § Could occur within “weeks to months” | Continuous for between two and four hours (frequent/daily) | High exposure (chronic exposure > OEL, or exposure exceeding OEL-STEL) | gv g
§ Balance of probability will occur
§ ≥ 70% and < 90% probability.
| E | Unavoidable | § Could occur within “days to weeks” | Continuous for eight-hour shift | Very high exposure (chronic exposure > 2 x OEL or exposure exceeding OEL-C)
§ Impact is imminent
§ ≥ 90% probability.

## Risk control effectiveness
RISK CONTROL EFFECTIVENESS GUIDE
RCE | Guide
Fully effective | Nothing more to be done except review and monitor the existing controls. Controls are well designed for the risk, are largely preventive and address the root causes. Management believes that they are effective and reliable at all times. Reactive controls only support preventive controls.
Mostly effective | Most controls are designed correctly and are in place and effective. Some more work to be done to improve operating effectiveness or management has doubts about operational effectiveness and reliability of the controls.
Mostly ineffective | While the design of controls may be largely correct in that they treat most of the root causes of the risk, they are not currently operationally very effective. There may be an over-reliance on reactive controls, or some of the controls do not seem correctly designed in that they do not treat root causes.
None | Virtually no credible control. Management has no confidence that any degree of control is being achieved.

## Risk matrix
RISK MATRIX
Consequences | 6 | I | I | I | I | I
| 5 | II | II | II | I | I
| 4 | III | III | II | I | I
| 3 | IV | III | II | II | I
| 2 | IV | IV | III | II | II
| 1 | IV | IV | III | III | III
|  | A | B | C | D | E
Likelihood
| Priority | Risk ranking | Action required
| I | Very high | Immediate action required, and these risks to be captured on IRM system.
| II | High | Strong mandatory action required, and these risks to be captured on IRM system.
| III | Medium | Action required, possibly at administrative level.
| IV | Low | Minor or no action required.