APPENDIX 9 – PROFORMA SUBCONTRACT DOCUMENT FOR TARGETED ENTERPRISES

THE SOUTH AFRICAN NATIONAL ROADS AGENCY SOC LIMITED

CONSTRUCTION WORKS SUBCONTRACT

PROFORMA

VERSION 1: AUGUST 2020

Aligned with Proforma Document for Construction 2019.1, 2020.1, 2020.2 and 2020.3

GENERAL NOTES TO COMPILER:

- Before proceeding, accept all changes in the proforma document, then select “Track Changes” to clearly indicate all of the Compiler’s changes in the draft document (i.e. highlighted for inclusions and crossed out for deletions).

- All notes to Compiler are to be addressed and then removed from the draft and final documents. However, do not amend the document footer indicating the proforma document version used.

- Confirm with the Engineer the number of copies of the draft documentation to be submitted to the Engineer.

- Where possible, the draft documentation should be printed double-sided to reduce the volume of the documentation.

- On submission of the draft documentation to the Engineer, the Contractor shall also submit on its letterhead a duly signed and dated version of the disclaimer below. This disclaimer is given as an example of an acceptable format of the disclaimer, but submission of this page with the example completed shall not be accepted. The disclaimer shall not form part of the final tender documents.

- Following the discussion or review of the draft documents by the Engineer, the Contractor is to accept all the tracked changes and incorporate the comments from the Engineer again through track changes for record purposes. These changes are then to be accepted into a final tender document. A CD containing the final tender document as well as all versions with all the changes indicated as tracked changes is to be submitted to the Engineer. Any major Deviations from this Pro-Forma document is to be done in consultation with Sanral Project Manager.

- Although the document is submitted for review to the Engineer, the Contractor is still ultimately responsible for the correctness and applicability of the information supplied in the document.

- These pages containing Notes to the Compiler do not form part of the tender document and must be deleted before submission of the draft documentation.

- The Subcontract number and description is linked to the title page and page T1-3. Insert a unique subcontract package number after SUBCONTRACT NO., Insert a unique subcontract package description after FOR, Insert the main SANRAL contract number after UNDER CONTRACT SANRAL, and Insert main SANRAL contract description title after FOR THE, on the Title page and on Page T1-3. The links in the document to be updated (on opening the document a request if the links is to be updated is to be accepted to update all the links in the document). Additional links can be added for other information repeated multiple times in the document to assist with future document preparation.

- In the document different options are provided for tender document collection, tender training, tender briefing and tender submission. Provision is either made for the above processes by remote electronic means (Option 1) or by physical means (Option 2 and 3). The selection of the appropriate option will depend on the access and availability of electronic means. Option 1 is preferred in terms of the Standard Operating Procedure: SMME Procurement under COVID-19 Lockdown conditions.

- This Pro-Forma is a generic document intended for use for all subcontract tenders. However, special attention to wording and requirements to be made where to be utilised for tenders aimed at CIDB 1 & 2 contractors. The document can also be utilised as basis for Supplier tenders with adaptation of Contract conditions and Specification.

EXAMPLE OF A DISCLAIMER TO ACCOMPANY A TENDER DOCUMENT FOR WHICH THE PROJECT SPECIFICATIONS HAVE BEEN SUBMITTED BY A CONTRACTOR

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

I, the Construction Manager,

acting on behalf of AB CONTRACTOR (Compiler to insert name of the Contractor)

declare that it has no material interest in any of the project specifications submitted and that the project specifications do not in any way whatsoever support a single product or system. All the project specifications are submitted based on SANRAL’s latest requirements as well as on current industry and international best practice, the information for which are at the Engineer’s disposal.

Signed for on behalf of

(Insert the full name of the Contractor)

Contractor’s Details:

Signature:

Print Name:

Date:

(Note to compiler: Insert Contractors details and address)

AB CONTRACTORS

Street address

Suburb

Town

Code

NAME OF tenderer:

Set sequential number

THE SOUTH AFRICAN NATIONAL

ROADS AGENCY SOC LIMITED

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

SUBCONTRACT DOCUMENT

BASE DATE: 			TENDER DOCUMENT

(Note to compiler: Insert Base date		VOLUME 3

Base date is 28 days prior to submission of Subcontract Offer

## CONTRACT NRA N.005-014-2014/1

ROUTINE ROAD MINTENANCE ON NATIONAL ROUTE 5 ECTIONS 1 TO 4: HARRISMITH TO WINBURG

PROJECT DOCUMENT

JUNE 2014       				TENDER DOCUMENT

VOLUME 3

## CONTRACT NRA N.005-014-2014/1

ROUTINE ROAD MINTENANCE ON NATIONAL ROUTE 5 ECTIONS 1 TO 4: HARRISMITH TO WINBURG

PROJECT DOCUMENT

JUNE 2014       				TENDER DOCUMENT

VOLUME 3

## CONTRACT NRA N.005-014-2014/1

ROUTINE ROAD MINTENANCE ON NATIONAL ROUTE 5 ECTIONS 1 TO 4: HARRISMITH TO WINBURG

PROJECT DOCUMENT

JUNE 2014       				TENDER DOCUMENT

VOLUME 3

## CONTRACT NRA N.005-014-2014/1

ROUTINE ROAD MINTENANCE ON NATIONAL ROUTE 5 ECTIONS 1 TO 4: HARRISMITH TO WINBURG

PROJECT DOCUMENT

JUNE 2014       				TENDER DOCUMENT

VOLUME 3

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

SUBCONTRACT DOCUMENT

(Note to Compiler: Enter relevant Contractor’s details. In the case of a Joint Venture, enter the details of both Firm A and Firm B)

| THIS DOCUMENT COMPILED BY: |  |  |
| --- | --- | --- |
| AB CONTRACTORS Street address Suburb Town Code Tel: Fax: e-mail: | Joint Venture (Note to Compiler: Delete this column if no JV information is to be recorded) | ABC CONTRACTORS Street address Suburb Town Code Tel: Fax: e-mail: (Note to Compiler: Delete this column if no JV information is to be recorded) |

UNDER THE DIRECTION OF:

(Note to Compiler: complete the relevant regional details) The Regional Manager (Northern/ Southern/ Eastern/ Western Region) The South African National Roads Agency SOC Ltd Street address Suburb Town Code Tel: (...) ............... Fax:(...) ...............

LIST OF CONTRACT DOCUMENTS

The following documents form part of this contract:

VOLUME 1:	The Conditions of Subcontract for Construction for Building and Engineering Works Designed by the Employer First Edition (2011), published by the International Federation of Consulting Engineers (FIDIC).

VOLUME 2:	The COLTO Standard Specifications for Road and Bridge Works for State Road Authorities (1998 edition), issued by the Committee of Land Transport Officials which the tenderer shall purchase himself. (See Note to Tenderer 2 below).

Note to Compiler:	For projects that include other disciplines such as electrical, lighting or building, reference to the applicable standard specifications applicable to each discipline is to be added as Volume 2B, Volume 2C etc. for example for electrical and lighting work the following to be added:

- SANS 1200: Standardised Specifications for Civil Engineering Construction (1990, including later editions and amendments).

- SANS 10098-1:2007 or as per latest amendments for South African National Roads Standard public lighting.

- SANS 60598-1:2014 Edition 6 IEC 60598-1:2014 General requirements and tests on lights.

- SANS 10142-1 and SANS 10142-2 Part 2: Medium-voltage installations above 1 kV a.c. not exceeding 22 kV a.c. and up to and including 3 MVA installed capacity.

VOLUME 3:	Project Document.

VOLUME 4:	Contract Drawings. (Note to Compiler: Delete if there are no drawings applicable)

Notes to Tenderer:

- Volume 1 is obtainable from CESA

P. O. Box 68482, Bryanston, 2021.

Tel: (011) 463 2022	Fax: (011) 463 7383	Email: general@cesa.co.za

- Volume 2 is obtainable from SAICE, Private Bag X200, Halfway House, 1685. Tel: (011) 8055947/8, e-mail: civilinfo@saice.org.za or can be purchased from the Employer.

- Volume 3 is this document issued at tender stage.

The standard conditions of tender (SANS 10845-3) is obtainable from the South African Bureau of Standards

Private Bag X191, Pretoria, 0001

Tel: (012) 428 7911	Fax: (012) 344 1568	Website: www.sabs.co.za

At contract stage Volume 3 will be a bound signed paper copy containing the following documents:

- Returnable schedules relevant to the project

- Agreements and Contract Data

- Pricing Data

- Scope of Work

- Site Information

- SUBMISSION OF TENDER – Of the contract documents, only the following elements of Volume 3 needs to be submitted:

(Note to Compiler: Option 1: Where remote electronic means are available)

Submitted electronically by e-mail or uploaded to share drive, in the following order:

- Form of Offer (signed and scanned as pdf)

- All returnable schedules and attachments (signed and scanned as pdf)

- Completed Pricing Schedule (scanned copy in pdf and copy in excel)

(Note to Compiler: Option 2: Where remote electronic means are not feasible)

Submitted electronically on a CD or USB device, in the following order:

- Form of Offer (signed and scanned as pdf)

- All returnable schedules and attachments (signed and scanned as pdf)

- Completed Pricing Schedule (scanned copy in pdf and copy in excel)

(Note to Compiler: Option 3: Where options 1 and 2 is not feasible)

Submitted in hardcopy in a neatly bound file and in the following order:

- Form of Offer (paper copy)

- All returnable schedules and attachments (paper copy)

- Completed Pricing Schedule (paper copy)

- Completed Pricing Schedule (electronically completed on CD in excel) (Note to Compiler: Decide on only paper copy or paper and electronic copy based on the size of the pricing schedule)

(Note to Compiler: Confirm that the above is similarly reflected in the tender data and pricing instructions)

Information provided by a tenderer over and above the above elements of Volume 3 shall be treated as information only and will only be bound into the contract document if the information has a bearing on the tender price and/or project specifications.

Table of Contents	PAGE

Part T1:	Tendering Procedures	T1.1

Part T2:	returnable schedules	T2.1

Part C1:	AGREEMENTS & CONTRACT DATA	C1.1

Part C2:	PRICING DATA	C2.1

Part C3:	SCOPE OF WORKS	C3.1

Part C4:	SITE INFORMATION	C4.1

Part C5:	annexures	C5.1

Part T1:	Tendering Procedures

PART T1	TENDERING PROCEDURES

Table of Contents	Page

T1.1	TENDER NOTICE AND INVITATION TO TENDER (SBD1)	T1.4

T1.2	TENDER DATA	T1.8

## AB CONTRACTOR (Compiler to insert name of the Contractor)

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

T1.1	TENDER NOTICE AND INVITATION TO TENDER (Incorporating SBD1)

Notes to Compiler:

      - All notes to the Compiler are to be addressed and then removed from the draft and final documents and the chapter heading moved to a position at one third from the top of the page.

      - The Engineer and relevant Regional SANRAL Project Engineer must be consulted prior to the placement of the tender advertisement. The tender notice shall be sent to the Engineer and relevant Regional SANRAL Project Engineer 3 weeks before the intended placement of the tender advertisement for checking.

AB CONTRACTOR (Compiler to insert name of the Contractor)

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

# T1.1	TENDER NOTICE AND INVITATION TO TENDER (SBD1)

## AB CONTRACTORS invites tenders from experienced EME/QSE subcontractors / suppliers for Contract SANRAL……………. (Note to Compiler: insert main contract number) FOR THE ………….. (Note to compiler: insert main contract description) endorsed by The South African National Roads Agency SOC Limited (SANRAL). This project is in the province of (Compiler to insert province) and in the (Compiler to insert local municipality or District Municipality based on the target area for the package)

Subcontractors are required for the following subcontracts:

: 	for

: 	for

: 	for

: 	for

(Note to Compiler: Add the subcontract no. and package description for the subcontract being advertised. For multiple work packages being advertised concurrently add the information for each package)

The approximate duration is ……. months. (Compiler to insert same duration as Contract Data C1.1.31)

Only tenderers who comply with the definition of a Targeted Enterprise under clause 4.1.1 and are at least 51% Black owned and who is an EME or QSE or cooperative, are eligible to tender.

Only tenderers that meet all the eligibility criteria under clause 4.1.1 of the Tender Data will be considered.

Only tenderers who meet the minimum functionality score as stated in clause 5.11.9 will be evaluated further on price and preference

It is estimated that tenderers should have a CIDB contractor grading designation of …….CE (Notes to Compiler: State applicable CIDB grading and class dependent on type of work – similarly in Tender Data where applicable) or higher, however tenderers attention is drawn to clause 4.1.1 of the Tender Data when submitting their tender.

(Notes to Compiler:

- Delete this sentence and replace with the table and sentence below when advertising multiple work packages simultaneously

- If the estimated construction value is within 20% of one of the limits set by CIDB, the advertisement must indicate the lower category. For example, if your estimated value is 20% within the bottom range of a category then rather specify one category lower.

- In terms of CIDB Regulation 25(1B), the CIDB grading designation to be inserted is to be based on the estimated annual value of the contract. Therefore if the nature of work for the package is repetitive over a long duration then 25(1B) to apply, else the grading designation is to be based on the estimated contract value.

- For tenders for supplier subcontracts, or work which do not have an appropriate CIDB grading designation, all reference to CIDB requirements is to be deleted and sentences accordingly amended.)

It is estimated that tenderers should have a CIDB contractor grading designation as indicated in the table below:

| Works Package | CIDB requirement |
| --- | --- |
| (Note to Compiler: Insert relevant package numbers and CIDB gradings, e.g.: N.001-090-2014/1_SC1 | 1 CE |
| N.001-090-2014/1_SC2 | 2 CE |
| N.001-090-2014/1_SC3: | 3 CE |

The tenderers attention is drawn to clause 4.1.1 of the Tender Data for each work package when submitting their tender.

Tenders from tenderers registered as potentially emerging enterprises but with a CIDB contractor grading designation lower than a contractor grading designation determined in accordance with the sum tendered, or a value determined in accordance with Regulation 25(1B) or 25(7A) of the Construction Industry Development Regulations, will not be accepted. (Note to Compiler: Delete reference to 25(1B) above if the nature of the work for the package is not repetitive over a long duration)

Only locally produced or locally manufactured products and components for construction will be considered.

Preferences are offered to tenderers who comply with the criteria stated in the Tender Data.

SUBCONTRACT TENDER DOCUMENTS

Tender documents are available :

- At no cost in electronic format via share drive / via website / via e-mail (Compiler to select appropriate where remote electronic means are available) . Prospective tenderers may send a request for a link to the document to the following address …… (Compiler to insert e-mail address for requests) Tenderers must have access to Microsoft Office © 2013 and Acrobat Adobe © 9.0, or similar compatible software, or

- At no cost for collection in electronic format on CD / USB device (Compiler to select appropriate). Tenderers must have access to Microsoft Office © 2013 and Acrobat Adobe © 9.0, or similar compatible software.The physical address for collection of tender documents is the ………….., (compiler to state the street address of the relevant office) where documents may be collected during the hours 09h00 to 16h00 (Monday to Friday), from …… (Compiler to state date). Prospective tenderers who can not access the information on the CD / USB device must pre-book for access to a computer workstation on site on a specific day and time. A request for access to a computer workstation is to be sent to the following address …… (Compiler to insert e-mail address and/or telephone number for requests), or

- At no cost for collection in Hardcopy.The physical address for collection of tender documents is the ………….., (Compiler to state the street address of the relevant office) where documents may be collected during the hours 09h00 to 16h00 (Monday to Friday), from …… (Compiler to state date)

TENDERERS’ BRIEFING AND TRAINING

(Note to Compiler: Option 1: where remote electronic means are available – preferred during COVID limitations -refer to SOP SMME Procurement under COVID-19 Lockdown conditions)

A tender clarification briefing presentation / pre-recorded video and training presentation / pre-recorded video are available to be downloaded via share drive / via website / via e-mail (Compiler to select appropriate) .Prospective tenderers may send a request for a link to the clarification briefing and training documents to the following address …… (Compiler to insert e-mail address for requests)

(Note to Compiler: Option 2: where option 1 is not feasible but electronic means are available)

A tender clarification briefing presentation / pre-recorded video and training presentation / pre-recorded video are available to be collected on a CD / USB device. The physical address for collection of the clarification briefing and training documents is ………….., (Compiler to state the street address of the relevant office) where documents may be collected during the hours 09h00 to 16h00 (Monday to Friday), from …… (Compiler to state date). Prospective tenderers who cannot access the information on the CD / USB device must pre-book for access to a computer workstation on site on a specific day and time. A request for access to a computer workstation is to be sent to the following address …… (Compiler to insert e-mail address and/or telephone number for requests)

(Note to Compiler: Option 3: where option 1 and option 2 is not feasible)

A compulsory tender clarification briefing and training session(s) with representatives of the Contractor and Engineer will take place at ............................ (Compiler to state the street address). Prospective tenderers must pre-book for the clarification briefing and training session, due to venue size limitations. A request for a clarification briefing and training session date and time is to be sent to the following address …… (Compiler to insert e-mail address and/or telephone number for requests). Tenders from tenderers who arrived late at the clarification briefing session will not be allowed, and their submissions shall be declared non-responsive.

A tenderer’s representative cannot represent more than one tenderer at the clarification briefing session.

COMPLETION AND DELIVERY OF TENDERS

The closing time for receipt of tenders is 10:00 on ………. (Compiler to insert date)

(Note to Compiler: Option 1: where remote electronic means are available – preferred during COVID limitations -refer to SOP SMME Procurement under COVID-19 Lockdown conditions)

Only tender offers submitted electronically by e-mail / uploaded to share drive (Compiler to select appropriate) as specified in the Tender Data will be accepted.

Tenders may only be submitted in the format as stated in the Tender Data.

(Note to Compiler: Option 2 or 3: where option 1 is not feasible)

Only tender offers submitted in Hardcopy / electronic format on CD or USB device (Compiler to select appropriate) and delivered to the address specified in the Tender Data will be accepted.

Requirements for sealing, addressing, delivery, opening and assessment of tenders are stated in the Tender Data.

Tenders may only be submitted in the format as stated in the Tender Data.

Queries relating to issues arising from the tenderer’s clarification briefing presentation / video or these documents may be addressed to the following: (Compiler to insert relevant contractor information)

| Enquiries |  |
| --- | --- |
| Contact Person: | (insert the contractor contact info) |
| Fax No: |  |
| E-mail: |  |

AB CONTRACTOR (Compiler to insert name of the Contractor)

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

T1.2	TENDER DATA

# T1.2	TENDER DATA

The conditions of tender are the standard conditions of tender as contained in SANS 10845-3:2015 Edition 1.

The standard conditions of tender make several references to the tender data for details that apply specifically to this tender. The tender data shall have precedence in the interpretation of any ambiguity or inconsistency between the tender data and the standard conditions of tender.

Each item of data given below is cross-referenced to the clause in the standard conditions of tender to which it mainly applies.

| Clause Number | Data |
| --- | --- |
| 2.1 | # Wherever reference is made in the documentation to bill of quantities it shall also mean pricing schedule. |
| 3.1 | # The Contractor is (Note to Compiler: Insert name of Contracting Firm) # The Contractor’s domicilium citandi et executandi (permanent physical business address) is: # Insert Physical business address # The Contractor’s address for communication relating to this contract is: Insert relevant address Where in the standard conditions of tender (SANS 10845-3:2015) reference is made to “the Employer”, it shall mean “the Contractor” as defined above. Main Contract Details: Contract Number: (Note to Compiler: Insert number of contract) Employer: The South African National Roads Agency SOC Limited Engineer: (Note to Compiler: Insert Name of Consulting Engineering) Firm) The Contractor: (Note to Compiler: Insert Name of Contracting Firm) The Conditions of Contract for the Main contract is: “Conditions of Contract for Building and Engineering Works designed by the Employer” (1999) published by the International Federation of Consulting Engineers (FIDIC) (Red book). |
| 3.2 | # The tender documents issued by the Contractor comprise: # Part T1: Tendering Procedures - T1.1 Tender Notice and Invitation to tender - T1.2 Tender data # Part T2: Returnable documents - T2.1 List of returnable documents - T2.2 Returnable schedules # Part C1: Agreements and contract data - C1.1 Form of Offer and Acceptance - C1.2 Contract data # Part C2: Pricing data - C2.1 Pricing instructions (assumptions) - C2.2 Pricing Schedules/Bill of quantities # Part C3: Scope of work # Part C4: Site information Part C5: Annexure |
| 3.4 | The language for communications is English. # The Contractor’s contact details is: # (Note to Compiler: Insert Name of the contracting firm) # Address: # Telephone number: # E-mail): |
| 3.5 | The tender process may be cancelled if: - Due to changed circumstances, there is no longer a need for the goods or services specified in the invitation; - Funds are no longer available to cover the total envisaged expenditure; - No acceptable tender is received; or - There is a material irregularity in the tender process The period of six months shall not apply. |
| 4.1.1 | Only those tenderers who satisfy the following criteria are eligible to submit tenders. If the tenderer fails to meet any of the eligibility criteria, he will be given 5 calendar days to become compliant. If the tenderer fails to submit the requested information in the required timeframe, his tender shall be deemed non-compliant. |
|  | - CIDB registration (Form A12) (Note to Compiler: Delete this clause for supplier subcontract tenders or work without CIDB category, where CIDB registration is not required) Registered with the CIDB, at close of tender, in a contractor grading designation equal to or higher than a contractor grading designation determined in accordance with the sum tendered, or a value determined in accordance with Regulation 25(1B) (Note to Compiler: Delete reference to 25(1B) if the nature of the work for the package is not repetitive over a long duration) or 25(7A) of the Construction Industry Development Regulations, for a CE class of construction work. Tenderers whose CIDB registration expires within the tender validity period, need to demonstrate that there is a reasonable chance of being registered in the appropriate grading designation during the tender evaluation period, by submitting a copy of their timely application for CIDB registration, with their tender submission. Tenders received from such tenderers who are not capable of being registered in the required contractor designation, within 21 working days after either expiry of their registration or after being requested to provide proof of registration, will be considered non-responsive. Note that in terms of the Construction Industry Development Board Act, 2000 (Act No. 38 of 2000) a registered contractor must apply for renewal of registration three months before the existing registration expires. Tenderers registered as potentially emerging enterprises but with a CIDB contractor grading designation lower than a contractor grading designation determined in accordance with the sum tendered, or a value determined in accordance with Regulation 25(1B) (Note to Compiler: Delete reference to 25(1B) if the nature of the work for the package is not repetitive over a long duration) or 25(7A) of the Construction Industry Development Regulations, are not eligible to have their tenders evaluated. |
|  | Category of tender; Upper limits per CIDB Regulation 17 (effective 7 October 2019); Contractor’s allowable margins (Incl. VAT). CE 1; R500 000; The Contractor will use its discretion in terms of CIDB Practice Note 3 on allowable margins to be accepted. CE 2; R1 000 000. CE 3; R3 000 000. CE 4; R6 000 000. CE 5; R10 000 000. CE 6; R20 000 000. CE 7; R60 000 000. CE 8; R200 000 000. |
|  | This contract is classified in terms of CIDB Regulation 25(1B), and the value of the contract may, for the purpose of CIDB Regulation 25(1), be taken at its annual value. (Note to Compiler: Delete this sentence if reference to 25(1B) was removed in the clauses above and the nature of the work for the package is not repetitive over a long duration) Joint Ventures are eligible to submit tenders provided that: - every member of the joint venture is registered with the CIDB; - the lead partner has a contractor grading designation of not lower than one level below the required grading designation in the class of construction works under consideration and possesses the required recognition status; and - the combined contractor grading designation calculated in accordance with the Construction Industry Development Regulations is equal to or higher than a contractor grading designation determined in accordance with the sum tendered for a CE class of construction work or a value determined in accordance with Regulation 25(1B) or 25(7A) of the Construction Industry Development Regulations. |
|  | - National Treasury Central Supplier Database Tenderers, or in the event of a joint venture, each member of the joint venture, shall be registered on the National Treasury Central Supplier Database at the closing date for tender submissions. |
|  | - Criteria for preferential procurement Only tenderers who comply with the definition of a Targeted Enterprise which is: - an EME or QSE which is at least 51% owned by black people; - an EME or QSE which is at least 51% owned by black people who are youth; - an EME or QSE which is at least 51% owned by black people who are women; - an EME or QSE which is at least 51% owned by black people with disabilities; - an EME or QSE which is 51% owned by black people living in rural or underdeveloped areas or townships; - a cooperative which is at least 51% owned by black people; - an EME or QSE which is at least 51% owned by black people who are military veterans; or - more than one of the categories referred to in paragraphs a to g; and - which is tax and COID compliant The tenderer shall submit a valid B-BBEE certificate as proof of eligibility. |
| 4.6 | Failure to apply instructions contained in addenda may render a tenderer’s offer non-responsive in terms of condition of tender 5.8. |
| 4.7 | # The arrangements for a clarification briefing and tender training session are: (Note to Compiler: Select appropriate option and insert relevant data and ensure that it is the same as it appears in the Tender Notice) (Note to Compiler: Option 1: where remote electronic means are available – preferred during COVID limitations -refer to SOP SMME Procurement under COVID-19 Lockdown conditions) A tender clarification briefing presentation / pre-recorded video and training presentation / pre-recorded video are available to be downloaded via share drive / via website / via e-mail (Compiler to select appropriate). Prospective tenderers must send a request for a link to the clarification briefing and training documents to the following address …… (Compiler to insert e-mail address for requests) The onus rests with the tenderer to ensure that the representative reading / viewing the clarification briefing presentation / video is appropriately qualified to understand all directives and clarifications given in the presentation / video. The signature on the duly completed and signed Form A1 shall be considered proof that the tenderer read/viewed the whole clarification briefing presentation / video and clearly understood all directives and clarifications given in the presentation / video. (Note to Compiler: Option 2: where option 1 is not feasible but electronic means are available) A tender clarification briefing presentation / pre-recorded video and training presentation / pre-recorded video are available to be collected on a CD / USB device. The physical address for collection of the clarification briefing and training documents is the ………….., (Compiler to state the street address of the relevant office) where documents may be collected during the hours 09h00 to 16h00 (Monday to Friday), from …… (Compiler to state date) Prospective tenderers who can not access the information on the CD / USB device must pre-book for access to a computer workstation on site on a specific day and time. A request for access to a computer workstation is to be sent to the following address …… (Compiler to insert e-mail address and/or telephone number for requests) The onus rests with the tenderer to ensure that the representative reading / viewing the clarification briefing presentation / video is appropriately qualified to understand all directives and clarifications given in the presentation / video. The signature on the duly completed and signed Form A1 shall be considered proof that the tenderer read/viewed the whole clarification briefing presentation / video and clearly understood all directives and clarifications given in the presentation / video. (Note to Compiler: Option 3: where option 1 and option 2 is not feasible) A compulsory tender clarification briefing and training session(s) with representatives of the Contractor and Engineer will take place at ............................ (Compiler to state the street address) Prospective tenderers must pre-book for the clarification briefing and training session, due to venue size limitations. A request for a clarification briefing and training session date and time is to be sent to the following address …… (Compiler to insert e-mail address and/or telephone number for requests) The clarification briefing session shall start strictly at the time indicated. Only then will the Contractor’s Representative circulate the attendance register for completion by those present. During this time, prospective tenderers may enter and complete the register. On completion by all present the Contractor’s Representative will: - read out from the collected lists calling for confirmation that all have signed; - close the door and not allow late arrivals to participate in the briefing session and their submissions shall be declared non-responsive. The signatures on the attendance register and duly completed and signed Form A1 shall be considered proof that the tenderer attended the whole briefing session and was available to hear all directives and clarifications given at the briefing session. Tenderers shall sign the attendance list in the name of the tendering entity or in the name of a member of the tendering entity. Addenda will be issued to, and tenders will be received only from, those tendering entities appearing on the attendance list. Tenders from tenderers who arrived late at the clarification briefing session will not be allowed, and their submissions shall be declared non-responsive. The onus rests with the tenderer to ensure that the person attending the clarification briefing on its behalf is appropriately qualified to understand all directives and clarifications given at the briefing. A tenderer’s representative cannot represent more than one tenderer at the clarification briefing. |
| 4.8 | Request clarifications at least 7 working days before the closing time. |
| 4.9 | Limited insurance will be provided by the Contractor. |
| 4.10 | Tenderers are required to state the rates and prices in Rand. |
| 4.12 | # Alternative tender offers will not be considered. |
| 4.13.1 | Alternative offers will not be considered. In the event of any discrepancy between the contents of the electronically priced schedule (if applicable), the print-out thereof and the electronically provided pricing schedule (if applicable) in pdf format, the contents of the provided pdf format shall be taken as the valid contents. For the information provided by the tenderer as part of his submission, e.g. rates, the signed print-out shall be taken as the valid submission. |
| 4.13.4 | Tenderers are required to submit all certificates as listed in the Schedule of Tender Compliance (Form D1). |
| 4.13.5 | Only the following needs to be submitted. (Note to Compiler: Option 1: where remote electronic means are available – preferred during COVID limitations -refer to SOP SMME Procurement under COVID-19 Lockdown conditions) The following information to be submitted electronically by e-mail / uploaded to share drive (Compiler to select appropriate), in the following order: - Form of Offer (signed and scanned as pdf) - All returnable schedules and attachments (signed and scanned as pdf) - Completed Pricing Schedule (scanned copy in pdf and copy in excel) Prospective tenderers must submit the completed tender document in a folder marked “Subcontract number & Tenderer name” to ……… (Compiler to insert e-mail address) / loaded to share drive with the following link ….. (Compiler to insert link) (Compiler to select appropriate method) (Note to Compiler: Option 2: where remote electronic means are not feasible) The following information to be submitted in electronic format on CD or USB device, in the following order: - Form of Offer (signed and scanned as pdf) - All returnable schedules and attachments (signed and scanned as pdf) - Completed Pricing Schedule (scanned copy in pdf and copy in excel) Place and seal the CD or USB devise containing the completed tender document in an envelope clearly marked “TENDER” and bearing the Contractor’s name, physical address and contact number, the tender subcontract number and description, the tenderer’s name, the tenderer’s physical address and contact telephone numbers. # The details to be shown on each tender offer package are: # TENDER CLOSING TIME: Time on Day, Date (Note to Compiler: State time, day and date) # FOR SUBCONTRACT (Note to Compiler: Insert Contract number and description). # CONTRACTOR: # Name of Contractor # Address # Contact Number # (Note to Compiler: Insert relevant office physical address and contact number). # TENDERER: # Name: # Physical address: # Contact Numbers:. Tenders must be submitted during office hours (09:00 to 16:00) Monday to Friday at the Contractor’s address. (Note to Compiler: Insert location map of relevant submission office) It is in the tenderer’s interest to ensure that the delivery of the tender offer is recorded in the Contractors tenders received register. (Note to Compiler: Option 3: where options1 and 2 are not feasible) The following information to be submitted in hard copy, in a neatly bound file and in the following order: - Form of Offer (signed printed paper) - All returnable schedules and attachments (signed printed paper) - Completed Pricing Schedule (printed paper - Completed Pricing Schedule (electronically completed on CD in excel). (Note to Compiler: Decide on only paper copy or paper and electronic copy based on the size of the pricing schedule) Place and seal the completed tender document in an envelope clearly marked “TENDER” and bearing the Contractor’s name, physical address and contact number, the tender subcontract number and description, the tenderer’s name, the tenderer’s physical address and contact telephone numbers. # The details to be shown on each tender offer package are: # TENDER CLOSING TIME: Time on Day, Date (Note to Compiler: State time, day and date) # FOR SUBCONTRACT (Note to Compiler : Insert Contract number and description). # CONTRACTOR: # Name of Contractor # Address # Contact Number # (Note to Compiler: Insert relevant office physical address and contact number). # TENDERER: # Name: # Physical address: # Contact Numbers:. Tenders must be submitted during office hours (09:00 to 16:00) Monday to Friday at the Contractor’s address. (Note to Compiler: Insert location map of relevant submission office) It is in the tenderer’s interest to ensure that the delivery of the tender offer is recorded in the Contractor’s tenders received register. |
| 4.14 | Provided that the omission is not a material omission, the Contractor reserves the right to condone the omission and may waive any nonconformities in the tender. Provided that the omission is not a material omission, the Contractor reserves the right to condone the omission and may request the tenderer to submit the necessary information or documentation within five (5) working days to rectify non-material non-conformities in the tender related to documentation requirements. |
| 4.15 | # The closing time for submission of tender offers is Time on Day, Date (Note to Compiler: Insert relevant time, day and date) |
| 4.16.1 | The tender offer validity period is 12 weeks. |
| 4.16.2 | # Where a tenderer, at any time after the opening of his tender offer but prior to entering into a contract based on his tender offer: - withdraws his tender; - gives notice of his inability to execute the contract in terms of his tender; or - fails to comply with a request made in terms of 4.17, 4.18 or 5.9, # such tenderer may be barred from tendering on any of the Contractor’s future tenders for a period to be determined by the Contractor, but not less than six (6) months, from the date of tender closure. This sanction also applies to tenders under evaluation and not yet awarded. This sanction does not apply to tenders under evaluation where a request for extension of the validity period was not accepted by the tenderer. The Contractor may fully or partly exempt a tenderer from the provisions of this condition if he is of the opinion that the circumstances justify the exemption. |
| 4.18 | Any additional information requested under this clause must be provided within five (5) working days of date of request. |
| 5.1 | The Contractor shall respond to clarifications received up to seven (7) working days before tender closing time. |
| 5.2 | The Contractor shall issue addenda until five (5) working days before tender closing time. |
| 5.4 | # The time and location for opening of the tender offers shall be: # Time: Time on Day, Date (Note to Compiler: Insert relevant time, day and date) (Note to Compiler: Option 1: where remote electronic means are available – preferred during COVID limitations -refer to SOP SMME Procurement under COVID-19 Lockdown conditions) # Venue: Opening of the tender offer via live streaming. An Invitation with a link shall be sent to all tenderers that accessed the tender documentation. (Note to Compiler: Option 2: where option 1 is not feasible) # Venue: ………. (Note to Compiler: insert location and address) |
| 5.7 | Prior to disqualification, the Contractor shall inform the tenderer and give the tenderer an opportunity to make representations within 14 days as to why the tender submitted should not be disqualified and as to why the tenderer should not be restricted by the National Treasury from conducting any business with any organ of state for a period not exceeding 10 years. In the event of disqualification, the Contractor may, at its sole discretion, claim damages from the tenderer and impose a specified period during which tender offers will not be accepted from the offending tenderer and, the Contractor shall inform SANRAL who in turn will communicate with National Treasury and the CIDB in writing. |
| 5.8 | A substantially responsive tender is a tender in which all of the material information and documentation submitted at close of tender contains non-material and non-conformities to the bid specifications but are not related to price. The correction of any such documentation or information, or the condonement for the non-inclusion of any such document or information may not be prejudicial towards the offer and claimed preference of any responsive tender or be construed to be giving an unfair advantage to any tender. A responsive tender is also one that conforms to all the terms, conditions, and scope of work of the tender documents, without material omissions. The test for a material omission is the same as the test for a material deviation or qualification. |
| 5.9 | # Arithmetical errors, omissions, discrepancies and imbalanced unit rates # Check responsive tenders for discrepancies between amounts in words and amounts in figures. Where there is a discrepancy between the amounts in figures and the amount in words, the amount appearing in the summary to the bill of quantities shall govern. # Check responsive tender offers for: - the gross misplacement of the decimal point in any unit rate; - omissions made in completing the pricing schedule or bills of quantities; or - arithmetic errors in: # i) line item totals resulting from the product of a unit rate and a quantity in bills of quantities or schedules of prices; or # ii) the summation of the prices. - imbalanced unit rates. # Notify shortlisted tenderers of all errors, omissions or imbalanced rates that are identified in their tender offers. # Where the tenderer elects to confirm the errors, omissions or re-balancing of imbalanced rates the tender offer shall be corrected as follows: - If bills of quantities or pricing schedules apply and there is an error in the line item total resulting from the product of the unit rate and the quantity, the unit rate shall govern, and the line item total shall be corrected. Where there is an obviously gross misplacement of the decimal point in the unit rate, the line item total as quoted and the unit rate shall be corrected. - Where there is an error in the total of the prices either as a result of other corrections required by this checking process or in the tenderer’s addition of prices, the total of the prices shall be corrected. - Where the unit rates are imbalanced adjust such rates by increasing or decreasing them and selected others, including rates between the management and operational sections, while retaining the total of the prices derived after any other corrections made under (a) and (b) above. # Where there is an omission of a line item, no correction is possible, and the offer may be declared non-responsive. # Declare as non-responsive and reject any offer from a tenderer who elects not to accept the corrections proposed and subject the tenderer to the sanction under 4.16.2. The tenderer is required to submit balanced unit rates for rate only items in the pricing schedule. The rates submitted for these items will be taken into account in the evaluation of tenders. |
| 5.11.1 | # The minimum percentage of evaluation points for functionality is not less than …%. (Note to Compiler: Insert relevant functionality score as agreed with the Engineer and SANRAL) The functionality points can be lowered by the Contractor, (typically by 5/100 points or 5%), should an adequate number of tenderers not achieve the functionality threshold. The bench mark for an adequate number of tenderers is ten (10) tenderers that achieve the functionality points, but it is at the Contractor’s discretion and depends on the Works to be subcontracted or any other valid considerations. Score each of the criteria and sub-criteria for functionality (NF) in accordance with the provisions of the tender data. Calculate the total number of tender evaluation points for functionality using the following formula: NF = W2 x SO / MS where: MS is the maximum possible score (100) for functionality in respect of a submission; and W2 is the maximum possible number of tender evaluation points (100) awarded for the functionality as stated in the tender data. SO is the score for functionality allocated to the submission under consideration, calculated as follows; - Each Tenderer will be evaluated, and points will be allocated according to the criteria in the Table below. (Note to Compiler: The below criteria is the latest criteria in the Sanral pro-forma documentation and it might differ from the criteria in the main contract documentation utilized. It is therefore proposed to utilize the latest criteria as indicated below to be agreed with the Engineer and SANRAL) - Information submitted in the returnable Form B3 will be used to allocate points for the respective criteria. - Only Tenderers who score a minimum of 75 percentage points or more (insert project specific functionality threshold) for functionality will be evaluated further. CIDB Grade and Package Value; Maximum Points out of 100; Total Points. Locality Table 5.11.1; CIDB Grading Table 5.11.2; Designated Groups Table 5.11.3. 1 - R 500 000; 60; 30; 10; 100. 2 - R 1 000 000; 60; 30; 10; 100. 3 - R 3 000 000; 60; 35; 5; 100. 4 - R 6 000 000; 60; 35; 5; 100. 5 - R 10 000 000; 60; 35; 5; 100. 6 - R 20 000 000; 60; 35; 5; 100. 7 - R 60 000 000; 60; 30; 10; 100. ## 5.11.1.1 Locality The points for Locality will be calculated as follows: - The project area(s) for this subcontract is xxx and xxx (insert identified project area endorsed by the PLC) - For the purposes of this evaluation, “based” shall mean the tenderer’s current physical address as recorded by the Companies and Intellectual Property Commission (CIPC) of the tenderer’s place of business. - The information provided in the returnable schedules will be used to calculate the points for locality. - The maximum number of points that can be awarded for locality is 60 (amend to be project specific). - The points for locality will be allocated as follows: Table 5.11.1.1: Locality CIDB Package Category; 1CE; 2CE; 3CE; 4CE; 5CE; 6CE. Typical Package Value; Up to R 1 mill; R 1 mill to R 6 mill; R 6 mill to R 20 mill. Locality; Tenderer is based in the Local Municipality(ies).; 60; 60; 60; 60; 60; 60. Tenderer is based outside the Local Municipality(ies) but in the District Municipality(ies).; 45; 45; 40; 40; 40; 40. Tenderer is based outside the District Municipality(ies), but in the Province.; 0; 0; 35; 35; 35; 35. Tenderer is based outside the Province, but in the RSA.; 0; 0; 0; 0; 30; 30. (Remove the non-applicable CIDB grades and amend the points allocation to be project specific) ## 5.11.1.2 Targeted CIDB Grade and class The points for CIDB Grading Designation will be calculated as follows: - The targeted CIDB grading and class for this subcontract is 3CE PE (insert the subcontract specific grading and class) - The information provided in the returnable schedules will be used to calculate the points for CIDB grading and class. - The maximum number of points that can be awarded for CIDB grading designation is 35 (amend to be project specific) - The points for Targeted CIDB Grading designation will be allocated as follows: Table 5.11.1.2: Targeted CIDB Grading Designation CIDB Package Category; 1CE; 2CE; 3CE; 4CE; 5CE; 6CE. Typical Package Value; Up to R 1 mill; R 1 mill to R 6 mill; R 6 mill to R 20 mill. CIDB Grading; Tenderer is registered as a CIDB 1; 35; 30; 0; 0; 0; 0. Tenderer is registered as a CIDB 2; 30; 35; 30; 0; 0; 0. Tenderer is registered as a CIDB 3; 0; 0; 35; 30; 0; 0. Tenderer is registered as a CIDB 4; 0; 0; 30; 35; 30; 0. Tenderer is registered as a CIDB 5; 0; 0; 0; 30; 35; 30. Tenderer is registered as a CIDB 6; 0; 0; 0; 0; 30; 35. Tenderer is registered as a CIDB 7 and higher; 0; 0; 0; 0; 0; 30. (Remove the non-applicable CIDB grade columns and amend the points allocation to be project specific) ## 5.11.1.3 Designated Group ownership The points for Designated Group ownership will be calculated as follows: - The targeted Designated Group ownership for this subcontract is Greater than 51% ownership by Black Youth (insert the Designated Group and ownership) - The information in the returnable schedules will be used to calculate the points for Designated Group ownership. - The maximum number of points that can be awarded for Designated Group ownership is 10 (amend to be project specific) - The points for Designated Group ownership will be allocated as follows: Table 5.11.1.3: Designated Group ownership CIDB Package Category; 1CE; 2CE; 3CE; 4CE; 5CE; 6CE. Typical Package Value; Up to R 1 mill; R 1 mill to R 6 mill; R 6 mill to R 20 mill. Designated Groups (no max score); Tenderer is 51%+ owned by black people who are youth.; 5; 5; 5; 5; 5; 5. Tenderer is 51%+ owned by black people who are women.; 5; 5; 5; 5; 5; 5. Tenderer is 51%+ owned by black people with disabilities.; 5; 5; 5; 5; 5; 5. Tenderer is 51%+ owned by black people who are military veterans.; 5; 5; 5; 5; 5; 5. (Remove the non-applicable CIDB grade columns and amend the Designated Group ownership and/or points allocation to be project specific) |
| 5.11.4 | # The procedure for the evaluation of responsive tenders is Method 3. # If two or more tenderers score an equal total number of points, and these tenders are also the highest ranked tenders, the contract must be awarded to the tenderer that scored the highest points for B-BBEE. # If functionality is part of the evaluation process and two or more tenderers score equal total points and equal preference points, the subcontract must be awarded to the tenderer that scored the highest points for functionality. # If two or more tenderers score equal total points in all respects, and these tenders are also the highest ranked tenders the award must be decided by the drawing of lots. |
| 5.11.7 | # The value of W1 is: - 90 where the financial value inclusive of VAT of the lowest responsive tender offer received has a value in excess of R50,000,000.00; or - 80 where the financial value inclusive of VAT of the lowest responsive tender offer received equals or is less than R50,000,000.00. A is the number calculated using the formula: A=(1-(P-Pm)/Pm) Where: P is the comparative offer of the tender offer under consideration; and Pm is the comparative offer of the most favourable comparative offer. In the event that the calculated value is negative, the allocated score shall be 0 (zero). |
| 5.11.8 | Up to 100 minus W1 tender evaluation points will be awarded to tenderers who submit responsive tenders and who are found to be eligible for the preference claimed. Points are based on a tenderer’s scorecard measured in terms of the Broad-Based Black Economic Empowerment Act (B-BBEE, Act 53 of 2003) and the Regulations (2017) to the Preferential Procurement Policy Framework Act (PPPFA, Act 5 of 2000). Points awarded will be according to a tenderer’s B-BBEE status level of contributor and summarised in the table below: B-BBEE Status Level of Contributor; Number of points for financial value up to and including R50,000,000; Number of points for financial value above R50,000,000. 1; 20; 10. 2; 18; 9. 3; 14; 6. 4; 12; 5. Other; 0; 0. Eligibility for preference points is subject to the following conditions: - A tenderer’s scorecard shall be a B-BBEE Certificate issued in accordance with: - the Amended Construction Sector Codes published in Notice 931 of 2017 of Government Gazette No. 41287 on 1 December 2017 by the Department of Trade and Industry. - in the event that the Measured Entity operates in more than one sector or a sub-sector, the scorecard for the sector or sub-sector in which the majority of its core activities (measured in terms of annual revenue) are located will be acceptable; and - The scorecard shall be submitted as a certificate attached to Returnable Schedule Form A11; and - The certificate shall: - be valid at the tender closing date; and - have been issued by a verification agency accredited by the South African National Accreditation System (SANAS); or - be in the form of a sworn affidavit accompanied with an audited financial statement of the year concerned or a certificate issued by the Companies and Intellectual Property Commission in the case of an Exempted Micro Enterprise (EME) with a total annual revenue of less than R3 million if issued in accordance with the amended Construction Sector Codes published in Notice 931 of 2017 of Government Gazette No. 41287 on 1 December 2017 by the Department of Trade and Industry; and - have a date of issue less than 12 (twelve) months prior to the original advertised tender closing date (see Tender Data 4.15); and - Compliance with any other information requested to be attached to Returnable Schedule Form A11; and - In the event of a joint venture (JV), a project-specific consolidated B-BBEE verification certificate in the name of the JV must be issued by a verification agency accredited by the South African National Accreditation System (SANAS) shall be submitted. |
| 5.13. | # The conditions stated in clauses 5.13(a) to (f) of the Conditions of Tender as well as the following additional clauses 5.13(g) to (m) shall be applied as objective criteria in terms of section 2(1)(f) of the Preferential Procurement Policy Framework Act, 2000 (Act No 5 of 2000) and as compelling and justifiable reasons in terms of Conditions of Tender clause 5.11: - the tenderer or any of its directors is not listed on National Treasury’s Register of Tender Defaulters or Restricted Suppliers, in terms of the Prevention and Combating of Corrupt Activities Act, 2004 (Act No 12 of 2004) as a tenderer or person prohibited from doing business with the public sector; - the tenderer has not abused the Contractor’s supply chain management system. - the tenderer has not failed to perform on any previous contract and has not been given a written notice to this effect. - the tenderer has not failed to comply with and complete the Declaration Certificate for Local Production and Content (Form A3.5) and the Local Content Declaration: Summary Schedule (Form A3.6) for each product. - the tenderer is tax compliant. The recommended tenderer who becomes non-compliant, prior to award, shall be notified and must become compliant within 7 working days of the date of being notified. A recommended tenderer who remains non-compliant after the 7 working days of being notified, shall be declared non-responsive. - the tenderer is registered and in good standing with the compensation fund or with a licensed compensation insurer. The licensed compensation insurer shall be approved by Department of Labour in terms of Section 80 of the Compensation for Injury and Disease Act, 1993 (Act No. 130 of 1993). - The Contractor has not failed to negotiate acceptable tender sum and/or rates in terms of 5.11.10 |
| 5.17 | The number of paper copies of the signed contract to be provided by the Contractor is one (1). |
| 5.19 | All requests shall be in writing. |
| ADDITIONAL CONDITIONS OF TENDER CLAUSES: |  |
| Clause Number | Data |
| 3.7 | Jurisdiction Unless stated otherwise in the tender data, each tenderer and the Contractor undertake to accept the jurisdiction of the law courts of the Republic of South Africa. |
| 5.11.10 | Negotiating acceptable tender sum and/or rates a) High tender sums submitted by Tenderers If the Contractor choose to include work in the subcontract package, for which he has tendered rates for work items in the Main Contract and the tenderer who scored the highest points tendered a higher sum or rates than that of the Contractor, the Contractor may either accept the rates or negotiate with the preferred tenderer. If the Contractor fails to negotiate a reasonable tender sum or rates with the tenderer, he may approach the second highest point scoring, compliant tenderer for negotiation. This process may be repeated until the Contractor manages to negotiate a reasonable tender sum or rates with a compliant tenderer. b) Provisional Sum If a provisional sum in the main contract is provided for the work items in the subcontract package, the Contractor shall report on the feasibility of the highest point scoring compliant tenderer’s tender sum and rates to the Engineer. - If the highest points scoring compliant tenderer’s tender sum and rates are deemed market related by the Engineer, the Contractor shall obtain the approval of SANRAL to utilise the provisional sum provided for the work items. - If the highest points scoring tenderer’s tender sum and rates are deemed not market related and SANRAL does not approve the utilisation of the relevant provisional sum, the Contractor may either accept the rates or negotiate with the highest points scoring tenderer for a market related tender sum and rates. If the Contractor fails to negotiate market related tender sum and rates with the tenderer, he may approach the next highest point scoring, compliant tenderer for negotiation. This process may be repeated until the Contractor manages to negotiate a reasonable tender sum and rates with a compliant tenderer. c) Low tender sums submitted by Tenderers The Contractor shall report to the Engineer and SANRAL on the feasibility of tender sums, rates or provisional sums of tenderers who tendered exceptionally low. Exceptionally low tender sums, rates or provisional sums are those that are more than ten percent (10%) less than what the Contractor tendered, or in the case of a provisional sum, what is deemed market related by the Engineer. - If the tender sums, rates or provisional sums of those tenderers who tendered exceptionally low are deemed to still be feasible by the Engineer, the Contractor may continue to include these tenders in his tender evaluation. - If the tender sums, rates or provisional sums of those tenderers who tendered exceptionally low are deemed not feasible by the Engineer, the Contractor may disqualify these tenders from his tender evaluation. |

Part T2:	returnable schedules

PART T2:	RETURNABLE SCHEDULES

Table of Contents	Page

T2.1	LIST OF RETURNABLE DOCUMENTS	T2.4

T2.2	RETURNABLE SCHEDULES	T2.5

T2.1	LIST OF RETURNABLE DOCUMENTS

Notes to tenderer:

- Returnable documents have been based on the SANS Standard Conditions of Tender for Construction Procurement and incorporate National Treasury requirements contained in their Standard Bidding Document (SBD) within them.

Returnable documents are separated into the following categories:

(i)	Forms, certificates and schedules for completion by the tenderer for use in 	the quantitative and qualitative evaluation of the tender (Forms A to C).

(ii)	A list of all returnable documents for completion by the tenderer (Form D1).

- Failure to submit fully completed relevant returnable documents may render such a tender offer non-responsive.

- Tenderers shall note that their signatures appended to each returnable form represents a declaration that they vouch for the accuracy and correctness of the information provided.

- Notwithstanding any check or audit conducted by or on behalf of the Contractor, the information provided in the returnable documents is accepted in good faith and as justification for entering into a contract with a tenderer. If subsequently any information is found to be incorrect such discovery shall be taken as willful misrepresentation by that tenderer to induce the contract. In such event the Contractor has the discretionary right under FIDIC Particular Condition 15.6 to terminate the contract.

- These forms must be completed in non-erasable ink and any alterations made prior to tender closure countersigned by an authorised signatory.

(Note to Compiler: All notes are to be addressed and then removed from the draft and final documents)

### T2.1	LIST OF RETURNABLE DOCUMENTS

Note to tenderer:

The list of returnable documents is shown in the following table, as indicated by the status of those documents it will be incorporated into the contract document.

| FORM | LIST OF RETURNABLE DOCUMENTS | STATUS |
| --- | --- | --- |
| FORM A1: | CLARIFICATION BRIEFING |  |
| FORM A2.1: | CERTIFICATE OF AUTHORITY FOR SIGNATORY |  |
| FORM A2.2: | CERTIFICATE OF SINGLE TENDER SUBMISSION |  |
| FORM A2.3: | CERTIFICATE OF FRONTING PRACTICES |  |
| FORM A3.1 (SBD4): | COMPULSORY DECLARATION | CONTRACT |
| FORM A3.2 (SBD9): | CERTIFICATE OF INDEPENDENT TENDER | CONTRACT |
| FORM A3.3 (SBD8): | DECLARATION OF TENDERER’S PAST SUPPLY CHAIN MANAGEMENT PRACTICES | CONTRACT |
| FORM A3.4: | REGISTRATION ON NATIONAL TREASURY CENTRAL SUPPLIER DATABASE | CONTRACT |
| FORM A3.5 (SBD6.2) | DECLARATION CERTIFICATE FOR LOCAL PRODUCTION AND CONTENT FOR DESIGNATED SECTORS | CONTRACT |
| FORM A4: | SCHEDULE OF DEVIATIONS OR QUALIFICATIONS BY TENDERER |  |
| FORM A5: | SCHEDULE OF ADDENDA TO TENDER DOCUMENTS |  |
| FORM A6 (SBD2): | CERTIFICATE OF TAX COMPLIANCE | CONTRACT |
| FORM A7: | TENDERER’S REGISTERED FINANCIAL SERVICE PROVIDER LETTER AND BANK DETAILS |  |
| FORM A8: | SCHEDULE OF CURRENT COMMITMENTS |  |
| FORM A9: | CERTIFICATE OF COMPLIANCE WITH COMPENSATION FOR OCCUPATIONAL INJURIES AND DISEASES ACT,1993 | CONTRACT |
| FORM A10: | REGISTRATION WITH CIDB (If applicable) | CONTRACT |
| FORM A11 (SBD6.1): | PREFERENCING SCHEDULE - TENDERER’S B-BBEE VERIFICATION | CONTRACT |
| FORM B1: | SCHEDULE OF WORK EXPERIENCE |  |
| FORM B2: | SCHEDULE OF CONTRACTOR’S EQUIPMENT |  |
| FORM B3 | FUNCTIONALITY CRITERIA |  |
| FORM C1: | CONTRACTOR’S ESTABLISHMENT ON SITE AND GENERAL OBLIGATIONS |  |
| FORM D1: | SCHEDULE OF TENDER COMPLIANCE |  |
| C1.1.1 (SBD7): | FORM OF OFFER | CONTRACT |
| C1.1.2: | FORM OF ACCEPTANCE | CONTRACT |
| C1.2.3: | CONTRACT DATA – INFORMATION PROVIDED BY THE TENDERER | CONTRACT |
| C2.2 (SBD3): | PRICING SCHEDULE (PROVIDED ON COMPACT DISC) | CONTRACT |

### T2.2	RETURNABLE SCHEDULES

Table of contents	Page

FORM A1: 	CLARIFICATION BRIEFING	T2.6

FORM A2.1: 	CERTIFICATE OF AUTHORITY FOR SIGNATORY	T2.7

FORM A2.2:	CERTIFICATE OF SINGLE TENDER SUBMISSION	T2.8

FORM A2.3:	CERTIFICATE OF FRONTING PRACTICES	T2.9

FORM A3.1:	COMPULSORY DECLARATION	T2.10

FORM A3.2:	CERTIFICATE OF INDEPENDENT TENDER	T2.15

FORM A3.3:	DECLARATION OF TENDERER’S PAST SUPPLY CHAIN MANAGEMENT PRACTICES	T2.17

FORM A3.4:	REGISTRATION ON NATIONAL TREASURY CENTRAL SUPPLIER 
DATABASE	T2.19

FORM A3.5:	DECLARATION CERTIFICATE FOR LOCAL PRODUCTION AND CONTENT FOR DESIGNATED SECTORS	T2.20

FORM A4:	SCHEDULE OF DEVIATIONS OR QUALIFICATIONS BY TENDERER	T2.21

FORM A5:	SCHEDULE OF ADDENDA TO TENDER DOCUMENTS	T2.22

FORM A6:	CERTIFICATE OF TAX COMPLIANCE	T2.23

FORM A7:	TENDERER’S REGISTERED FINANCIAL SERVICE PROVIDER LETTER AND BANK DETAILS	T2.24

FORM A8:	SCHEDULE OF CURRENT COMMITMENTS	T2.26

FORM A9:	CERTIFICATE OF COMPLIANCE WITH COMPENSATION FOR OCCUPATIONAL INJURIES AND DISEASES ACT, 1993	T2.27

FORM A10:	CERTIFICATE OF REGISTRATION WITH CIDB	T2.28

FORM A11:	PREFERENCING SCHEDULE – TENDERER’S B-BBEE VERIFICATION	T2.29

FORM B1:	SCHEDULE OF WORK EXPERIENCE	T2.31

FORM B2:	SCHEDULE OF CONTRACTOR’S EQUIPMENT	T2.32

FORM B3:	FUNCTIONALITY CRITERIA	T2.33

FORM C1:	CONTRACTOR’S ESTABLISHMENT ON SITE AND GENERAL OBLIGATIONS	T2.34

FORM D1:	SCHEDULE OF TENDER COMPLIANCE	T2.35

#### FORM A1: 	CLARIFICATION BRIEFING

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

This is to certify that I,

representative of (tenderer)

of (address)

telephone number

fax number

e-mail

(Note to Compiler: Option 1: where electronic means are available)

read / viewed the clarification briefing presentation/pre-recorded video presented by the Contractor.

TENDERER'S REPRESENTATIVE (Signature)

(Note to Compiler: Option 2: where option 1 is not feasible)

attended the clarification briefing session on 	.(date)

conducted by the Contractor’s representative.

Unless the attendee’s name, details and signature also appear on the attendance register this Certificate of Attendance shall not be accepted and the tenderer’s offer shall be deemed non-responsive and will not be considered.

TENDERER'S REPRESENTATIVE (Signature):

CONTRACTOR’S REPRESENTATIVE (Signature):

NAME (IN CAPITALS):

#### FORM A2.1: 	CERTIFICATE OF AUTHORITY FOR SIGNATORY

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

Notes to tenderer:

1.	The signatory for the tenderer shall confirm his/her authority thereto by attaching a duly signed and dated copy of the relevant resolution of the board of directors/partners on the tendering company’s letterhead.

2.	In the event that the tenderer is a joint venture, a certificate is required from each member of the joint venture clearly setting out:

- authority for signatory,

- undertaking to formally enter into a joint venture contract should an award be made to the joint venture,

- name of designated lead member of the intended joint venture, as required by tender condition 4.13.2.

3.	The resolution below is given as an example of an acceptable format for authorisation, but submission of this page with the example completed shall not be accepted as authorisation of the tenderer’s signatory.

By resolution of the board of directors/partners passed at a meeting held on

Mr./Ms. 		, whose signature appears below, has been

duly authorised to sign all documents in connection with the tender for:

Proforma

SUBCONTRACT

(Insert Contract Number and Description)

and any contract which may arise there from on behalf of

(enter name of tenderer in block capitals)

SIGNED ON BEHALF OF THE COMPANY:

IN THE CAPACITY OF:

DATE:

SIGNATURE OF SIGNATORY:

WITNESSES:

SIGNATURE		SIGNATURE

NAME (PRINT)		NAME (PRINT)

#### FORM A2.2:	CERTIFICATE OF SINGLE TENDER SUBMISSION

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

Notes to tenderer:

- This certificate serves as a declaration by the tenderer that a single tender was submitted.

- In the case of a Joint Venture (JV), a separate certificate is to be completed and submitted by each JV member.

DECLARATION

I, the undersigned,

in submitting the accompanying tender on behalf of the tenderer do hereby make the following statements that I certify to be true and complete in every respect:

- I have read and understand the notes to, and the contents of, this certificate.

- I understand that the accompanying tender and any other tender shall be disqualified in the event that I, including a Joint Venture partner, or Key Person, participate in more than 1 (one) tender.

SIGNATURE: 	…………………………………………………………………

DATE: 	…………………………………………………………………

NAME: 	…………………………………………………………………

POSITION: 	…………………………………………………………………

#### FORM A2.3:	CERTIFICATE OF FRONTING PRACTICES

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

Fronting Practices

Window-dressing: This includes cases in which black people are appointed or introduced to an enterprise on the basis of tokenism and may be:

- Discouraged or inhibited from substantially participating in the core activities of an enterprise; and

- Discouraged or inhibited from substantially participating in the stated areas and/or levels of their participation;

Benefit Diversion: This includes initiatives implemented where the economic benefits received as a result of the B-BBEE Status of an enterprise do not flow to black people in the ratio as specified in the relevant legal documentation.

Opportunistic Intermediaries: This includes enterprises that have concluded agreements with other enterprises with a view to leveraging the opportunistic intermediary's favourable B-BBEE status in circumstances where the agreement involves:

- Significant limitations or restrictions upon the identity of the opportunistic intermediary's suppliers, service providers, clients or customers;

- The maintenance of their business operations in a context reasonably considered improbable having regard to resources; and

- Terms and conditions that are not negotiated at arms-length on a fair and reasonable basis.

DECLARATION

I, the undersigned,

in submitting the accompanying tender on behalf of the tenderer do hereby make the following statements that I certify to be true and complete in every respect:

- I have read and understand the contents of this certificate.

- I accept that the Employer may report fronting practices to the Department of Trade and Industry and the BEE commissioner.

- I accept that intentional misrepresentation by measured entities may constitute fraudulent practices that shall be reported to the Department of Trade and Industry and the BEE commissioner.

SIGNATURE: 	…………………………………………………………………

DATE: 	…………………………………………………………………

NAME: 	…………………………………………………………………

POSITION: 	…………………………………………………………………

FORM A3.1:	COMPULSORY DECLARATION (INCORPORATING SBD4)

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

Notes to tenderer:

- Any legal person, including persons employed by the State, or persons having a kinship with persons employed by the State, including a blood relationship, may make an offer or offers in terms of this tender. In view of possible allegations of favouritism, should the resulting tender, or part thereof, be awarded to persons employed by the State, or to persons connected with or related to them, it is required that the tenderer or his/her authorised representative declare his/her position in relation to the evaluating/adjudicating authority where:

- the tenderer is employed by the State; and/or

- the legal person on whose behalf the tender document is signed, has a relationship with person/s who are involved in the evaluation and/or adjudication of the tender, or where it is known that such a relationship exists between the person or persons for or on whose behalf the declarant acts and persons who are involved with the evaluation and/or adjudication of the tender.

- Definitions:

2.1	“State” means:

- any national or provincial department, national or provincial public entity or constitutional institution within the meaning of the Public Finance Management Act, 1999 (Act No. 1 of 1999);

- any municipality or municipal entity;

- provincial legislature;

- National Assembly or the National Council of Provinces; or

- Parliament.

  - “Shareholder” means a person who owns shares in the company and is actively involved in the management of the enterprise or business and exercises control over the enterprise.

- In the case of a joint venture (JV), a separate declaration form is to be completed and submitted by each JV member.

FORM A3.1 (SBD4):	COMPULSORY DECLARATION (continued)

The following particulars must be furnished. In the case of a joint venture, separate declarations in respect of each partner must be completed and submitted.

Section 1: Enterprise details Name of enterprise. Contact person. E-mail. Telephone. Cell. Fax. Physical address. Postal address.

Section 2: Particulars of companies and close corporations Company / Close Corporation registration number.

Section 3: SARS information Tax reference number. VAT registration number; (state Not Registered if not registered for VAT).

Section 4: CIDB registration number (Not applicable for supplier subcontracts or work without CIDB category, where CIDB registration is not required) CIDB Registration number.

Section 5: Particulars of principals Principal: means a natural person who is a partner in a partnership, a sole proprietor, a director of a company established in terms of the Companies Act of 2008 (Act No. 71 of 2008) or a member of a close corporation registered in terms of the Close Corporations Act, 1984, (Act No. 69 of 1984) Full name of principal; Identity number; Personal tax reference number. Attach separate page if necessary.

FORM A3.1 (SBD4):	COMPULSORY DECLARATION (continued)

Section 6: Record in the service of the state: Indicate by marking the relevant boxes with a cross, if any principal is currently or has been within the last 12 months in the service of any of the following: - a member of any municipal council - a member of any provincial legislature - a member of the National Assembly or the National Council of Province - a member of the board of directors of any municipal entity - an official of any municipality or municipal entity; - an employee of any department, national or provincial public entity or constitutional institution within the meaning of the Public Finance Management Act, 1999 (Act 1 of 1999) - a member of an accounting authority of any national or provincial public entity - an employee of Parliament or a provincial legislature. If any of the above boxes are marked, disclose the following: Name of principal; Name of institution, public office, board or organ of state and position held; Status of service (tick appropriate column). Current; Within last 12 months. Insert separate page if necessary.

Section 7: Record of family member in the service of the state: Family member: a person’s spouse, whether in a marriage or in a customary union according to indigenous law, domestic partner in a civil union, or child, parent, brother, sister, whether such relationship results from birth, marriage or adoption Indicate by marking the relevant boxes with a cross, if any family member of a principal as defined in section 5 is currently or has within the last 12 months been in the service of any of the following: - a member of any municipal council - a member of any provincial legislature - a member of the National Assembly or the National Council of Province - a member of the board of directors of any municipal entity - an official of any municipality or municipal entity; an employee of any department, national or provincial public entity or constitutional institution within the meaning of the Public Finance Management Act, 1999 (Act 1 of 1999) a member of an accounting authority of any national or provincial public entity an employee of Parliament or a provincial legislature. If any of the above boxes are marked, disclose the following: Name of family member; Name of institution, public office, board or organ of state and position held; Status of service (tick appropriate column). Current; Within last 12 months. Insert separate page if necessary.

FORM A3.1 (SBD4):	COMPULSORY DECLARATION (continued)

Section 8: Record of termination of previous contracts with an organ of state Was any contract between the tendering entity, including any of its joint venture partners, terminated during the past five years for reasons other than the employer no longer requiring such works or the employer failing to make payment in terms of the contract? - Yes; No (tick appropriate box). If yes, provide particulars: Insert separate page if necessary

Section 9: Declaration The undersigned, who warrants that he/she is duly authorised to do so on behalf of the tendering entity, confirms that the contents of this Declaration are within my personal knowledge, save where stated otherwise in an attachment hereto, and to the best of my belief is both true and correct, and that: - neither the name of the tendering entity, nor any of its principals, appears on: a) the Register of Tender Defaulters established in terms of the Prevention and Combating of Corrupt Activities Act of 2004 (Act No. 12 of 2004); or b) National Treasury’s Database of Restricted Suppliers (see www.treasury.gov.za); - the tendering entity or any of its principals has not been convicted of fraud or corruption by a court of law (including a court outside of the Republic of South Africa) within the last five years; - any principal who is presently employed by the state has the necessary permission to undertake remunerative work outside such employment (attach permission to this declaration); - the tendering entity is not associated, linked or involved with any other tendering entities submitting tender offers; - the tendering entity has not engaged in any prohibited restrictive horizontal practices, including consultation, communication, agreement, or arrangement with any competing or potential tendering entity regarding prices, geographical areas in which goods and services will be rendered, approaches to determining prices or pricing parameters, intentions to submit a tender or not, the content of the submission (specification, timing, conditions of contract, etc.) or intention to not win a tender; - the tendering entity has no other relationship with any of the tenderers or those responsible for compiling the scope of work that could cause or be interpreted as a conflict of interest; - neither the tenderer nor any of its principals owes municipal rates and taxes or municipal service charges to any municipality or a municipal entity, and are not in arrears for more than three months; - SARS may, on an on-going basis during the term of the contract, disclose the tenderer’s tax compliance status to the Employer and, when called upon to do so, obtain the written consent of any subcontractors who are subcontracted to execute a portion of the contract that is entered into in excess of the threshold prescribed by National Treasury, for SARS to do likewise.

I, the undersigned certify that the information furnished in Form A3 above is correct. I accept that the Employer may reject the tender or act against me in terms of 5.7 of the Conditions of Tender should this declaration prove to be false. Signature (duly authorised) Date Position Name of Enterprise

FORM A3.1 (SBD4):	COMPULSORY DECLARATION (continued)

NOTE 1: The Standard Conditions of Tender contained in SANS 10845-3 prohibits anticompetitive practices (clause 3.1) and requires that tenderers avoid conflicts of interest, only submit a tender offer if the tenderer or any of his principals is not under any restriction to do business with the Employer (4.1.1) and submit only one tender either as a single tendering entity or as a member in a joint venture (clause 4.13.1). Clause 5.7 also empowers the Employer to disqualify any tenderer who engages in fraudulent and corrupt practice. Clause 3.1 also requires tenderers to comply with all legal obligations.

NOTE 2: Section 30(1) of the Public Service Act, 1994, prohibits an employee (person who is employed in posts on the establishment of departments) from performing or engaging remunerative work outside his or her employment in the relevant department, except with the written permission of the executive authority of the department. When in operation, Section 8(2) of the Public Administration Management Act, 2014, will prohibit an employee of the public administration (i.e. municipalities and all national departments, national government components listed in Part A of Schedule 3 to the Public Service Act, provincial departments including the office of the premier listed in Schedule 1 of the Public Service Act and provincial departments listed in schedule 2 of the Public Service Act, and provincial government components listed in Part B of schedule 3 of the Public Service Act) or persons contracted to executive authorities in accordance with the provisions of section 12A of the Public Service Act of 1994 or persons performing similar functions in municipalities, from conducting business with the State or to be a director of a public or private company conducting business with the State. The offence for doing so is a fine or imprisonment for a period not exceeding five years, or both. It is also a serious misconduct which may result in the termination of employment by the employer.

NOTE 3: Regulation 44 of Supply Chain Management regulations issued in terms of the Municipal Finance Management Act of 2003 requires that municipalities and municipal entities should not award a contract to a person who is in the service of the State, a director, manager or principal shareholder in the service of the State or who has been in the service of the State in the previous twelve months.

NOTE 4: Regulation 45 of Supply Chain Management regulations requires a municipality or municipal entity to disclose in the notes to the annual statements particulars of any award made to a close family member in the service of the State.

NOTE 5: Corrupt activities which give rise to an offence in terms of the Prevention and Combating of Corrupt Activities Act of 2004, include improperly influencing in any way the procurement of any contract, the fixing of the price, consideration or other moneys stipulated or otherwise provided for in any contract, and the manipulating by any means of the award of a tender.

NOTE 6: Section 4 of the Competition Act of 1998 prohibits restrictive horizontal practice, including agreements between parties in a horizontal relationship, which have the effect of substantially preventing or lessening competition, directly or indirectly fixing prices or dividing markets or constituting collusive tendering. Section 5 also prohibits restrictive vertical practices. Any restrictive practices that are suspicious will be reported to the Competition Commission for investigation and possible imposition of administrative penalties.

FORM A3.2:	CERTIFICATE OF INDEPENDENT TENDER (INCORPORATING SBD9)

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

Notes to tenderer:

- This certificate conforms to Treasury Regulation 16A9 and the requirement of section 4 (1) (b) (iii) of the Competition Act, 1998 (Act No 89 of 1998), as amended, that prohibits an agreement between, or concerted practice by, firms, or a decision by an association of firms, if it is between parties in a horizontal relationship and if it involves collusive tendering.

- Collusive tendering is a conspiracy between businesses that would normally be expected to compete, to agree not to compete, in a tender process.

- This certificate serves as a declaration by the tenderer that the tender submitted is free from any collusion with a competitor.

- If the tenderer is a joint venture, a declaration is required from each member of the joint venture.

Declaration

I, the undersigned, in submitting the accompanying tender on behalf of the tenderer do hereby make the following statements that I certify to be true and complete in every respect:

- I have read and understand the notes to, and the contents of, this Certificate;

- I understand that the accompanying tender will be disqualified if this Certificate is found to be not true and complete in every respect;

- I am authorised by the tenderer to sign this Certificate, and to submit the accompanying tender, on behalf of the tenderer;

- Each person whose signature appears on the accompanying tender has been authorised by the tenderer to determine the terms of, and to sign the tender, on behalf of the tenderer;

- For the purposes of this Certificate and the accompanying tender, I understand that the word “competitor” shall include any individual or organisation, other than the tenderer, whether or not affiliated with the tenderer, who:

- has been requested to submit a tender in response to this tender invitation;

- could potentially submit a tender in response to this tender invitation, based on their qualifications, abilities or experience; and

- provides the same goods and services as the tenderer and/or is in the same line of business as the tenderer.

- The tenderer has arrived at the accompanying tender independently from, and without consultation, communication, agreement or arrangement with any competitor. However, communication between partners in a joint venture or consortium will not be construed as collusive tendering.

- In particular, without limiting the generality of statement 6 above, there has been no consultation, communication, agreement or arrangement with any competitor regarding:

- prices;

- geographical area where product or service will be rendered (market allocation);

- methods, factors or formulas used to calculate prices;

- the intention or decision to submit, or not to submit, a tender;

- the submission of a tender which does not meet the specifications and conditions of the tender; or

- tendering with the intention not to win the tender.

- In addition, there have been no consultations, communications, agreements or arrangements with any competitor regarding the quality, quantity, specifications and conditions or delivery particulars of the products or services to which this tender relates.

- The terms of the accompanying tender have not been, and will not be, disclosed by the tenderer, directly or indirectly, to any competitor, prior to the date and time of the official tender opening or of the awarding of the contract.

10.	I am aware that, in addition and without prejudice to any other remedy provided to combat any restrictive practices related to tenders and contracts, tenders that are suspicious will be reported to the Competitions Commission for investigation and possible imposition of administrative penalties in terms of section 59 of the Competition Act, 1998 (Act No 89 of 1998) and/or may be reported to the National Prosecuting Authority for criminal investigation and/or may be restricted from conducting business with the public sector for a period not exceeding ten (10) years in terms of the Prevention and Combating of Corrupt Activities Act, 2004 (Act No 12 of 2004) or any other applicable legislation.

SIGNATURE:

NAME:

POSITION:

DATE:

NAME OF TENDERER:

FORM A3.3:	DECLARATION OF TENDERER’S PAST SUPPLY CHAIN MANAGEMENT PRACTICES (INCORPORATING SBD8)

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

Notes to tenderer:

- This declaration:

- must form part of all tenders submitted: and

- if the tenderer is a joint venture, a declaration is required from each member of the joint venture.

- This form serves as a declaration to be used by institutions in ensuring that when goods and services are being procured, all reasonable steps are taken to combat the abuse of the supply chain management system.

- The tender of any tenderer may be disregarded if that tenderer or any of its directors has:

- abused the institution’s supply chain management system;

- committed fraud or any other improper conduct in relation to such system; or

- failed to perform on any previous contract.

- In order to give effect to the above, the following questionnaire must be completed and submitted with this tender.

| 4.1 | Is the tenderer or any of its directors listed on the National Treasury’s Database of Restricted Suppliers as companies or persons prohibited from doing business with the public sector? Companies or persons who are listed on this Database were informed in writing of this restriction by the Accounting Officer/ Authority of the institution that imposed the restriction after the audi alteram parlem rule was applied. The Database of Restricted Suppliers now resides on the National Treasury website (www.treasury.gov.za) and can be accessed by clicking on its link at the bottom of the home page. | Yes | No |
| --- | --- | --- | --- |
| 4.1.1 | If Yes, furnish particulars: |  |  |
| 4.2 | Is the tenderer or any of its directors listed on the Register for Tender Defaulters in terms of Section 29 of the Prevention and Combating of Corrupt Activities Act, 2004 (Act No 12 of 2004)? The Register for Tender Defaulters can be accessed on the National Treasury website www.treasury.gov.za by clicking on its link at the bottom of the home page. | Yes | No |
| 4.2.1 | If Yes, furnish particulars: |  |  |

| 4.3 | Was the tenderer or any of its directors convicted by a court of law (including a court outside the Republic of South Africa) for fraud or corruption during the past five years? | Yes | No |
| --- | --- | --- | --- |
| 4.3.1 | If Yes, furnish particulars: |  |  |
| 4.4 | Was any contract between the tenderer and any organ of State terminated during the past five years on account of failure to perform on or comply with the contract? | Yes | No |
| 4.4.1 | If Yes, furnish particulars: |  |  |

DECLARATION

I, the undersigned,

certify that the information furnished on this declaration form is true and correct.

I accept that, in addition to cancellation of a contract, action may be taken against me should this declaration prove to be false.

SIGNATURE:

POSITION:

DATE:

NAME OF TENDERER:

#### FORM A3.4:	REGISTRATION ON NATIONAL TREASURY CENTRAL SUPPLIER DATABASE

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

The tenderer shall provide a printed copy of the Active Supplier Listing on the National Treasury Central Supplier Database. (www.treasury.gov.za). In the case of a joint venture (JV), the tenderer shall provide printed copies of the Active Supplier Listing on the National Treasury Central Supplier Database for each member of the JV.

Name of Contractor:

CSD Master Registration Number (Supplier Number):

Supplier Commodity:

Delivery Location:

SIGNED BY TENDERER:

FORM A3.5:	DECLARATION CERTIFICATE FOR LOCAL PRODUCTION AND CONTENT FOR DESIGNATED SECTORS (INCORPORATING SBD6.2)

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

The stipulated minimum threshold(s) for local production and content (refer to Annex A of SATS 1286:2011) for this bid are indicated in the below table (Note to Compiler: The below list of materials to be amended by deleting the materials not applicable to the scope of work in line with the Main Contract minimum threshold):

- The Tenderer to confirm that the minimum threshold will be achieved by either indicating the percentage to be achieved or by indicating “Yes” or “” in the below table

| Description of services, works or goods | Stipulated Minimum threshold | Minimum threshold to be achieved by Tenderer |
| --- | --- | --- |
| Steel value-added construction material products |  |  |
| Fabricated Structural Steel | 100% |  |
| Joining/Connecting Components | 100% |  |
| Frames | 100% |  |
| Roof and Cladding | 100% |  |
| Fasteners | 100% |  |
| Wire Products | 100% |  |
| Ducting and Structural Pipework | 100% |  |
| Gutters, downpipes & launders | 100% |  |
| Primary steel construction material products |  |  |
| Plates (>4.5mm thick and supplied in flat pieces | 100% |  |
| Sheets (<4.5mm thick and supplied in coils) | 100% |  |
| Galvanised and Colour Coated coils | 100% |  |
| WireRod and Drawn Wire | 100% |  |
| Sections (Channels, Angles, I-Beams and H-Beams) | 100% |  |
| Reinforcing bars | 100% |  |
| Electrical cable material products |  |  |
| Low Voltage | 90% |  |
| Low Cost Reticulation | 90% |  |
| Medium & High Voltage | 90% |  |
| ACR | 90% |  |
| Telecom cable material products |  |  |
| Optical Fibre Cables | 90% |  |
| Copper Telecom Cables | 90% |  |
| Yellow metal equipment |  |  |
| Articulated dump trucks (ADT) | 60% |  |
| Tractor loader backhoe (TLB) | 60% |  |
| Front end loader (FEL) | 60% |  |
| Plastic Pipes |  |  |
| Polyvinyl chloride (PVC) pipes | 100% |  |
| High density polyethylene (HDPE) pipes | 100% |  |
| Polypropylene (PP) pipes | 100% |  |
| Glass reinforced plastic (GRP) pipes | 100% |  |
| Textiles, Clothing, Leather and Footwear |  |  |
| Textiles | 100% |  |

SIGNED BY TENDERER:

#### FORM A4:	SCHEDULE OF DEVIATIONS OR QUALIFICATIONS BY TENDERER

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

| Page | Description |
| --- | --- |

SIGNED BY TENDERER:

#### FORM A5:	SCHEDULE OF ADDENDA TO TENDER DOCUMENTS

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

## FOR THE

| We confirm that the following communications received from the Employer before the submission of this tender offer, amending the tender documents, have been taken into account in this tender offer. |  |  |
| --- | --- | --- |
|  | Date | Title or Details |

SIGNED BY TENDERER:

FORM A6:	CERTIFICATE OF TAX COMPLIANCE (INCORPORATING SBD2)

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

The tenderer shall complete the declaration below.

I, 	 (name)

the undersigned in my capacity as 	 (position)

on behalf of 	 (name of company)

herewith grant consent that SARS may disclose to the Contractor or to the South African National Roads Agency SOC Limited (SANRAL) our tax compliance status. For this purpose, our unique security personal identification number (PIN) is

our tax reference number is

and our tax clearance certificate number is 	.

In the event of a joint venture, each member shall comply with the above requirement.

SIGNED BY TENDERER:

#### FORM A7:	TENDERER’S REGISTERED FINANCIAL SERVICE PROVIDER LETTER AND BANK DETAILS (Note to Compiler: Delete this form for estimated Subcontract amounts less than R1,000,000.00 therefore not required for CIDB 1 and 2)

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

Notes to tenderer:

- The tenderer shall attach to this form a letter (dated less than 3 months prior to the tender closing date) from a Registered Financial Service Provider (registered with the FSB) which declares how the entity conducts its account and confirms that the Tenderer has the financial means net of current commitments (independent of any contractual advance payment) available to meet the construction cash flow requirements estimated for the subject contract.

- Failure to provide the required letter with the tender submission may render the tenderer’s offer non-responsive in terms of tender condition 5.8.

- In the event that the tenderer is a joint venture enterprise, details of all the members of the joint venture shall be similarly provided and attached to this form.

- The successful tenderer will be requested to demonstrate its financial capability to execute the contract prior to award at the Employer’s discretion

- In the event that the Employer at its sole discretion is not satisfied with the financial capability of the tenderer as a result of whatsoever nature and reason, the Employer reserves the right to invoke the provisions under tender data 5.13. In addition, the Employer reserves the right to perform a full risk assessment as per tender data 5.13. Furthermore, if the aforementioned occurs, any and all report/s will be used to evaluate the Tenderer’s ability to perform the contract as stated in sub-clause 5.13.(b) of the SANS Standard Conditions of Tender.

- The letter shall contain the information as indicated below.

DATE

Bank Name

FSB Number

Bank Address

(Letter to be on the Financial Service Provider’s letter head)

RE:	ACCOUNT CONDUCT AND CASHFLOW CONFIRMATION

To Whom It May Concern:

We hereby confirm that (Insert Tenderer Name) has been banking with xxxx Bank for a period of xxx years and the account has been conducted in a satisfactory manner. (Insert Tenderer Name) has the financial means, net of current commitments, available to meet the construction cash flow requirements to the value of R…… for contract (insert contract number).

- Name of Account Holder:

- Account Number:

- Bank name:

- Branch Number:

- Bank and branch contact details

Yours Sincerely,

BANK STAMP

Name______________________	Signature ___________________

#### FORM A8:	SCHEDULE OF CURRENT COMMITMENTS

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

Notes to tenderer:

- The tenderer shall list below all contracts currently under construction or awarded and about to commence and tenders for which offers have been submitted but awards not yet made.

- In the event of a joint venture enterprise, details of all the members of the joint venture shall similarly be attached to this form.

- The lists must be restricted to not more than 10 contracts and 10 tenders. If a tenderer’s actual commitments or potential commitments are greater than 10 each, those listed should be in descending order of expected final contract value or sum tendered.

| Table 1: CONTRACTS AWARDED |  |  |  |  |
| --- | --- | --- | --- | --- |
| Employer | Contract | Expected total value of contract (incl. VAT) | Duration (Months) | Expected completion date |

| Table 2: TENDERS NOT YET AWARDED |  |  |  |  |
| --- | --- | --- | --- | --- |
| Employer | Contract | Sum Tendered (incl. VAT) | Tendered Duration (Months) | Expected commencement |

SIGNED BY TENDERER:

#### FORM A9:	CERTIFICATE OF COMPLIANCE WITH COMPENSATION FOR OCCUPATIONAL INJURIES AND DISEASES ACT, 1993

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

Notes to tenderer:

- Discovery that the tenderer has failed to make proper disclosure may result in the Contractor terminating a contract that flows from this tender on the ground that it has been rendered invalid by the tenderer’s misrepresentation.

- The tenderer shall attach to this Form evidence that he is registered and in good standing with the compensation fund or with a licensed compensation insurer who is approved by the Department of Labour in terms of section 80 of the Compensation for Occupational Injuries and Diseases Act, 1993 (Act No 130 of 1993) (COID).  If the tenderer fails to meet this requirement, the tenderer will be given 5 calendar days to become compliant.

- The tenderer is required to disclose, by also attaching documentary evidence to this form, all inspections, investigations and their outcomes conducted by the Department of Labour into the conduct of the tenderer at any time during the 36 months preceding the date of this tender.

- In the event of a joint venture, each and every member of the unincorporated Joint Venture shall comply with the above requirements.

SIGNED BY TENDERER:

FORM A10:	CERTIFICATE OF REGISTRATION WITH CIDB Note to Compiler – Delete this form for supplier subcontract or work without CIDB category, where CIDB registration is not required)

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

The tenderer shall provide a printed copy of the Active Contractor’s Listing off the CIDB website www.cidb.org.za. Tenderers whose CIDB registration expires within 21 days after close of tender shall attach proof of their application for re-registration (refer to tender data clause 4.1.1). In the case of a Joint Venture, a printed copy of the Active Contractor’s Listing must be provided for each member of the Joint Venture.

Complete the following details of his registration with the Construction Industry Development Board.

Name of Contractor:

Contractor Grading Designation:

CIDB Contractor Registration Number:

Expiry Date:

SIGNED BY TENDERER:

FORM A11:	PREFERENCING SCHEDULE – TENDERER’S B-BBEE VERIFICATION (INCORPORATING SBD6.1)

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

Notes to Tenderer:

- The tenderer shall attach to this form a valid B-BBEE verification certificate issued in accordance with:

- the amended Construction Sector Codes published in Notice 931 of 2017 of Government Gazette No. 41287 on 1 December 2017 by the Department of Trade and Industry.

- in the event that the Measured Entity operates in more than one sector or sub-sector, the scorecard for the sector or sub-sector in which the majority of its core activities (measured in terms of Annual Revenue) are located will be acceptable.

- The certificate shall:

- have been issued by a verification agency accredited by the South African National Accreditation System (SANAS); or

- be in the form of a sworn affidavit or a certificate issued by the Companies and Intellectual Property Commission in the case of an Exempted Micro Enterprise (EME) with a total annual revenue of less than R3 million if issued in accordance with the amended Construction Sector Codes published in Notice 931 of 2017 of Government Gazette No. 41287 on 1 December 2017 by the Department of Trade and Industry; and

- be valid at the original advertised tender closing date; and

- have a date of issue less than 12 (twelve) months prior to the original advertised tender closing date (see Tender Data 4.15).

- In the event of an un-incorporated joint venture (JV), a project specific consolidated B-BBEE verification certificate in the name of the JV shall be attached, as well as a valid B-BBEE verification certificate for each member of the JV on which the JV certificate was calculated.

- The attached verification certificate and the associated assessment report shall comply with the requirements of Tender Data clause 5.11.8 and shall identify:

- The name and domicilium citandi et executandi of the tenderer.

- The registration and VAT number of the tenderer.

- The dates of granting of the B-BBEE score and the period of validity.

- The expiry date of the verification certificate.

- A unique identification number.

- The standard and/or normative document, including the issue and/or revision used to evaluate the tenderer.

- The name and/or mark/logo of the B-BBEE verification agency or registered auditor.

- The category (Generic, QSE, EME) in which the tenderer has been measured.

- The B-BBEE status level.

- The South African National Accreditation System (SANAS) logo on the verification certificate once verification agencies have been accredited.

- The B-BBEE procurement recognition level.

- The score achieved per B-BBEE element.

- The % black shareholding.

- The % black women shareholding.

- The % black persons with disabilities shareholding

- The % black youth shareholding

- The % black people living in rural or underdeveloped areas or townships shareholding

- The % black military veterans shareholding

- The value-added status of the tenderer.

5.	The Employer will not be responsible to acquire data that it needs for its own reporting systems and which may not form part of a verification agency’s standard certificate format. The tenderer, at its own cost, must acquire any missing specified data listed in 4 above from its selected verification agency or registered auditor and have it recorded on the certificate. Alternatively, such missing data must be supplied separately, but certified as correct by the same verification agency or registered auditor and also attached to this form.

SIGNED BY TENDERER:

#### FORM B1:	SCHEDULE OF WORK EXPERIENCE

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

Notes to tenderer:

- The information in this returnable form for work over the last 5 years will be utilised to calculate points for Previous Relevant Experience (as per Tender Data 5.11.1)

| EMPLOYER (NAME, TEL NO & FAX NO) | CONSULTING ENGINEER (NAME, TEL NO & FAX NO) | NATURE OF WORK | VALUE OF WORK | YEAR COMPLETED |
| --- | --- | --- | --- | --- |
|  | , |  |  |  |

SIGNED BY TENDERER:

#### FORM B2:	SCHEDULE OF CONTRACTOR’S EQUIPMENT

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

Notes to tenderer:

- The tenderer shall provide details of the major plant and equipment required for this contract.

- The information in this returnable form will be utilized to calculate points for Relevant Construction Equipment (as per Tender Data 5.11.1)

- The tenderer shall state below the number of each construction plant to be used on this contract and what constructional plant will be immediately available for this contract, what constructional plant will become available by virtue of outstanding orders, and what further constructional plant will be acquired or hired for the work should the tenderer be awarded the contract. The tender to indicate: Constructional plant owned and immediately available (I); Constructional plant on order (O) (State details of arrangements made, with delivery dates); Constructional plant that will be hired (H) (State details of delivery arrangements)

| PLANT AND EQUIPMENT TYPE (Note to Compiler - list major plant and equipment envisaged to be used on this contract) | NUMBER TO BE USED ON THIS CONTRACT | DATE OF MANUFACTURE | AVAILABILITY (State either I, O or H) |
| --- | --- | --- | --- |

SIGNED BY TENDERER:

#### FORM B3:	FUNCTIONALITY CRITERIA

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

Note to tenderer:

The tenderer shall provide the following functionality criteria in the below table. (Note to Compiler – Align the required criteria with the Tender Data 5.11.1 functionality requirements and therefore remove eg Experience and plant if not applicable)

| FUNCTIONALITY CRITERIA | INFORMATION REQUIRED |  |
| --- | --- | --- |
| Locality | Tenderer address (complete address below and attach proof of address as recorded by the Companies and Intellectual Property Commission (CIPC) of the tenderer’s place of business ) |  |
| CIDB Grade and class (not applicable for supplier subcontracts or work without CIDB category, where CIDB registration is not required) | Indicate Tenderer CIDB grade and class below |  |
| Experience | Complete information in Form B1 |  |
| Plant and equipment | Complete information in Form B2 |  |
| Designated group ownership | Select the appropriate Designated Group ownership of the tenderer below as per B-BBEE certificate (mark with X): |  |
|  | ≥51% ownership by black Youth |  |
|  | ≥51% ownership by black Women |  |
|  | 51% ownership by black Military veterans |  |
|  | ≥51% ownership by black Disabled persons (Differently abled) |  |
|  | None of the above |  |

SIGNED BY TENDERER:

#### FORM C1:	CONTRACTOR’S ESTABLISHMENT ON SITE AND GENERAL OBLIGATIONS

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

Note to tenderer:

If the tenderer should require additional compensation for his obligations under section 1300 (over and above the total tendered for items B13.01(a), (b) and (c)) by including such additional compensation in the tendered rates and/or lump sum of items in the bill of quantities, these items and the value of such additional compensation shall also be set out in a letter attached to this form.

Should the combined, extended total tendered for Item B13.01 The contractor’s general obligations:

- Fixed obligations

- Value-related obligations

- Time-related obligations

exceed a maximum of 15% of the tender sum, the tenderer shall clearly set out his reasons for tendering in this manner in a letter attached to this page.

The Contractor will duly consider these reasons but reserves the right to consider the tendered rates to be imbalanced and to deal with them in terms of Tender Data clause 5.9 contained in this volume.

Total tendered for Item B13.01 expressed as a percentage of the tender sum (excluding VAT) ……...%

SIGNED BY TENDERER:

#### FORM D1:	SCHEDULE OF TENDER COMPLIANCE

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

| FORM NO / SBD NO | FORM DESCRIPTION | TICK IF COMPLETED |
| --- | --- | --- |
| FORM A1: | CLARIFICATION BRIEFING |  |
| FORM A2.1: | CERTIFICATE OF AUTHORITY FOR SIGNATORY |  |
| FORM A2.2: | CERTIFICATE OF SINGLE TENDER SUBMISSION |  |
| FORM A2.3: | CERTIFICATE OF FRONTING PRACTICES |  |
| FORM A3.1 (SBD4): | COMPULSORY DECLARATION |  |
| FORM A3.2 (SBD9): | CERTIFICATE OF INDEPENDENT TENDER |  |
| FORM A3.3 (SBD8): | DECLARATION OF TENDERER’S PAST SUPPLY CHAIN MANAGEMENT PRACTICES |  |
| FORM A3.4: | REGISTRATION ON NATIONAL TREASURY CENTRAL SUPPLIER DATABASE |  |
| FORM A3.5 (SBD6.2) | DECLARATION CERTIFICATE FOR LOCAL PRODUCTION AND CONTENT FOR DESIGNATED SECTORS |  |
| FORM A4: | SCHEDULE OF DEVIATIONS OR QUALIFICATIONS BY TENDERER |  |
| FORM A5: | SCHEDULE OF ADDENDA TO TENDER DOCUMENTS |  |
| FORM A6 (SBD2): | CERTIFICATE OF TAX COMPLIANCE |  |
| FORM A7: | TENDERER’S REGISTERED FINANCIAL SERVICE PROVIDER LETTER AND BANK DETAILS |  |
| FORM A8: | SCHEDULE OF CURRENT COMMITMENTS |  |
| FORM A9: | CERTIFICATE OF COMPLIANCE WITH COMPENSATION FOR OCCUPATIONAL INJURIES AND DISEASES ACT,1993 |  |
| FORM A10: | REGISTRATION WITH CIDB (if applicable) |  |
| FORM A11 (SBD6.1): | PREFERENCING SCHEDULE - TENDERER’S B-BBEE VERIFICATION |  |
| FORM B1: | SCHEDULE OF WORK EXPERIENCE |  |
| FORM B2: | SCHEDULE OF CONTRACTOR’S EQUIPMENT |  |
| FORM B3 | FUNCTIONALITY CRITERIA |  |
| FORM C1: | CONTRACTOR’S ESTABLISHMENT ON SITE AND GENERAL OBLIGATIONS |  |
| FORM D1: | SCHEDULE OF TENDER COMPLIANCE |  |
| C1.1.1 (SBD7): | FORM OF OFFER |  |
| C1.1.2 | FORM OF ACCEPTANCE |  |
| C1.2.3: | CONTRACT DATA – INFORMATION PROVIDED BY THE TENDERER |  |
| C2.2 (SBD3): | PRICING SCHEDULE (PROVIDED ON COMPACT DISC) |  |

SIGNED BY TENDERER:

Part C1:	AGREEMENTS & CONTRACT DATA

PART C1	AGREEMENTS AND CONTRACT DATA

Table of Contents	PAGE

C1.1	FORMS OF OFFER AND ACCEPTANCE	C1.3

C1.1.1	FORM OF OFFER	C1.3

C1.1.2	FORM OF ACCEPTANCE	C1.5

C1.1.3	APPENDIX TO FORM OF ACCEPTANCE	C1.7

C1.1.4	TAX COMPLIANCE	C1.9

C1.1.5	AGREEMENT IN TERMS OF THE OCCUPATIONAL HEALTH AND SAFETY ACT 1993 (ACT NO. 85 OF 1993) AND CONSTRUCTION REGULATIONS, 2014	C1.10

C1.1.6	FORM OF BANKING DETAILS	C1.12

C1.1.7	APPOINTMENT IN TERMS OF SECTION 4 OF THE MINE HEALTH AND SAFETY ACT (Note to Compiler: Delete if not applicable)	C1.13

C1.2	CONTRACT DATA	C1.14

C1.2.1	CONDITIONS OF SUBCONTRACT	C1.14

C1.2.2	APPENDIX TO TENDER: CONTRACT DATA - INFORMATION PROVIDED BY THE CONTRACTOR	C1.36

C1.2.3	APPENDIX TO TENDER: CONTRACT DATA – INFORMATION PROVIDED BY THE TENDERER	C1.40

##### C1.1	FORMS OF OFFER AND ACCEPTANCE

##### C1.1.1	FORM OF OFFER

Contractor

PO Box 415

PRETORIA

0001

Dear Sir,

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

            - I/we, by signing this form of offer acknowledge it is the equivalent of the Letter of Subcontractor’s Offer as defined in clause 1.1.10 in the “Conditions of Subcontract for Construction for Building and Engineering Works designed by the Employer” (2011), published by the International Federation of Consulting Engineers (FIDIC).

            - I/we, confirm that I/we practise the principles of corporate governance that abhors corruption and fraud and that I/we have examined the documents listed in the tender data and addenda thereto as listed in the returnable schedules and am/are duly authorised to represent and commit the tenderer to the contractual obligations contained therein.

            - I/we further confirm that by submitting this offer the tenderer accepts the conditions of tender and offers to perform all of the obligations and liabilities of the contractor under the contract including compliance with all its terms and conditions according to their true intent and meaning for an amount to be determined in accordance with the conditions of tender and the conditions of contract identified in the contract data.

            - PRICE OFFERED

THE OFFERED TOTAL OF THE PRICES (INCLUSIVE OF VALUE ADDED TAX) BROUGHT FORWARD FROM SECTION C2.2: PRICING SCHEDULE SUMMARY IS

(in words)

(R 	 in figures)

I/we confirm that if any difference between the total of the Pricing Schedule Summary and the amounts stated above exists, the total in the Pricing Schedule Summary shall apply.

            - PREFERENCE CLAIMED

I/we claim the following B-BBEE contributor status level ......................... as per Returnable Schedule Form A11: Tenderer’s B-BBEE Verification Certificate subject to Tender Data 5.11.8. In the event of any difference between the above stated status level and the Verification Certificate attached to Form A11, the Verification Certificate shall apply.

            - You may accept this offer by signing and returning to the tenderer one copy of the Form of Acceptance before the end of the period of validity stated in the tender data, (or at the end of any agreed extension thereof), whereupon the tenderer becomes the party named as the contractor in the conditions of contract identified in the contract data.

            - Notwithstanding anything contained in a covering letter to this tender, I/we declare this offer is submitted entirely without deviations or qualifications other than those stipulated in Form A4: Schedule of Deviations or Qualifications by the tenderer and that it is made free from any fraud, corruption and misrepresentation.

Yours faithfully

SIGNATURE:		DATE:

NAME (IN CAPITALS):

CAPACITY:

NAME AND ADDRESS OF ORGANISATION:

NAME AND SIGNATURE OF WITNESSES:

WITNESS 1:

SIGNATURE:

NAME (IN CAPITALS):

WITNESS 2:

SIGNATURE:

NAME (IN CAPITALS):

##### C1.1.2	FORM OF ACCEPTANCE

(Note to Compiler: Form to be printed on Contractor letterhead)

To (Name of successful Subcontractor)

Dear Sir,

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

- It is our pleasure to inform you that the Contractor accepts your select if applicable corrected/corrected alternative/alternative offer in the amount of R…………….. (i.e. including VAT but excluding CPA, and any contingent sum not in the priced schedule) for a contract period of ........... months and with a Base date of ..........(28 days prior to the closing date of subcontract tender)

- The amount due may not be the accepted price but payment shall be made in accordance with the conditions of contract identified in the contract data.

- This Form of Acceptance is the equivalent of the Contractors Letter of Acceptance as defined in clause 1.1.6 of the “Conditions of Subcontract for Construction for Building and Engineering Works designed by the Employer” (2011), published by the International Federation of Consulting Engineers (FIDIC).

- Acceptance shall form an agreement between us according to the terms and conditions contained in this form and in the contract that is comprised of:

Part C1: Agreements and Contract Data (including this form of acceptance),

Part C2: Pricing Data,

Proforma

Part C3: Scope of the Work,

Part C4: Site Information, and

Part C5: Annexures

together with issued drawings and other documents, or parts thereof, which may be incorporated by reference into the Parts listed above.

- Deviations and/or qualifications included in your offer as well as any changes to the terms of the offer agreed by us during the process of offer and acceptance shall not be valid unless contained in the appended schedule of deviations. In the event that an alternative offer is accepted, it is a fundamental condition of acceptance that all responsibilities and concomitant liabilities arising from the alternative design pass from us to you. (Note to Compiler: If no deviation/alternative tender then replace the above part of this paragraph with “There are no alternatives, deviations, qualifications or changes to the documents”). Addenda issued during the tender period are deemed not to be deviations to the tender documents and schedules.

- (Note to Compiler: Delete this paragraph if not applicable – eg. For off-site suppliers) Notwithstanding the need to agree the mandate required by Section 37 of the Occupational Health and Safety Act (Act 85 of 1993), a proforma of which is attached for your reference, we hereby appoint you as the Subcontractor in terms of Regulation 7(1)(v).

- Within 14 calendar days of the date of this Form of Acceptance (including the schedule of deviations if any) you shall deliver to us:

  - Fully completed and signed Form C1.1.3 Appendix to Form of Acceptance

  - Fully completed and signed Form C1.1.4 Tax compliance

  - Fully completed and signed Form C 1.1.5 Agreement in terms of the OHS Act and Regulations.

  - Proof that you are registered and in good standing with the compensation fund or with a licensed compensation insurer.

  - A completed and signed Form C1.1.6 Form of Banking Details

Failure to fulfil any of the above obligations shall constitute a repudiation of this agreement and we may at our discretion apply any rights of remedy including barring you from tendering on any of our future tenders for a period to be determined by us, but not less than six (6) months, from the date of tender closure. Note to Compiler: To agree with Engineer and Sanral prior to this sanction be contemplated)

- The effective date of the Subcontract shall be the date of this Form of Acceptance unless you, within four (4) calendar days of the effective date, notify us in writing of any justification why you cannot accept the contents of this agreement.

- The Subcontract Commencement Date is …. (Note to Compiler: insert relevant day & date not less than 14 days after the date of this Form of Acceptance)

- Notwithstanding that a full, original-signed copy of the Subcontract document containing all contract data and schedules (including that of accepted deviations) will be delivered to you, this Form of Acceptance constitutes the binding Subcontract between us.

- Please contact ………… at ……. to make arrangements for the signing of the Subcontract documents.

Proforma

SIGNATURE:		 DATE:

NAME (IN CAPITALS):

CAPACITY: Managing Director (Note to Compiler: Insert relevant information)

SUBCONTRACTOR’S NAME AND ADDRESS: (Note to Compiler: insert relevant physical address)

NAME & SIGNATURE OF WITNESSES:

WITNESS 1:

SIGNATURE:

NAME (IN CAPITALS):

WITNESS 2:

SIGNATURE:

NAME (IN CAPITALS):

##### C1.1.3	APPENDIX TO FORM OF ACCEPTANCE

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

Notes to Compiler (delete notes for Subcontract document):

- The extent of deviations from the tender documents issued by the Contractor before the tender closing date is limited to those permitted in terms of the conditions of tender.

- A tenderer’s covering letter shall not be included in the final Subcontract document. Should any such letter, which constitutes a deviation as aforesaid, become the subject of agreements reached during the process of offer and acceptance, the outcome of such agreement shall be recorded here.

- Any other matter arising from the process of offer and acceptance, either as a confirmation, clarification or change to the tender documents and which it is agreed by the parties, becomes an obligation of the Subcontract, shall also be recorded here.

- Any change or addition to the tender documents arising from the above agreements and recorded here, shall also be incorporated into the final Subcontract.

Schedule of deviations

The deviations listed below constitute agreed variations/amendments to the tender data and schedules negotiated between the Subcontractor and the Contractor based on information provided in Form A4: Schedule of Variations or Deviations by Subcontractor, or imposed or agreed conditions of award. Addenda issued during the tender period are deemed not to be variations to the tender.

1.	Subject:

Proforma

Details:

2	Subject:

Details:

3	Subject:

Details:

4	Subject:

Details:

By the duly authorised representatives signing this agreement, the Contractor and the tenderer agree to and accept the schedule of deviations as the only deviations from and amendments to the documents listed in the tender data and addenda thereto as listed in the returnable schedules, as well as any confirmation, clarification or changes to the terms of the offer agreed by the tenderer and the Employer during this process of offer and acceptance.

It is expressly agreed that no other matter whether in writing, oral communication or implied during the period between the issue of the tender documents and the receipt by the tenderer of a completed signed copy of this agreement shall have any meaning or effect in the Subcontract between the parties arising from this agreement.

SIGNATURE:		DATE:

NAME (IN CAPITALS):

CAPACITY:

NAME AND ADDRESS OF CONTRACTOR:

##### C1.1.4	TAX COMPLIANCE

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

Note:

In terms of National Treasury Instruction No 3 of 2014/2015 with reference to the Public Finance Management Act, 1999 (Act No 1 of 1999) and Regulations, the contractor and subcontractors are required to provide the Employer with written confirmation to access the SARS Electronic Tax Compliance Status (TCS) System to verify and continuously track the tax compliance status of all persons conducting business with the State.

The Subcontractor shall complete the declaration below.

Proforma

I, 	 (name)

the undersigned in my capacity as 	 (position)

on behalf of

(name of company)

herewith grant consent that SARS may disclose to

(Note to Compiler: insert Contractor description) our tax compliance status on an ongoing basis for the Subcontract term.

For this purpose, our unique security personal identification number (PIN) is 	,

our tax reference number is …………..….. and our tax clearance certificate number is 	.

In addition, the Subcontractor shall obtain written consent from each of its subcontractors, undisclosed principals and partners involved in this Subcontract confirming that SARS may, on an ongoing basis during the Subcontract term, disclose the subcontractors’ tax compliance status to the Employer. For this purpose the Contractor shall provide the Employer with the unique security personal identification number (PIN), tax reference number and tax clearance certificate for each of its subcontractors, undisclosed principals and partners involved in this Subcontract.

SIGNATURE:

DATE:

##### C1.1.5	AGREEMENT IN TERMS OF THE OCCUPATIONAL HEALTH AND SAFETY ACT 1993 (ACT NO. 85 OF 1993) AND CONSTRUCTION REGULATIONS, 2014

This AGREEMENT made at

on this the …………..……. day of ………………………….…….. in the year …………………… between

(Note to Compiler: insert name of Contractor) (hereinafter called "the Contractor") on

the one part, herein represented by

in his capacity as

and 	 (hereinafter called "the Mandatory")

of the other part, herein represented by

in his capacity as

## WHEREAS the Contractor is desirous that certain Works be constructed, namely

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

Proforma

FOR THE

and has accepted a tender by the Mandatory for the construction, completion & maintenance of such works and whereas the Contractor and the Mandatory have agreed to certain arrangements and procedures to be followed in order to ensure compliance by the Mandatory with the provisions of the Occupational Health and Safety Act 1993 (Act 85 of 1993);

NOW THEREFORE THIS AGREEMENT WITNESSETH AS FOLLOWS:

1.	The Mandatory shall execute the work in accordance with the contract documents pertaining to this Subcontract.

2.	This Agreement shall hold good from its commencement date, to either:

(a)	the date of the Performance Certificate issued in terms of sub-clause 11.3 of the FIDIC Conditions of Subcontract for Construction for building and engineering works designed by the Employer, 2011 (hereinafter referred to as "the GCC"), as contained in Volume 1 of the contract documents pertaining to this Subcontract, or

(b)	the date of termination of the Subcontract in terms of clauses 15, 16 or 19 of the GCC.

3	The Mandatory declares himself to be conversant with the following:

(a)	All the requirements, regulations and standards of the Occupational Health and Safety Act (Act 85 of 1993), hereinafter referred to as "The Act", together with its amendments and with special reference to the following Sections of The Act.

(i)	Section 8: General duties of Contractors to their employees.

(ii)	Section 9: General duties of Contractors and self-employed persons to persons other than employees.

(iii)	Section 37: Acts or omissions by employees or mandatories and

(iv)	Sub-section 37(2) relating to the purpose and meaning of this Agreement.

(b)	The procedures and safety rules of the Contractor as pertaining to the Mandatory and to all his Service Providers.

4	In addition to the requirements of sub-clause 2.2 the GCC and all relevant requirements of Volume 3 of the contract documents pertaining to this Subcontract, the Mandatory agrees to execute all the works forming part of this Subcontract and to operate and utilize all machinery, plant and equipment in accordance with The Act.

5.	The Mandatory is responsible for the compliance with the Act by all his Subcontractors, whether or not nominated and/or approved by the Contractor.

6.	The Mandatory warrants that all his and his Subcontractors’ workmen are covered in terms of the Compensation for Occupational Injuries and Diseases Act 1993 which cover shall remain in force whilst any such workmen are present on site. A letter of good standing from the Compensation Commissioner to this effect must be produced to the Contractor upon signature of the agreement.

7.	The Mandatory undertakes to ensure that he and/or his Subcontractors and/or their respective employees will at all times comply with the following conditions:

(a)	The Mandatory shall assume the responsibility in terms of Section 16.1 of The Act. The Mandatory shall not delegate any duty in terms of Section 16.2 of The Act without the prior written approval of the Contractor. If the Mandatory obtains such approval and delegates any duty in terms of section 16.2 a copy of such written delegation shall immediately be forwarded to the Contractor.

(b)	All incidents referred to in The Act shall be reported by the Mandatory to the Department of Labour as well as to the Contractor. The Contractor will further be provided with copies of all written documentation relating to any incident.

(c)	The Contractor hereby obtains an interest in the issue of any formal enquiry conducted in terms of section 32 of The Act into any incident involving the Mandatory and/or his employees and/or its Subcontractors.

Proforma

In witness thereof the parties hereto have set their signatures hereon in the presence of the subscribing witnesses:

SIGNED FOR AND ON BEHALF OF THE CONTRACTOR

WITNESS:

NAME (IN CAPITALS): ...................................................

SIGNED FOR AND ON BEHALF OF THE MANDATARY:

WITNESS: ...................................................

NAME (IN CAPITALS): ...................................................

##### C1.1.6	FORM OF BANKING DETAILS

Notes to Subcontractor:

1.	The Contractor applies an Electronic Funds Transfer system for all payments.

To:

The Subcontractor

(Note to Compiler: insert contractor address)

Dear Sir

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

BANKING DETAILS

By signing this document, we accept the following:

- The banking details submitted are those of (Note to Compiler: insert name of successful subcontractor) and we take full responsibility for their correctness.

- We indemnify the Contractor from any and all outcomes if an electronic transfer is made into an incorrect bank account using the banking details submitted.

Account Name:	…………………………………………………………………………………………

Bank:	…………………………………………………………………………………………

Proforma

Branch Name:	…………………………………………………………………………………………

Branch Code:	…………………………………………………………………………………………

Account Number:	…………………………………………………………………………………………

Yours faithfully

Authorised Signatory for (Note to Compiler: Insert name of successful subcontractor)

DATE: ………………………………………….

##### C1.1.7	APPOINTMENT IN TERMS OF SECTION 4 OF THE MINE HEALTH AND SAFETY ACT (Note to Compiler: Delete if not applicable)

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

APPOINTMENT IN TERMS OF SECTION 4 OF THE MINE HEALTH AND SAFETY ACT (ACT NO 29 OF 1996) AS AMENDED BY THE MINE HEALTH AND SAFETY AMENDMENT ACT (ACT NO 72 OF 1997)

I,

In my capacity as

of the Contractor,

who has contracted with the Employer to undertake the above-named Main Contract, to perform all functions entrusted to the Employer by sections 2 and 3 of the Act, as amended, who is the owner of the Mines(s) state name (s) or state "to be worked under the requirements of the abovementioned contract"

hereby appoint

of the Subcontractor,

who has contracted with the Contractor to undertake the above-named Subcontract, to perform all functions entrusted to the Contractor by sections 2 and 3 of the Act, as amended.

Signed:

Date:

Witnesses:	1.			2.

Name (print) 		Name (print)

I hereby accept the above appointment

Signed:

Date:

Witnesses:	1.			2.

Name (print) 		Name (print)

##### C1.2	CONTRACT DATA

##### C1.2.1	CONDITIONS OF SUBCONTRACT

Note to tenderer

1.	The Conditions of Subcontract comprise the “General Conditions of Subcontract”, which form part of the “FIDIC Conditions of Subcontract for Construction”, First Edition 2011, publish by the International Federation of Consulting Engineers (FIDIC), and the following “Particular Conditions of Subcontract”, which include amendments and additions to these General Conditions of Subcontract. as prescribed by the Contractor.

TABLE OF CONTENTS	PAGE

PART A:	CONDITIONS OF SUBCONTRACT FOR CONSTRUCTION - FIDIC 
AMENDMENTS	C1.15

PART B:	PARTICULAR CONDITIONS OF SUBCONTRACT	C1.16

1.1	Subcontract Definitions	C1.17

1.5	Priority of Subcontract Documents	C1.18

1.6	Notices, Consents, Approvals, Certificates, Confirmations, Decisions, and Determinations	C1.18

1.7	Joint and Several Liability under the Subcontract	C1.18

1.9	Subcontract Agreement	C1.18

2.1	Subcontractor’s Knowledge of Main Contract	C1.19

3.2	Access to the Site	C1.19

6.4	Subcontractor’s Representative	C1.19

“6.5	Recruitment of Labour, Rates of Wages and Conditions of 
Labour	C1.19

6.6	Working Hours	C1.19

6.7	Health and Safety	C1.20

6.8	Subcontractor’s Personnel	C1.20

6.9	Records of Subcontractor’s Personnel and Equipment	C1.20

8.1	Commencement of Subcontract Works	C1.20

8.6	Suspension of Subcontract Works by the Contractor	C1.20

8.7	Subcontract Damages for Delay	C1.20

“8.8	Incentive for early completion of Subcontract section	C1.21

10.2	Taking Over Subcontract Works	C1.21

11.2	Subcontract Defects Notification Period	C1.21

11.3	Performance Certificate	C1.21

14.1	The Subcontract Price	C1.21

14.6	Interim Subcontract Payments	C1.21

14.7	Payment of Retention Money under the Subcontract	C1.22

14.8	Final Subcontract Payment	C1.22

15.3	Payment after Termination of the Main Contract	C1.22

15.5	Notice to Correct under the Subcontract	C1.22

17.3	Subcontract Limitation of Liability	C1.22

“17.4	Intellectual and Industrial Property Rights	C1.23

20.4	Subcontract Disputes	C1.23

20.5	Appointment of the Subcontract DAB	C1.23

20.6	Obtaining Subcontract DAB’s Decision	C1.23

20.7	Subcontract Arbitration	C1.23

ANNEX A:	PARTICULARS OF THE MAIN CONTRACT	C1.24

ANNEX B:	SCOPE OF SUBCONTRACT WORKS AND SCHEDULES OF SUBCONTRACT DOCUMENTS	C1.26

ANNEX C:	INCENTIVE(S) FOR EARLY COMPLETION, TAKING-OVER BY THE CONTRACTOR AND SUBCONTRACT BILL OF QUANTITIES	C1.27

ANNEX D:	EQUIPMENT, TEMPORARY WORKS, FACILITIES, AND FREE-ISSUE MATERIALS TO BE PROVIDED BY THE CONTRACTOR (Sub-clause 4.1, 7.1 & 7.2)	C1.28

ANNEX E:	INSURANCES (Sub-clause 18.1 & 18.2)	C1.30

ANNEX F:	SUBCONTRACT PROGRAMME (Sub-clause 8.3)	C1.31

###### PART A:	CONDITIONS OF SUBCONTRACT FOR CONSTRUCTION - FIDIC AMENDMENTS

Up to … (Note to Compiler: insert current date) the following amendments have been issued by FIDIC.

###### PART B:	PARTICULAR CONDITIONS OF SUBCONTRACT

The following additional amendments to the FIDIC Conditions of Subcontract for Construction, 2011 apply to this contract.

SUBJECT INDEX

| Index | Clause |  | Clause |
| --- | --- | --- | --- |
| Access to the site | 3.2 | Subcontract agreement | 1.9 |
| Appendix to Subcontractor’s Offer definition | 1.1.3 | Subcontract arbitration | 20.7 |
| Appointment of a subcontract DAB | 20.5 | Subcontract Bill of Quantities definition | 1.1.18 |
| BP definition | 1.1.42 | Subcontract damages for delay | 8.7 |
|  |  | Subcontract Defects Notification | 11.2 |
| Commencement of subcontract works | 8.1 | Period |  |
| Contractors Letter of Acceptance definition | 1.1.6 | Subcontract definitions | 1.1 |
| Cost definition | 1.1.40 | Subcontract disputes | 20.4 |
|  |  | Subcontractor limitation of liability | 17.3 |
| Day definition | 1.1.45 | Subcontract Specification definition | 1.1.29 |
|  |  | Subcontractor’s Base Date definition | 1.1.44 |
| Final subcontract payment | 14.8 | Subcontractor’s knowledge of Main | 2.1 |
|  |  | Agreement |  |
| Health and safety | 6.7 | Subcontractor’s personnel | 6.8 |
|  |  | Subcontractor’s representative | 6.4 |
| Incentive for early completion of Subcontract | 8.8 | Suspension of Subcontract works | 8.6 |
| section |  | By the contractor |  |
| Interim subcontract payments | 14.6 |  |  |
| Intellectual and Industrial property rights | 17.4 | Target Area definition | 1.1.41 |
|  |  | Taking over subcontract works | 10.2 |
| Joint and several liability under the | 1.7 | Targeted Enterprise definition | 1.1.42 |
| Subcontract |  | Targeted Labour definition | 1.1.43 |
|  |  | The subcontract price | 14.1 |
| Letter of Subcontractor’s Offer definition | 1.1.10 |  |  |
|  |  | Working day definition | 1.1.46 |
| Notices, Consents, Approvals, Certificates, | 1.6 | Working hours | 6.6 |
| Confirmations, Decisions and Determinations |  |  |  |
| Notice to correct under the subcontract | 15.5 |  |  |
| Obtaining Subcontract DAB’s decision | 20.6 |  |  |
| Payment after termination of the Main contract | 15.3 |  |  |
| Payment after termination of the Main | 15.3 |  |  |
| Contract |  |  |  |
| Payment of retention money under the | 14.7 |  |  |
| subcontract |  |  |  |
| Performance certificate | 11.3 |  |  |
| Priority of Subcontract Documents | 1.5 |  |  |
| Records of Subcontractor’s Personnel | 6.9 |  |  |
| Recruitment of Labour, Rates of wages and | 6.5 |  |  |
| conditions of labour |  |  |  |
| Request for proposal for subcontract variation | 13.3 |  |  |

PARTICULAR CONDITIONS AMENDING THE GENERAL CONDITIONS OF SUBCONTRACT FOR CONSTRUCTION (FIDIC)

###### 1.1	Subcontract Definitions

Replace 1.1.3 with:

“ “Appendix to the Subcontractor’s Offer” means the completed sections entitled C1.2.2 Appendix to Tender: Contract Data – Information provided by the Contractor and C1.2.3 Appendix to Tender: Contract Data – Information provided by the Tenderer.”

Replace 1.1.6 with:

“ “Contractor’s Letter of Acceptance” means the Form of Acceptance as contained in part C1.1.2 of the Subcontract including any appended memoranda comprising agreements between and signed by both Parties to the Subcontract.”.

Replace 1.1.10 with:

“ “Letter of Subcontractor’s Offer” means the Form of Offer as contained in part C1.1.1 of the Subcontract.”

1.1.18	Add the following:

“Subcontract Bill of Quantities shall also mean the Pricing Schedule as contained in Part C2 of the Subcontract .”

Replace 1.1.29 with:

“ “Subcontract Specification” means that document entitled Scope of Works, as included in the Subcontract, and any additions and modifications to the Scope of Works in accordance with the Main Contract. Such document specifies the Works.”

Add the following:

    - “Cost” as stated under Main Contract Sub-Clause 1.1.4.3.

    - “Target Area” means the geographic area defined in the Main Contract’s Contract Data for Targeted Labour and which typically are:

              - one or more Provinces;

              - one or more Metropolitan or District Municipalities;

              - one or more Local Municipalities;

              - one or more Wards that are predominantly located within an area and within a predefined radius of the construction activity;

              - one or more of the areas listed in the definition of Designated Groups.

    - Targeted Enterprise” is is an entity to which the Contractor subcontracts a percentage of the contract value as a condition of contract and which is:

- an EME or QSE which is at least 51% owned by black people;

- an EME or QSE which is at least 51% owned by black people who are youth;

- an EME or QSE which is at least 51% owned by black people who are women;

- an EME or QSE which is at least 51% owned by black people with disabilities;

- an EME or QSE which is 51% owned by black people living in rural or underdeveloped areas or townships;

- a cooperative which is at least 51% owned by black people;

- an EME or QSE which is at least 51% owned by black people who are military veterans; or

- more than one of the categories referred to in paragraphs a to g; and

- which is tax and COID compliant.

    - “Targeted Labour” means Persons:.

  - who are employed by the Contractor or a subcontractor in the performance of the Main Contract; and

  - whose monthly earnings are derived from hours worked for a fixed hourly rate which is adjusted from time to time by legislation (as a statutory minimum) and the Contractor’s or subcontractor’s employment policies; and

  - permanently reside in the Target Area(s) or who are recognized as being residents of the Target Area(s) based on identification and association with, and recognition by, the residents of the Target Area(s); and

  - who are defined as a Target Group in the Main Contract’s Contract Data.

    - “Subcontract’s Base Date” means the date 28 days prior to the latest date for submission of the subcontract tender.

    - A “day” means a calendar day, except for any extension of time that is granted under Sub-Clause 8.4 [Extension of Subcontract Time for Completion], in which case a “day” means a working day. A “year” means 365 calendar days.

    - A “working day” means a day that is not listed as a Special non-working day.

###### 1.5	Priority of Subcontract Documents

Insert the following at the end of the 1st paragraph before the colon:

“… unless specifically stated otherwise in the Subcontract”

Replace sub-paragraph items (1) to (9) with:

“(1)	the Forms of Offer and Acceptance;

(2)	the Appendix to the Subcontractor’s Offer;

(3)	the Particular Conditions of Subcontract and Annexes, except any part of any Annex that is referred to elsewhere in this listed priority of Subcontract documents;

(4)	the General Conditions of Subcontract;

(5)	the Subcontract Specification;

(6)	the Subcontract Drawings,

(7)	the Standard Specifications,

(8)	the Subcontract Bill of Quantities; and

(9)	the Schedules and any other documents forming part of the Subcontract.”

###### 1.6	Notices, Consents, Approvals, Certificates, Confirmations, Decisions, and Determinations

Add the following paragraph at the end of this clause:

“However, such notice, instruction, consent or request is not deemed to have been delivered by virtue of its appearance in the minutes of meetings.”

###### 1.7	Joint and Several Liability under the Subcontract

Replace 1.7(b) with:

“(b)	No later than 14 days after the date of the Contractor’s Letter of Acceptance these persons shall notify the other Party of their leader who shall have authority to bind that other Party and each of these persons; and”

###### 1.9	Subcontract Agreement

Replace the 1st two sentences with the following:

“The Parties shall enter into a Subcontract Agreement when the Contractor issues to the Subcontractor the Contractor’s Letter of Acceptance (see Particular Condition Sub-Clause 1.1.6). The Subcontract Agreement shall be in the form prescribed in the tender documents.”

Add the following at the end of the sub-clause:

“If under the Main Contract, the Engineer does not consent to the Subcontract, upon notice from the Contractor of such non-consent:

    - The Parties shall be discharged from further performance of the Subcontract, without prejudice to the rights of either Party in respect of any previous breach of the Subcontract;

    - The Contractor shall immediately return the Subcontract Performance Guarantee (if applicable) to the Subcontractor; and

    - Payment by the Contractor of the amounts and/or Costs as described in (a) to (d) of Sub-Clause 15.3 [Payment after Termination of the Main Contract] shall be due 28 days after the Parties’ discharge from the Subcontract.”

###### 2.1	Subcontractor’s Knowledge of Main Contract

In the 8th line of the 1st paragraph after the word “Contract”, add “as amended”.

Add the following paragraph at the end of the last paragraph:

“The Subcontractor shall treat the details of the Subcontract as private and confidential, except to the extent necessary to carry out obligations under it or to comply with applicable Laws. The Subcontractor shall not publish, permit to be published, or disclose any particulars of the Subcontract Works or the Main Works in any trade or technical paper or elsewhere without the previous agreement of the Contractor.”

###### 3.2	Access to the Site

Delete the 2nd paragraph and substitute the following:

“Right of access to and possession of the Site shall be on Subcontract Commencement Date except if otherwise detailed in the Subcontract Specification. The Contractor shall not be bound to make any part of the Site available exclusively to the Subcontractor except those parts of the Site for those periods as expressly detailed in the Subcontract Specification.”

###### 6.4	Subcontractor’s Representative

Add the following paragraph at the end of this clause:

“The Contractor may require the Subcontractor’s Representative to attend progress and/or contractual meetings with the Employer and/or the Engineer. If the Subcontractor’s Representative attends any of these meetings, he shall be permitted to review the record of the meeting and, if he has not objected to this record within 7 days of its receipt, those minutes shall be deemed to be accurate and to be accepted by the Subcontractor’s Representative.”

Add the following new sub-clauses:

###### “6.5	Recruitment of Labour, Rates of Wages and Conditions of Labour

The Subcontractor shall utilise Labour and Targeted Labour from the Target Area(s) as stated in the Main Contract, utilising the Labour Database of Targeted Labour as stated in the Main Contract.

The Subcontractor shall pay rates of wages, and observe conditions of labour, which are not lower than those established for the trade or industry where the work is carried out. If no established rates or conditions are applicable, the Subcontractor shall pay rates of wages observe conditions which are not lower than the general level of wages and conditions observed locally by the employers whose trade or industry is similar to that of the Contractor. The conditions as stated in the Appendix to the Subcontractor’s Offer as well as shall also apply.

###### 6.6	Working Hours

No work shall be carried out on Site on any special non-working day or within non-working hours of any day as stated in the Appendix to the Subcontractor’s Offer unless:

(a)	Otherwise stated in the Subcontract or Main Contract

(b)	The Contractor gives consent; or

(c)	The work is unavoidable or necessary for the protection of life or property or for the safety of the Works, in which case the Subcontractor shall immediately advise the Contractor.

###### 6.7	Health and Safety

The Subcontractor shall be in good standing in terms of the Compensation for Occupational Injuries and Disease Act (COIDA) and have a letter as proof.

The Subcontractor shall be made conversant and comply with the Contractor’s project specific Health and Safety plan, at all times.

The Subcontractor shall comply with all legal requirements pertaining to an employer, which include the responsibility to provide as far as reasonably practicable a safe and healthy working environment for his employees, as per Section 8 of the OHS Act.

###### 6.8	Subcontractor’s Personnel

The Subcontractors’ personnel shall be appropriately skilled and experienced in their respective trades or occupations. The Contractor may require the Subcontractor to remove (or cause to be removed) any person employed on the site or works, including the Subcontractors’ representative, if applicable, who:

    - Persists in any misconduct and lack of care

    - Carries out duties incompetently or negligently

    - Fails to conform with any provision of the Subcontract

    - Persists in any conduct which is prejudicial to safety, health or protection of the environment

    - is found, based on reasonable evidence, to have engaged in corrupt, fraudulent, collusive or coercive practice; or

    - has been recruited from the Contractor’s Personnel or the Employer’s Personnel in breach of Sub-Clause 6.2 [Persons in the Service of Others].

The Subcontractor and/or his personnel will be provided with opportunities to receive training as contemplated in the Main Contract. The Subcontractor shall co-operate and ensure participation in all training provided.

###### 6.9	Records of Subcontractor’s Personnel and Equipment

The Subcontractor shall submit, to the Contractor, details showing the number of each class of Subcontractor’s Personnel and of each type of Subcontractor’s Equipment on the Site. Details shall be submitted each calendar month, in a form approved by the Contractor, until the Subcontractor has completed all the Subcontract Works.”

###### 8.1	Commencement of Subcontract Works

In the 2nd line of the 2nd paragraph, after the words “Commencement Date”, insert “but within the period stated in the Appendix to the Subcontractor’s Offer”

###### 8.6	Suspension of Subcontract Works by the Contractor

Add the following to the end of the 1st paragraph:

“If Main Contract Sub-Clause 8.9 [Consequences of suspension] applies, then the Cost payable shall be the Suspension cost calculated in pay item B13.01 of the Subcontract Bill of Quantities (if applicable and as appropriate having regard to any other compensation which may already have been granted in respect of the circumstances concerned), else Cost payable shall be all expenditure reasonably incurred (or to be incurred) by the Subcontractor, whether on or off the Site, including overhead and similar charges, but does not include profit.”

###### 8.7	Subcontract Damages for Delay

Replace the last sentence of the 1st paragraph with the following:

‘These delay damages shall be as calculated from the rate stated in the Appendix to the Subcontractor’s Offer, for every day between the relevant Subcontract Time for Completion and the date upon which completion of the Subcontract Works or Subcontract Section was achieved in accordance with Sub-Clause 10.1 [Completion of Subcontract Works]. However, the total amount due under this sub-clause shall be as determined between the Contractor, Engineer and Employer and shall not exceed the maximum amount of delay damages (if any) stated in the Appendix to the Subcontractor’s Offer.”

###### 10.2	Taking-Over Subcontract Works

Add the following paragraph:

“The Employer may make use of any part of the permanent works prior to issue of a taking-over certificate for the Subcontract Works.”

###### 11.2	Subcontract Defects Notification Period

Add the following paragraph after the 1st paragraph:

“If the Subcontract Works is taken-over by the Contractor before taking-over of the Main Works by the Employer in terms of Sub-Clause 10.3 [Taking-Over by the Contractor], then the Subcontract Defects Notification Period shall be from the date on which the whole of the Subcontract Works have been taken-over under Clause 10 [Completion of and Taking-Over the Subcontract Works] until expiry of the period as stated in the Appendix to the Subcontractor’s Offer.”

Replace Sub-Clause 11.3 [Performance Certificate], with the following new subclause 11.3 [Subcontract Performance Certificate]:

###### “11.3	Subcontract Performance Certificate

Performance of the Subcontractor’s obligations shall not be considered to have been completed until the Contractor has issued the Subcontract Performance Certificate to the Subcontractor, stating the date on which the Subcontractor has completed his obligations under the Subcontract. The Contractor shall issue the Subcontract Performance Certificate within 7 days of the expiry of the Subcontract Defects Notification Period, or as soon thereafter as the Subcontractor has supplied all the Subcontractor’s Documents and completed and tested all the Subcontract Works, including remedying any defects.

After the Subcontract Performance Certificate has been issued, the provisions of the Main Contract Clauses 11.10 [Unfulfilled Obligations] and 11.11 [Clearance of Site] shall apply equally to the Subcontract.“

###### 14.1	The Subcontract Price

Add the following new paragraphs:

“Any quantities which may be set out in the Subcontract Bill of Quantities or other Schedule are estimated quantities and are not to be taken as the actual and correct quantities:

- of the Subcontract Works which the Subcontractor is required to execute, or

- for the purposes of Clause 12 [Measurement and Evaluation]

The Subcontractor shall submit to the Contractor within 14 days of receiving a written request, a full breakdown of all rates. The Contractor may take account of the breakdown when evaluating claims and making decisions.”

###### 14.6	Interim Subcontract Payments

In the 1st line of the 1st paragraph, delete “70 days” and replace with “14 days (if the Subcontractor is a Targeted Enterprise) or 30 days (if the Subcontractor is not a Targeted Enterprise)”.

Delete all the paragraphs except for, the 1st paragraph (ending with the words “… Appendix to the Subcontractor’s Offer.”) and the last paragraph (commencing with the words “If the Subcontractor is under …”), and replace with the following paragraph:

“Provided that the Contractor shall be entitled to withhold or defer payment of all or part of any sums otherwise due in respect of a Subcontractor’s monthly statement if a dispute arises or has arisen between the Subcontractor and the Contractor involving any question of measurement or quantities or any other matter included in the Subcontractor’s monthly statement. Any payment so withheld or deferred shall be limited to the extent that the amounts in the Subcontractor’s monthly statement are the subject of a dispute. If the Contractor withholds or defers payment of any amount in a Subcontractor’s monthly statement, then he shall notify the Subcontractor of his reasons for doing so as soon as is reasonably practicable but not later than the date when this payment would otherwise have become due. The Contractor’s withholding or deferring payment of any amount in a Subcontractor’s monthly statement shall not preclude the Subcontractor from including that amount in following Subcontractor’s monthly statements.”

Add the following as a new pen-ultimate paragraph:

“The Contractor shall pay the Subcontractor the full value as certified by the Engineer as being due to the Subcontractor in each Interim Payment Certificate, without any deduction for plant, equipment, materials or fuel supplied by the Contractor.”

###### 14.7	Payment of Retention Money under the Subcontract

Delete all the paragraphs and replace with the following paragraphs:

“If the whole of the Subcontract Works have been taken-over under Sub-Clause 10.2 [Taking-Over the Subcontract Works] or Sub-Clause 10.3 [Taking-Over by the Contractor], the Contractor shall pay the Subcontractor the first half of the retention money under the Subcontract no later than 14 days after the whole of the Subcontract Works have been taken-over and all minor outstanding work have been completed. If a part of the Subcontract Works has been taken-over under Sub-Clause 10.2 [Taking-Over the Subcontract Works] or Sub-Clause 10.3 [Taking-Over by the Contractor], the Contractor shall pay the Subcontractor a proportion of the retention money under the Subcontract no later than 14 days after that part has been taken-over by the Contractor. This proportion shall be 50% of the proportion calculated by dividing the estimated subcontract value of the part by the estimated final Subcontract Price.

No later than 7 days after expiry of the Subcontract Defects Notification Period, the Contractor shall pay the Subcontractor the remaining portion of the retention money under the Subcontract. However, if any work remains to be executed under Clause 11 [Defects Liability], the Contractor shall be entitled to withhold payment of the estimated cost of this work until it has been executed and the Subcontract Performance Certificate issued.”

###### 14.8	Final Subcontract Payment

Delete the last paragraph and replace with the following:

“Within 7 days after the Subcontractor has finally performed his obligations under the Subcontract, provided that 35 days have expired since submission by the Subcontractor of the Subcontractor’s Final Statement, the Contractor shall pay to the Subcontractor the balance of the Subcontract Price finally due.”

###### 15.3	Payment after Termination of the Main Contract

Delete the 2nd and 3rd paragraphs (beginning with “If the Main Contract has been terminated …” and ending with “… the Subcontractor shall place the same at the Employer’s disposal.”) and replace with the following:

“Payment by the Contractor of any of these amounts or Costs shall be due as soon as practicable after termination of the Subcontract.

If Main Contract Clause 19.7 [Release from Performance under the Law] applies to the Main Contract or the Main Contract has been terminated under Main Contract Sub-Clause 16.2 [Termination by Contractor] or Main Contract Sub-Clause 19.6 [Optional Termination, Payment and Release], and the Contractor receives payment from the Employer for any Subcontract Plant and/or materials, then the Subcontract Plant and/or materials shall become the property of (and be at the risk of) the Employer when paid for by the Employer, and the Subcontractor shall place the same at the Employer’s disposal.”

###### 15.5	Notice to Correct under the Subcontract

Add the following at the end of the 1st paragraph:

“The Notice shall:

- describe the Subcontractor’s failure;

- state the sub-clause and/or provisions of the Contract under which the Subcontractor has the obligation; and

- specify the time within which the Subcontractor shall remedy the failure, which shall be reasonable, taking due regard of the nature of the failure and the work and/or other action required to remedy it.

The time specified in the Notice to Correct shall not imply any extension of Time for Completion.”

###### 17.3	Subcontract Limitation of Liability

Add the following additional clause references to the last sentence of the 1st paragraph, before the words “under Clause 15 [Termination of the Main Contract and Termination of the Subcontract by the Contractor]” :

“ as specifically provided for in Sub-Clause 8.7 [Subcontract Damages for Delay]; Sub-Clause 17.4 [Intellectual and Industrial Property Rights]; and under”

Add the following new sub-clause:

###### “17.4	Intellectual and Industrial Property Rights

The provisions of Main Contract Sub-Clause 17.5 [Intellectual and Industrial Property Rights] shall apply to the Subcontract.”

###### 20.4	Subcontract Disputes

Add the following after the 1st paragraph:

“The Notice of Dispute shall be given as soon as practicable, and not later than 21 days after the Party became aware, or should have become aware, of the event or circumstance giving rise to the Dispute. The Notice of Dispute shall refer to the relevant clause(s) in the subcontract agreement. If the Party fails to give notice, he shall have no further right to dispute the event or circumstance, or the part thereof not disputed in the said notice.

Prior to referral of any dispute to the Subcontract DAB in terms of this Sub-Clause, the dispute shall first be referred to the Engineer in writing for its decision, with a copy to the other Party. The Engineer’s decision shall be binding on both Parties unless and until it shall be revised by a Subcontract DAB decision in accordance with Sub-clause 20.6 [Obtaining Subcontract DAB’s Decision]. Either Party shall have the right to refer a dispute to the Subcontract DAB after receipt of the Engineer’s decision on the dispute. Provided that, unless either Party shall, within 21 days after his receipt of a decision by the Engineer, refer the dispute to the Subcontract DAB for a decision, he shall have no further right to dispute that decision or the part thereof not disputed in the said notice. “

Add the following paragraphs before the last paragraph:

“Where the subject of the Subcontractor dispute is referred to the Main Contract DAB, the Contractor shall use all reasonable endeavours to pursue the dispute on the Contractor’s and the Subcontractor’s behalf and for both the Contractor’s and the Subcontractor’s benefit, and shall regularly keep the Subcontractor informed of the progress of these endeavours. The Contractor shall as soon as practicable but not later than 7 days of its receipt of the Main Contract DAB decision, notify the Subcontractor of this decision. Unless the Subcontractor notifies the Contractor of his dissatisfaction with the Main Contract DAB’s decision within 7 days of his receipt of the Contractor’s notice, this decision shall be deemed to be accepted by the Subcontractor. This decision shall be binding on both Parties to the Subcontract unless and until it shall be revised in an amicable settlement as described in Sub-Clause 20.6 [Obtaining Subcontract DAB’s Decision], or an arbitral award in accordance with Sub-Clause 20.7 [Subcontract Arbitration].”

###### 20.5	Appointment of the Subcontract DAB

Add the following prior to the 1st paragraph:

“Where the subject of the Subcontract dispute is not referred to the Main Contract DAB, and the decision by the Engineer on a dispute made under Sub-clause 20.4 [Subcontract Disputes], is referred to the Subcontract DAB, the dispute between the Contractor and the Subcontractor shall be decided by a Subcontract DAB.

Where a Main Contract DAB is appointed under the Main Contract, the Subcontract DAB shall comprise of the members of the Main Contract DAB.”

Add the following as the 1st part of the 1st sentence of the 1st paragraph:

“Where a Main Contract DAB is not appointed under the Main Contract…”

In the 10th line of the 1st paragraph, replace “FIDIC” with “SAICE”.

In the last sentence of the last paragraph delete the full stop and add the following:

“and the provisions relating to payment shall not apply hence the Party that referred the dispute to the Subcontract DAB shall be responsible for paying the remuneration of the Subcontract DAB.”

###### 20.6	Obtaining Subcontract DAB’s Decision

Add the following after the 1st paragraph:

“The appointed Subcontractor’s DAB shall have the freedom to first mediate between the parties in an effort to settle the dispute by mutual agreement before adjudicating the matter as is provided for in these conditions and give a decision in the dispute that has been referred.”

###### 20.7	Subcontract Arbitration

Delete the paragraph and replace with the following paragraph:

“Unless settled amicably, any Subcontractor dispute in respect of which the Main Contract DAB’s decision or Subcontract DAB’s decision (if any) has not become final and binding shall be finally settled by means of Arbitration. The Arbitration shall be conducted under the provision of the South African law as it applies to Arbitration (Act 42 of 1965).”

###### ANNEX A:	PARTICULARS OF THE MAIN CONTRACT

| PART A (Subcontract Sub-Clause 2.1) |  |  |
| --- | --- | --- |
| 1. | PARTIES |  |
|  | Name and address of Employer: | The South African National Roads Agency SOC Limited (SANRAL) 48 Tambotie Avenue Val De Grace Pretoria, 0184 |
|  | Legal form of Employer: | Company |
|  | Name and address of Engineer: | Compiler to insert |
|  | Legal form of Engineer: | Compiler to insert: Company, Partnership, Individual, Proprietorship |
|  | Name and address of Contractor: | Compiler to insert |
|  | Legal form of Contractor: | Compiler to insert: Company, Partnership, Individual, Proprietorship |
| 2. | MAIN CONTRACT COMMENCEMENT DATE |  |
|  | Main Contract Commencement Date: | Compiler to insert |
| 3. | TIME FOR COMPLETION |  |
|  | Times for Completion under the Main Contract |  |
|  | - Section Times for Completion: | Compiler to insert description and the Times for Completion of any Section of the Main Works pursuant to the Main Contract Sub-Clause 8.2 [Time for Completion] |
|  | - Time for Completion: | Compiler to insert Time for Completion of the Main Works pursuant to the Main Contract Sub-Clause 8.2 [Time for Completion] as well as approved Extention of Time of the Main Contract. |
|  | - Programme | Compiler to attach the latest programme and indicate a reference to the programme here |
| 4. | DESCRIPTION OF WORKS UNDER THE MAIN CONTRACT |  |
|  | - The Site is Located: | Compiler to insert description of location of the Site |
|  | - The Main Works Comprise: | Compiler to insert description of the Main Works |
| 5. | CONDITIONS OF THE MAIN CONTRACT |  |
|  | The Conditions of the Main Contract consist of the FIDIC Conditions of Contract for Construction for Building and Engineering Works Designed by the Employer, First Edition 1999, published by the International Federation of Consulting Engineers (FIDIC) together with the Particular Conditions of the Main Contract. The Appendix to Tender of the Main Contract and the Particular Conditions of the Main Contract is attached to this Annex A (Note to Compiler: The Appendix to Tender of the Main Contract and the Particular Conditions of the Main Contract MUST be attached to the Annex A of the successful Subcontractor’s Subcontract. See sub-clause 2.1 of FIDIC Conditions of Subcontract, 2011). |  |
| 6. | CONFIDENTIAL PARTS OF THE MAIN CONTRACT |  |
|  | The following parts of the Main Contract will be confidential between the Employer and the Contractor, and shall not be made available for inspection to the Subcontractor | C2.2 Pricing Schedule (Incorporating SBD3) C2.3 Summary of Pricing Schedule (Note to Compiler: Add to this list as required) |
| PART B (Subcontract Sub-Clause 2.2) |  |  |
|  | Exclusions | (Note to Compiler: List as required) |

###### ANNEX B:	SCOPE OF SUBCONTRACT WORKS AND SCHEDULES OF SUBCONTRACT DOCUMENTS

| 1. | Scope of Subcontract Works |  |
| --- | --- | --- |
|  | The Scope of Subcontract Works is contained in (or referred to in): | Part C3: Scope of Works Part C4: Site Information |
| 2. | Schedule of Technical documents for the Subcontract Works |  |
|  | The Technical documents for the Subcontract Works are contained in (or referred to in): | Part C3: Scope of Works Part C4: Site Information |

###### ANNEX C:	TAKING-OVER BY THE CONTRACTOR AND SUBCONTRACT BILL OF QUANTITIES

| 1. | Taking-Over by the Contractor (Sub-Clause 10.3) |  |
| --- | --- | --- |
|  | Provided completion of the Subcontract Works has been achieved in accordance with sub-clause 10.1 [Completion of Subcontract Works], the Subcontractor may apply by notice to the Contractor for the Contractor to take-over the Subcontract Works. The Contractor shall, within 7 days after receiving the Subcontractor’s application: - Issue a certificate.to the Subcontractor verifying the taking-over of the Subcontract Works, and stating the date of such taking-over, or - Reject the application, giving reasons and specifying the work required to be done by the Subcontractor to enable a taking-over certificate to be issued. The Subcontractor shall then complete this work before issuing a further notice under this sub-clause. If the Contractor fails to either issue a taking-over certificate or to reject the Subcontractor’s application within the period of 7 days, and if the Subcontract Works have been completed in accordance with the Subcontract, these works shall be deemed to have been taken-over on the last day of the period of 7 days. |  |
| 2. | Subcontract Bill of Quantities and/or schedule of prices (if any) (Sub-Clause 1.1.18) |  |
|  | The subcontract Bill of quantities is contained in Part C2 Pricing Data |  |

###### ANNEX D:	EQUIPMENT, TEMPORARY WORKS, FACILITIES, AND FREE-ISSUE MATERIALS TO BE PROVIDED BY THE CONTRACTOR (Sub-Clauses 4.1, 7.1 & 7.2)

| 1. | Equipment, Temporary Works, Facilities, and Free-issue Materials |  |
| --- | --- | --- |
|  | The Equipment, Temporary Works, Facilities and Free-Issue Materials listed shall be provided by the Contractor to the Subcontractor | (Note to Compiler: List as applicable) |
| 2. | Common Use of Facilities |  |
|  | Access to the work areas within the Site | (Note to Compiler: Indicate details and arrangements, and terms and conditions, of the Subcontractor’s access to the work areas, shared work areas, and requirement for allowance of other contractors within the work areas and use of each facility, where applicable) |
|  | Transport of local labour to work areas within the Site | (Note to Compiler: Indicate details and arrangements, and terms and conditions, for the transport of local labour to work areas within the site. Also indicate arrangement (if any) for transport of local labour to site) |
|  | Common camp facilities, including messing, medical, security, safety, recreation, laundry, house-keeping, electricity, water, sewage, waste disposal, and other general camp services | (Note to Compiler: Indicate details and arrangements, and terms and conditions, of the Subcontractor’s use of each facility, where applicable) |
| 3. | Use of Temporary Works, Equipment and Facilities by Subcontractor at no charge |  |
|  | Temporary Works (including Traffic Accommodation) | (Note to Compiler: Indicate details and arrangements, and terms and conditions, of the Subcontractor’s use of each item. If any item is to be provided for the exclusive use of the Subcontractor, this should be expressly stated) |
|  | Contractor’s Equipment and vehicles | (Note to Compiler: Indicate details and arrangements, and terms and conditions, of the Subcontractor’s use of each item. If any item is to be provided for the exclusive use of the Subcontractor, this should be expressly stated) |
|  | Facilities | (Note to Compiler: Indicate details and arrangements, and terms and conditions, of the Subcontractor’s use of each item. If any item is to be provided for the exclusive use of the Subcontractor, this should be expressly stated) |
| 4. | Use of Temporary Works, Equipment and Facilities by Subcontractor to be charged |  |
|  | Temporary Works (including Traffic Accommodation) | (Note to Compiler: Indicate details and arrangements, and terms and conditions, of the Subcontractor’s use of each item. If any item is to be provided for the exclusive use of the Subcontractor, this should be expressly stated) |
|  | Contractor’s Equipment and vehicles | (Note to Compiler: Indicate details and arrangements, and terms and conditions, of the Subcontractor’s use of each item. If any item is to be provided for the exclusive use of the Subcontractor, this should be expressly stated) |
|  | Facilities | (Note to Compiler: Indicate details and arrangements, and terms and conditions, of the Subcontractor’s use of each item. If any item is to be provided for the exclusive use of the Subcontractor, this should be expressly stated) |

| 5. | Free-Issue Materials |  |
| --- | --- | --- |
|  | Material 1 | (Note to Compiler: Indicate details and arrangements, the place(s) for delivery, and terms and conditions, of the supply of each item of material) |
|  | Material 2 |  |
|  | Material 3 |  |

###### ANNEX E:	INSURANCES (Sub-Clauses 18.1 & 18.2)

| 1. | Insurances to be effected and maintained by the Subcontractor |  |
| --- | --- | --- |
|  | The Insurances listed shall be effected and maintained by the Subcontractor | The Subcontractor is to provide his own insurance for his personnel, public liability and relevant plant and equipment. The subcontractor will be covered under the main contract for the Subcontract Works. The subcontractor will also be liable for payment of applicable excess and any additional cost arising from each claim (Note to Compiler: Indicate details of any other required insurances to be effected and maintained by the Subcontractor) |
| 2. | Insurances to be effected and maintained by the Contractor under the Main Contract that relate to the Subcontract Works |  |
|  | The Insurances listed shall be effected and maintained by the Contractor | The Contractor is to provide insurance for the Works. (Note to Compiler: Indicate details of any other insurances to be effected and maintained by the Contractor) |
| 3. | Insurances to be effected and maintained by the Employer under the Main Contract that relate to the Subcontract Works |  |
|  | The Insurances listed shall be effected and maintained by the Employer | The Employer will not effect or maintain any insurance that relate to the Subcontract Works. |

###### ANNEX F:	SUBCONTRACT PROGRAMME (Sub-Clause 8.3)

| A. | Initial Subcontract Programme |  |
| --- | --- | --- |
|  | Form and detail of the programme | The form and detail of the programme for the execution of the Subcontract Works shall fully comply with the programming and reporting requirements of the Main Contract and, in any case, shall: (Note to Compiler: Amend list if required to Indicate additional requirements or list the minimum requirements of the programme) - be prepared in sufficient detail to ensure the adequate planning, execution and monitoring of the Subcontract Works; - use the programming software specified in the Main Contract; - take due account of the Subcontract Time for Completion; - identify all relevant activities including those that relate to design, manufacture, procurement, and on Site works; - show earliest and latest start and finish dates for each work activity; - identify when and what information, drawings, materials, equipment, facilities, and/or temporary works are required from the Contractor, the Engineer and/or the Employer; - identify when and what approvals, consents, and/or certificates are required from the Contractor, the Engineer and/or the Employer; - identify the date(s) and location(s) within the Site that access is required to execute (parts of) the Subcontract Works; - identify holiday periods; - identify key delivery dates of Subcontract Plant and materials’ - identify dates by which work will be ready for inspection and/or testing; - logically link all activities; - identify where the critical path(s) lie(s); - identify all float; - include sufficient flexibility in order to make adequate adjustments to allow for interfacing the Subcontractor’s activities with the Contractor and other contractors working on the Site; - allow for weather conditions which are at the Subcontractor’s risk (if any), and other Subcontractor’s time risks; and - be supported by a schedule giving sufficient details of the Subcontractor’s resource requirements in terms of manpower, work rates, items of plant, equipment and materials for each work activity to justify the activity duration shown in the programme. |
|  | Acceptance | The Contractor shall within 14 days of receiving the initial programme respond by either stating that this initial programme complies with the Subcontract, in which case it shall become the Subcontract Programme; or rejecting this initial programme, giving sufficiently detailed and cogent reasons to enable the Subcontractor to revise the initial programme in a timely manner. If the Subcontractor receives no response from the Contractor within 14 days of submitting the initial programme, it shall become the Subcontract Programme. If the Contractor responds stating that the initial programme fails (to the extent stated) to comply with the Subcontract, the Subcontractor shall submit a revised initial programme within 7 days of receipt of the Contractor’s response, taking due account of the reasons given by the Contractor. The Contractor shall within 7 days of receiving this revised initial programme, respond by either stating that it complies with the Subcontract in which case it shall become the Subcontract Programme; or stating that the initial programme fails (to the extent stated) to comply with the Subcontract, giving sufficiently detailed and cogent reasons to enable the Subcontractor to further revise the initial programme in a timely manner. |
| B. | Updating the Subcontract Programme |  |
|  | Updating | The Subcontract programme shall be updated and submitted to the Contractor no later than 28 days from the date that the Subcontractor’s initial programme became the Subcontract Programme and, in any case, within 7 days of the occurrence of any of the following: (Note to Compiler: Amend List if required to list instances when an updated programme is required) - The Subcontractor changing his method(s) and/or sequencing of work and/or duration of activities and/or allocation of resources; - Any delay event experienced by the Subcontractor in his execution of the Subcontract Works of whatsoever cause which impacts the critical path or, if there is more than one critical path, any of the critical paths; - Notification from the Contractor of any delay event which has occurred, or specific probable future events or circumstances, which may adversely affect the Subcontractor’s work, increase the Subcontract Price or delay the execution of the Subcontract Works; - The grant by the Contractor of an extension of the Subcontract Time for Completion; - Receipt of a Contractor’s Instruction regarding the programming and/or sequencing of the Subcontract Works; and - Receipt of notification from the Contractor that the actual progress of the Subcontract Works is too slow to complete within the Subcontract Time for Completion and/or does not conform to the Subcontract Programme. The updated programme shall show modifications to the Subcontract Programme necessary to ensure completion of the Subcontract Works within the Subcontract Time for Completion. |
|  | Acceptance | The Contractor shall within 7 days of receiving the updated programme respond by either stating that it complies with the Subcontract, in which case it shall become the Subcontract Programme; or stating that it fails (to the extent stated) to comply with the Subcontract, giving sufficiently detailed and cogent reasons to enable the Subcontractor to revise it in a timely manner. If the Subcontractor receives no response from the Contractor within 7 days of submitting the updated programme, it shall become the Subcontract Programme. If the Contractor responds stating that the updated programme fails (to the extent stated) to comply with the Subcontract, the Subcontractor shall submit a revised updated programme within 7 days of receipt of the Contractor’s response, taking due account of the reasons given by the Contractor. The Contractor shall within 7 days of receiving this revised updated programme, respond by either stating that it complies with the Subcontract, in which case it shall become the Subcontract Programme; or stating that it fails (to the extent stated) to comply with the Subcontract, giving sufficiently detailed and cogent reasons to enable the Subcontractor to further revise the updated programme in a timely manner. |
|  | Subcontract duration | Thereafter, for the duration of the Subcontract Works, the Subcontractor shall update the programme and each updated programme shall be subject to the requirements of this Annex. The Subcontractor shall not delay any work whilst awaiting a response from the Contractor in respect of any updated or revised updated Subcontract programme. Provided that any response by the Contractor in respect of any programme submitted by the Subcontractor that relates to the Subcontract Works shall not be taken as: - Conferring any right on the Subcontractor other than those set out in the Subcontract, or - Any waiver of the Contractor’s rights or the Subcontractor’s obligations under the Subcontract. |

##### C1.2.2	APPENDIX TO TENDER: CONTRACT DATA - INFORMATION PROVIDED BY THE CONTRACTOR

      - This form is the equivalent of the Appendix to the Subcontractor’s Offer as defined in Sub-Clause 1.1.3 of the FIDIC Conditions of Subcontract, 2011.

      - Subcontract clause numbers (SCl No.) refer to the FIDIC Conditions of Subcontract, 2011. The prefix PCC refers to an amendment or addition in the Particular Conditions of Contract.

| SCl No | Item | Data |
| --- | --- | --- |
| 1.1.4 | Contractor | means Compiler to insert name of the Contractor’s firm Physical address: Compiler to insert Tel: Cell: Email: |
| 1.1.7 | Contractor’s Subcontract Representative | ………………….. (Compiler to insert details of the Contracts Manager or his delegated representative, the approved Construction Manager (Contractor’s Representative) |
| (Note to Compiler: complete the following if there are Subcontract Sections) 1.1.28 | Subcontract section: ……… Subcontract section ………. Subcontract section ………. | Time for Completion ………. Time for Completion ………. Time for Completion ………. |
| 1.1.31 | Subcontract Time for Completion | ……… months from the Commencement Date (Compiler to insert number of days or months) |
| 1.4 | Subcontract Communications | Communications between the parties shall be from the Subcontractor through to the Contractor. The addresses for communication with the Contractor shall be: Contractor: Physical address: (Note to Compiler: Insert relevant physical address) Postal address: (Note to Compiler: Insert relevant postal address) Tel: Cell: Email: |
| 4.2 | Subcontract Performance Security | Not applicable for Targeted Enterprise Subcontractors |
| PCC 6.5 | Rates of Wages and Conditions of Labour | The Subcontractor shall be registered with the Bargaining Council for the Civil Engineering Industry (Government Notice R.490 – Part III in Government Gazette No. 37750) and rates for Wages and Conditions of Labour agreed by the Bargaining Council for the Civil Engineering Industry shall apply to the Subcontractor except where a specific industry publishes its own Wage Rates and Conditions of Labour. (Note to Compiler: In cases where the works package falls under a specific industry (e.g. Forestry) that publishes its own wage rates and Conditions of Labour, then delete the previous sentence and insert the specific industry wage rates and Conditions of Labour) |
| PCC 6.6 | Working Hours | Special non-working days are: a) All designated public holidays (including all foreseeable statutory declared election days) (b) The annual shut-down period between December and January (c) Day before Easter Weekend (d) Day of State school term closure and day prior to State school term start (e) Other non-working days and restricted working hours specified in section B1200 in the Main Contract as follows: i) (Note to Compiler: Add the restrictions from B1200 of the Main Contract) (f) Sundays (g) Between sunset and sunrise (Note to Compiler: amend the above to correspond with A6.5 of the Main Contract) |
| PCC 8.1 | Subcontract Commencement Date | As stated in Clause C1.1.2 Form of Acceptance. |
| PCC 8.1 | Period in which the Subcontract Work is to commence | Within 14 days of the Subcontract Commencement Date |
| PCC 8.7 | Delay Damages | R........ /day (Note to Compiler: Insert an amount per day that can not exceed either the Main Contract Daily Delay Damage amount or the Subcontract Maximum amount of Delay Damages) |
| PCC 8.7 | Maximum amount of Delay Damages | Up to 10% of the Accepted Subcontract Price |
| PCC 11.2 | Subcontract Defects Notification Period | (Note to Compiler: Insert an appropriate period for the type of work and risk of defects over time but not exceeding 12 months, utilising the following guide: 12 months – For High risk and high value subcontracts 6 months – As a general norm 3 months – For CE1, 2 and and 3s) ____ months. |
| 13.5 | Subcontract Adjustments for Changes in Cost | Statistical Releases published by Statistics South Africa |
|  | TABLE OF ADJUSTMENT DATA. Coefficient; Resource; Definition; Publication; Table. x = 0,15; Fixed. a = ……; Labour (L); “Labour Index” shall be the price index for “Consumer Price Index” for the …………. (Note to Compiler: Insert Province) Province; P0141; A. b = ……; Equipment (E); “Equipment Index” shall be the price index for “Plant and Equipment”; P0151.1; 4. c = ……; Material (M); “Materials Index” shall be the price index for the “Civil Engineering Material” product …….., (Note to Compiler: Insert most appropriate product, for type of work i.e.: “Roads, General (excl. Bitumen)” for projects that are both road and structures intensive, “Roads, Refurbishment (Excl. Bitumen)” for projects that are road intensive, “Structures (Excl. Bitumen)” for all structures intensive projects); P0151.1; 6. d = ……; Fuel (F); “Fuel Index” and shall be the price index for “Coal and Petroleum Products”, for “Diesel”; P0142.1; 1. “Ln”, “En””, “Mn” and “Fn” are the current cost indices for period “n”, each of which is applicable to the relevant tabulated cost element on a date 49 days prior to the last day of the period to which the interim Subcontract Payment or final Subcontract Payment relates. “Lo”, “Eo”, “Mo” and “Fo” are the base cost indices, each of which is applicable to the relevant tabulated cost element on the Subcontract Base Date (the date 28 days prior to the latest date for submission of the Subcontractor’s Offer).. (Note to Compiler: The coefficients a, b, c, and d is to be the same as the coefficients of the Main Contract – any proposed changes to be confirmed with the Employer). |
| 14.2 | Total Subcontract Advance Payment | ………..% of Accepted Subcontract Price (Note to Compiler: Indicate percentage if applicable else indicate 0%) |
| 14.2 | Number, Timing and proportions of instalments of advance payment | (Note to Compiler: Indicate details of advance payment installments if applicable else indicate Not Applicable) |
| PCC 14.6 | Percentage of Retention | 5% of the Value of Completed Work |
| PCC 14.6 | Limit of Retention Money | 5% of the Subcontract Price |
| 14.11 | Subcontract Currencies of Payment | South African Rand (ZAR) |
| PCC 20.5 | Appointment of the Subcontract DAB | Where a Main Contract DAB is appointed under the Main Contract, the Subcontract DAB shall comprise of the same members of the Main Contract DAB. Where a Main Contract DAB is not appointed under the Main Contract, the Subcontract DAB shall comprise of 1 (one) member only. |

##### C1.2.3	APPENDIX TO TENDER: CONTRACT DATA – INFORMATION PROVIDED BY THE TENDERER

Note to Tenderer:

This form is the equivalent of the Appendix to the Subcontractor’s Offer as defined in Sub-Clause 1.1.3 of the FIDIC Conditions of Subcontract, 2011

            - FIDIC CONDITIONS OF SUBCONTRACT

1.a	Clause 1.1.34: Subcontractor

The subcontractor is:

1.b	Clause 1.4: Subcontract Communications

Communications to the Subcontractor shall be delivered, sent or transmitted to the following:

Physical address:

Telephone:

Facsimile:

E-mail:

1.c	Clause 1.1.39: Subcontractor’s Representatives

The authorized and designated representative of the Subcontractor is:

Name:

SIGNED BY TENDERER:

Part C2:	PRICING DATA

PART C2	PRICING DATA

TABLE OF CONTENTS	PAGE

C2.1	PRICING INSTRUCTIONS	C2.3

C2.2	PRICING SCHEDULE (INCORPORATING SBD3) (provided on compact 
disc)	C2.5

C2.3	SUMMARY OF PRICING SCHEDULE 	C2.6

C2.1	PRICING INSTRUCTIONS

C2.1.1 	Measurement and payment shall be in accordance with the relevant provisions of the Standard Specifications as amended in the Scope of Works.

C2.1.2	The units of measurement described in the Bill of Quantities are metric units. Abbreviations used in the Bill of Quantities are detailed in the Standard Specifications.

C2.1.3	For the purposes of the Bill of Quantities, the following words shall have the meanings hereby assigned to them.

Unit:	The unit of measurement for each item of work as defined in the Standard Specifications or the Scope of Works.

Quantity:	The number of units of work for each item.

Rate:	The payment per unit of work for which the Subcontractor tenders to do the work.

Amount:	The product of the quantity and the rate tendered for an item.

Lump Sum:	An amount tendered for an item, the extent of which is described in the Bill of Quantities, the Scope of Work or elsewhere, but of which the quantity of work is not measured in units.

Prime cost:	Is a specific type of Provisional Sum where payment is made on the production of invoices showing the cost price of the implementation or installation of the service required. Services rendered in this manner carry a mark-up for which a rate is offered at tender stage to cover all the Subcontractor’s handling, supervision and liability costs in providing the item or services. Any percentage adjustment or lump sum mark-up against the Prime cost for handling fee, profits, etc. shall not be negative .

Provisional Sum:	A sum (if any) which is specified in the contract as a provisional sum, for the execution of any part of the works or the supply of plant, materials or services under Sub-Clause 13.5 (Provisional sums) of the Main Contract. Any percentage adjustment or lump sum mark-up against the Provisional Sum for handling fee, profits, etc. shall not be negative

C2.1.4 	Unless otherwise stated, items are measured net in accordance with the drawings, and no allowance is made for waste.

C2.1.5	It will be assumed that prices included in the Bill of Quantities are based on Acts, Ordinances, Regulations, By-laws, International Standards and National Standards that were published 28 days before the closing date for tenders. (Refer to www.stanza.org,za or www.iso.org for information standards).

C2.1.6	The prices and rates in the Bill of Quantities are fully inclusive prices for the work described under the items, and include all duties, taxes (except Value Added Tax) and other levies payable by the Contractor. Such prices and rates cover all costs and expenses that may be required in and for the execution of the work described in accordance with the provisions of the Scope of Work, and shall cover the cost of all general risks, liabilities and obligations set forth or implied, as well as overhead charges and profit. These prices will be used as a basis for assessment of payment for additional work that may have to be carried out.

C2.1.7	Where the Scope of Work requires detailed drawings and designs or other information to be provided, all costs associated therewith are deemed to have been provided for and included in the unit rates and sum amount tendered such items.

C2.1.8	An item against which no price is entered will be considered to be covered by the other prices or rates in the Pricing Schedule. A single lump sum will apply should a number of items be grouped together for pricing purposes.

C2.1.9	The quantities set out in the Bill of Quantities are approximate and do not necessarily represent the actual amount of work to be done. The quantities of work accepted and certified for payment will be used for determining payments due and not the quantities given in the Bill of Quantities.

C2.1.10	Reasonable compensation will be received where no pay item appears in the Bill of Quantities in respect of work required in terms of the Contract and which is not covered in any other pay item.

C2.1.11	The short descriptions of the items of payment given in the Bill of Quantities are only for the purposes of identifying the items. More details regarding the extent of the work entailed under each item appear in the Scope of Work.

C2.1.12	The item numbers appearing in the Bill of Quantities refer to the corresponding item numbers in the Standard Specifications.

C2.1.13	If the pricing schedule is provided electronically in excel format and in hard copy or pdf (Note to Compiler: Remove as applicable), in the event of any discrepancy between the signed printed hard copy or pdf copy, and the electronically submitted copy in excel, the tender rates in the signed hard copy or pdf copy will govern (Note to Compiler: Remove as applicable). The item numbers and description of the hard copy or pdf document will govern. For all addenda issued relating to the pricing schedule, the item numbers, description and quantities of the issued document will govern.

C2.2	PRICING SCHEDULE (INCORPORATING SBD3) (provided on compact disc)

(Note to Compiler: Insert the relevant Schedule of Quantities for the type of Work Package that is to be sub-let according to the Main contract.

Use the Main Contract Pricing Schedule as a Master list to compile the Pricing Schedule, with individual line items listed in the subcontract to be reflected in the Main contract pricing schedule) (Note to Compiler: Consult with the relevant Engineer)

C2.3	SUMMARY OF PRICING SCHEDULE

SUBCONTRACT NO.

FOR

UNDER CONTRACT SANRAL

FOR THE

(Note to Compiler: Remove or add as applicable)

| SCHEDULE A: ROADWORKS (from page …………) | R ……………………………………………. |
| --- | --- |
| SCHEDULE B: STRUCTURES (from page …………) | R ……………………………………………. |
| SUBTOTAL | R ……………………………………………. |
| VALUE ADDED TAX @ 15% of Subtotal | R ……………………………………………. |
| TOTAL CARRIED TO C.1.1.1: FORM OF OFFER | R ……………………………………………. |

Part C3:	SCOPE OF WORKS

PART C3	SCOPE OF WORKS

TABLE OF CONTENTS	PAGE

C3.1	GENERAL SPECIFICATION	C3.3

C3.1.1	SCOPE	C3.3

C3.1.2	DESCRIPTION OF THE WORKS	C3.3

C3.1.3	DRAWINGS	C3.4

C3.1.4	CONSTRUCTION IN CONFINED AREAS	C3.5

C3.1.5	SUBCONTRACTOR’S CAMP SITE	C3.5

C3.1.6	ADDITIONAL REQUIREMENTS FOR CONSTRUCTION ACTIVITIES	C3.5

C3.1.7	ALLOWANCE FOR OTHER CONTRACTORS AND ACCOMMODATION OF OTHER CONTRACTS	C3.6

C3.1.8	PROGRAMME, RESTRICTION AND COMPLETION OF ACTIVITIES	C3.6

C3.1.9	 OCCUPATIONAL HEALTH AND SAFETY	C3.7

C3.1.10	 CHANGES TO SCOPE OF WORK	C3.7

C3.1.11	INTEGRATED TRANSPORTATION INFORMATION SYSTEM (FOR INFORMATION PURPOSES)	C3.7

C3.1.12	CONTRACTOR SUPPORT OF TARGETED ENTERPRISES	C3.7

C3.1.13	TRAINING, COACHING, GUIDANCE, MENTORING and assistance	C3.9

C3.2	STANDARD SPECIFICATIONS	C3.12

C3.3.	PARTICULAR PROJECT SPECIFICATION AMENDING THE STANDARD SPECIFICATIONS	C3.12

C3.3.1	COLTO SERIES 1000: GENERAL	C3.13

SECTION b1100:	DEFINITIONS AND TERMS	C3.13

PART C3:	SCOPE OF WORKS

(Note to Compiler: The below is the minimum requirements to be contained in the document. The contractor to Insert the relevant information to describe the Scope of work for the type of Work Package that is to be sub-let)

C3.1	GENERAL SPECIFICATION

C3.1.1	SCOPE

This section provides the description of the project and the general requirements for executing the subcontract work. The work required is the (Note to Compiler: refer only to work applicable to the subcontract) of the national road (number) Section (number) (from km to km). The total distance is approximately (length) km. (Note to Compiler: refer only to the portion of the site applicable to the subcontract)

It is a requirement of the Main Contract for the Contractor to facilitate the Subcontractor development of targeted enterprises as a contract participation goal by means of subcontracting some of the scheduled work section(s) to targeted enterprises as subcontractors.

C3.1.2	DESCRIPTION OF THE WORKS

C3.1.2.1		Description of site

(a)	Location of site (Note to Compiler: refer only to the portion of the site applicable to the subcontract)

The general locality of the site is indicated on the locality plan bound in the back of this volume.

The term “Site” as defined in the Main Contract in terms of Clause 1.1.6.7 of the FIDIC Conditions of Contract for Construction, 1999 and is bound by the limits of construction as shown in the drawings or the title of the project and extends to also include the following:

- Areas outside the construction zone areas where accommodation of traffic is placed.

- All borrowpits defined in the applications approved by the relevant Department of Minerals and Energy.

- All haul roads constructed by the Contractor for purposes of access.

- Any non-adjacent sites specified in the contract documentation.

- The Contractor’s and his subcontractors’ camp sites

The portion of the site applicable to this subcontract will comprise:

- The section of National Route (number) Section (number) (from km to km). The total distance is approximately (length) km. (Note to Compiler: add additional descriptions for relevant subcontract e.g. on-ramps and off-ramps forming part of an interchange, as well as overpasses and underpasses within the national road reserve up to the limits of the SANRAL’s responsibility whether or not it has direct access off the national road. Excluded are provincial, municipal and private cross roads, which are not accessible from the road reserve of the national road, but the overpass and underpass structures are part of the “Site”, The “Site” will also include all road signs within 500 metres of an intersection or interchange, which form part of the road signs layout for the national road. The “Site” will also include land not provided by the SANRAL, where equipment and/or materials for use in the permanent works of the contract can be stored and/or stockpiled with the provision that the land selected for this purpose be approved by the Engineer. The Contractor must make their own arrangements for the use of such land and must obtain written approval from the owner(s) concerned)

(b)	Access to the site

Vehicular Access to the site shall be from established interchanges, intersections and approved accesses.

(Note to Compiler: In the event that the Contractor will make any part of the site available exclusively to the Subcontractor, then those parts of the site and the periods of exclusive access to be detailed here as per amended Conditions of Contract 3.2

## C3.1.2.2		Nature of Subcontract work

The description of the project contained in this section is merely an outline of the Subcontract works and shall not limit the work to be carried out by the Subcontractor under this Subcontract. Approximate quantities of each type of work to be carried out in accordance with the Subcontract documents are listed in the Bill of Quantities bound in this volume.

The nature of work to be carried out under this Subcontract includes: (Note to Compiler: Add/ Remove as is relevant for the Work Package)

- Erection and maintenance of the subcontractor’s camp site

- Clearing and grubbing.

- Removal of trees

- Provision of traffic control facilities

- Management of traffic control facilities and traffic safety as part of the accommodation of traffic

- Construction and clearing of drains.

- Installation of prefabricated culverts including inlet and outlet structures.

- Concrete channelling and concrete linings for open drains.

- Construction of concrete paving, kerbs and channels

- Construction of small concrete and other structures.

- Construction of concrete walkways

- Pitching, stonework and protection against erosion.

- Construction of gabions.

- Patching and repairing edge breaks

- Erection of guardrails.

- Landscaping.

- Fencing

- Road signs

- Road markings

- Finishing the road and road reserve.

- Site Security Services.

- Haulage of Materials

- Supply of plant

- Supply of fuel

- Construction of concrete pavements

- Laying of asphalt using asphalt pavers

- Structural concrete such as culvert and bridges

- Crushing of materials

- Precast manufacture

- Batch plant erection and operations

- Earthworks, Layerworks construction

- Structural steel fabrication, erection

C3.1.3	DRAWINGS

The drawings issued in electronic format on a CD as part of the tender documents, shall be used for tender purposes only.

The Subcontractor will be issued with the contract drawings in electronic format on a CD. Any prints which the Subcontractor may require shall be at own cost.

Any information in the possession of the Subcontractor, which the Engineer requires to record as-built information, shall be supplied to the Engineer via the Contractor, before a Taking-Over Certificate will be issued.

Only figured dimensions shall be used and drawings shall not be scaled unless so instructed by the Engineer. The Engineer will supply all figured dimensions omitted from the drawings.

C3.1.4	CONSTRUCTION IN CONFINED AREAS

It may be necessary for the Subcontractor to work within confined areas. Except where provided for in the specifications, no additional payment will be made for work done in such confined areas. In certain instances, the width of the work to be undertaken may decrease to zero and the working space may be confined. The work method in such confined areas will be determined by the Subcontractor’s constructional equipment. The Contractor will provide assistance as required.

However, the Subcontractor must note that measurement and payment will only be made in accordance with the authorised dimensions, irrespective of the method used for achieving these dimensions and that the tendered rates and amounts shall include full compensation for all special equipment and construction methods and for all difficulties encountered when working in confined areas and narrow widths, and at or around obstructions, and that no extra payment will be made nor will any claim for additional payment be considered in such cases.

C3.1.5	SUBCONTRACTOR’S CAMP SITE

The Subcontractor shall provide a suitable site for his camp.  However, the Contractor will provide shared facilities as detailed in Annex D of the Contract Data of the Conditions of Subcontract.

C3.1.6	ADDITIONAL REQUIREMENTS FOR CONSTRUCTION ACTIVITIES

In addition to the requirements specified in the Standard Specifications, the Subcontractor shall adhere to the following requirements.

(Note to Compiler: Only add/remove items listed as is relevant to the Work Package)

C3.1.6.1		Accommodation of traffic

The Contractor will provide Traffic Accommodation as detailed in Annex D of the Contract Data of the Conditions of Subcontract .

C3.1.6.2		Environmental requirements

Trees and shrubs established in landscaped areas of interchanges and in the road reserve may under no circumstances be disturbed without specific instruction from the Contractor for their removal. Trees and shrubs inadvertently destroyed by the Subcontractor shall be replaced with the equivalent at the Subcontractor’s own cost.

Disposal of any bituminous-based material shall only be at an approved location and by means of an approved method, arranged beforehand with the Contractor.  Bituminous binders shall not be disposed of on the Site but shall be returned to the supplier for disposal.

C3.1.6.3		Dayworks

Sub-clause 13.6 of the FIDIC Conditions of Subcontract for Construction, 2011, refers.

The Subcontractor shall tender the rates applicable to daywork, as provided for in the Bill of Quantities. These rates will be taken into account in the adjudication of tenders.

The tendered rates shall be considered to include full compensation for the work to be performed, including supervision of labour, all plant operators and other operating costs, overheads and profit. Hourly rates for transport and equipment shall apply to the actual number of hours for which the vehicles or equipment are required for a specific item of work, including travelling time if applicable.

The Contractor on behalf of his Subcontractors, shall maintain a hard cover duplicate book on site for the purposes of recording daywork. The Contractor shall record the total time claimed under each relevant item of the Bill of Quantities and the applicable instruction of the Engineer and shall ensure that the total times claimed are agreed and signed daily by the Engineer’s representative on site.

The Subcontractor shall not claim daywork for any work for which an applicable rate has been tendered or agreed to in writing by the Engineer.

The cost of materials used and paid for by the Contractor or his Subcontractors, as authorised by the Engineer, shall be reimbursed at net cost, exclusive of Value Added Tax, plus the percentage as tendered for the Contractor's overhead charges and profit.

In the event where no allowance has been made for a specific item in the Bill of Quantities, the Engineer may order daywork according to sub-clause 13.6 of the FIDIC Conditions of Subcontract for Construction, 2011.

C3.1.7	ALLOWANCE FOR OTHER CONTRACTORS AND ACCOMMODATION OF OTHER CONTRACTS

Access to work areas and requirement for allowance of other contractors within the work areas is detailed in Annex D of the contract Data of the Conditions of Subcontract.

C3.1.8	PROGRAMME, RESTRICTION AND COMPLETION OF ACTIVITIES

This clause covers matters relating to the programme of work, restriction on certain activities, completion and responding time of specified activities, and compliance with the specifications.

C3.1.8.1		Programme

The Time for Completion of the Works is specified in the Appendix to the Subcontractor’s Offer.

The requirements of the Subcontract programme are specified in Annex F of the Contract Data of the Conditions of Subcontract.

The Contractor will determine the extent and frequency of the work to be executed in terms of the subcontract, as certain activities are dependent upon the climatic conditions encountered during the period of the subcontract and on progress of the Contractor or other subcontractors.

The frequency and commencement period of some of the key activities, as instructed by the Contractor are scheduled in Table C3.1.8/1.

(Note to Compiler: Only add/remove items listed as is relevant to the Work Package)

| TABLE C3.1.8/1: FREQUENCY AND COMMENCEMENT PERIOD OF ACTIVITIES |  |  |
| --- | --- | --- |
| Activity | Frequency | Start period |
| Linemarking | (state days and frequency) |  |

C3.1.8.2		Restriction on activities

Work activities will be restricted on days or hours indicated in clause 6.6 of the Contract Data of the Conditions of Subcontract .and the Subcontractor must allow for these restrictions in his programme and no extension of time or claims in this regard will be considered.

C3.1.8.3		Completion time of specified activities

(Note to Compiler: Amend as appropriate for type of subcontract e.g. Fix time or multiple establishments as is relevant to the Work Package)

Generally, the activities covered by this subcontract will be on a continuous basis. However, certain specified activities are considered to be of a non-continuous nature and multiple establishments will be required as instructed by the Contractor. (Note to Compiler: These establishments and the number thereof should be reflected in the pricing schedule)

C3.1.9		OCCUPATIONAL HEALTH AND SAFETY

In terms of the Construction Regulation 5(1)(b) of the Occupational Health and Safety Act, 1993 (Act No 85 of 1993), the South African National Roads Agency SOC Limited, as the Employer, is required to compile a specification on health and safety for the project. The Contractor will furnish the Subcontractor with the applicable specification and his Health and Safety plan.

The Method Statement shall be provided by the Contractor / The Method Statement for each activity shall be developed by the Subcontractor. (Note to Compiler: Amend as appropriate)

C3.1.10	INTEGRATED TRANSPORTATION INFORMATION SYSTEM (FOR INFORMATION PURPOSES)

The Employer has developed a comprehensive information management tool called ITIS (Integrated Transportation Information System) to address all facets of its strategic and tactical planning, design, construction and maintenance of the entire road network. This provides support for the management tasks of the Employer and to allow the personnel to make technical decisions more quickly and efficiently.

ITIS is an integrated approach to the sharing and inter-relating of technical performance information for the Employer and relies on people following procedures to populate system with data. ITIS currently consist of the following platforms:

- ITIS Web – Web enabled portal providing online access to various functions, workflows and reports.

- ITIS Desktop – Offline data capture tool enabling the capture of information offline, validation and then synchronisation of data with the ITIS database.

- ITIS Mobile – Application (Android 4.3 or later and IOS 6 or later) that allows the in-field capture of information using a smart phone or tablet (must have camera and GPS), validation and then synchronisation of data with the ITIS database.

The Employer then has several ITIS modules running on any of the above ITIS platforms which affect the Contractor, who will need to use these modules to perform certain procedures and to provide required information. The current modules applicable and their description are as follows:

- Project Information Module – employment and training data.

The Subcontractor will be required to supply relevant information to the Contractor to enable compliance with his obligations.

C3.1.12	CONTRACTOR SUPPORT OF TARGETED ENTERPRISES

The Contractor shall appoint a dedicated Targeted Enterprise Construction Manager (TE Construction Manager) whose sole responsibility shall be to assist with the execution of its responsibilities towards Targeted Enterprises and Target Groups. Amongst others, the TE Construction Manager shall facilitate the training, mentoring, development and support of Targeted Enterprises.

The TE Construction Manager shall have on his team one (1) TE Site Supervisor for every six (6) Targeted Enterprises which are in their respective construction phases and one (1) Senior TE Supervisor for every six (6) TE Site Supervisors.

The TE Construction Manager shall develop and establish a Targeted Enterprise Training, Development and Support Programme, which shall be approved by the Employer and Engineer and acknowledged by the Project Liaison committee (PLC) prior to implementation, and which shall adhere to Government’s and the Employer’s Transformation and Supply Chain Management Policies and principles.

- General Obligations

The Contractor shall, with the assistance of the TE Construction Manager, comply with the following obligations:

- Assist the Targeted Enterprises in instituting a quality assurance system;

- Provide adequate training, coaching, guidance, mentoring and any other identified and approved assistance to Targeted Enterprises;

- Provide support and any other identified and approved assistance to ensure that the Targeted Enterprises meet their obligations and commitments with respect to their subcontracts, and

- Ensure that the Contract Participation Goals (CPG) objectives are achieved.

- Subcontract Agreements

The Contractor, in liaison with the Employer and the Engineer, shall conclude the subcontract agreements and provide the necessary management support to the Targeted Enterprises. The subcontract agreements shall be in accordance with the provisions of amended sub-clause 4.4 of the Conditions of Contract and shall be consistent with the terms and conditions of the Main Contract.

A copy of each subcontract agreement shall be filed with the Engineer after confirming that it is in accordance with the provisions of the Main Contract and after it has been acknowledged by the PLC.

Note:

To protect Targeted Enterprises’ competitive advantage and/or tender strategy, only the main subcontract agreement shall be available to the PLC for acknowledgement and not the pricing structure and/or Schedule of Quantities.

- Quality of Work and Performance of Targeted Enterprises

The Contractor shall closely monitor and supervise all Targeted Enterprises and shall train, coach, guide, mentor and assist each Targeted Enterprise in all aspects of management, execution and completion of its subcontract. This shall typically include assistance with planning of the Works, sourcing and ordering of materials, labour relations, monthly measurements and invoicing procedures. The extent and level of such training, coaching, guidance, mentoring, and assistance to be provided by the Contractor shall commensurate with the level of subcontract applicable and shall be directed at enabling the Targeted Enterprise to achieve the successful execution and completion of its subcontract.

The Contractor shall give reasonable warning to the Targeted Enterprise when any contravention of the terms and conditions of the subcontract has occurred or appears likely to occur. The Contractor shall, whenever feasible, give the Targeted Enterprise reasonable opportunity to make good any such contravention, or to avoid such contravention, and shall render all reasonable assistance to the Targeted Enterprise in this regard.

- Dispute Avoidance and Resolution Procedures

When any disputes arise as provided for in the subcontract, the Contractor shall explain fully to the Targeted Enterprise that such actions are provided for in the subcontract. If such action is contemplated it shall be discussed with the Employer and the Engineer before any action is taken and communicated with the PLC as soon as action has been taken.

If the Targeted Enterprise, in the opinion of the Engineer, fails to comply with any of the criteria listed below, the Engineer shall issue a written warning to the Contractor, stating all the areas of non-compliance. A copy of the letter of warning shall be forwarded to the Employer. The criteria are as follows:

- Acceptable standard of work as set out in the specifications;

- Progress in accordance with the time constraints in the subcontract and the subcontract programme;

- Punctual and full payment of the workforce and suppliers;

- Site safety; and

- Accommodation of traffic.

The Targeted Enterprise shall have 21 days from the date of receipt of the letter of warning by the Contractor to address and rectify the issues raised by the Engineer, except for sub-clauses (iv) and (v) above, for which the reaction time shall be in accordance with the relevant specifications for those aspects of the Works, but which shall not be longer than 24 hours. Failure by the Targeted Enterprise to comply with a deadline, will be sufficient grounds for the Contractor to apply a penalty or terminate the subcontract provided that the Employer and the Engineer is satisfied that the Contractor has made every effort to correct the performance of the Targeted Enterprise.

C3.1.13	TRAINING, COACHING, GUIDANCE, MENTORING and assistance

- Purpose of the Training and Skills Development Programme(s)

Skills development forms an integral part of the Employer’s Transformation and Community Development Policies and hence, it is important to the Employer that Targeted Labour and Targeted Enterprises be equipped with skills that can be used to gain meaningful future employment and secure subcontracting opportunities.

It is, therefore, a requirement that the Contractor provide Training, Coaching, Guidance, Mentoring and assistance to the Targeted Labour and Targeted Enterprises, to ensure skills development within the Construction Industry.

The Contractor shall, in collaboration with the Employer and the Engineer, develop a Training and Skills Development Programme(s) which shall be managed by the Contractor’s TE Construction Manager.

- Skills Audit and Analysis

Prior to developing the Training and Skills Development Programme(s), the Contractor shall conduct a Skills Audit and Analysis of the Subcontractor’s employees to determine their levels of education, existing qualifications, and skills sets. The outcome of the Skills Audit and Analysis shall be used to develop a Training and Skills Development Programme(s) that will benefit both the employee and the Construction Industry at large.

Included in the Skills Audit and Analysis shall be a separate section, analysing the education, qualifications and skills sets of the Subcontractor by the Contractor to develop a Training and Skills Development Programme(s) that will develop and improve the ability of small business owners and their supervisory staff to better manage their enterprises.

- Developing the Training and Skills Development Programme(s)

The Employer shall be involved in the decision making and quality control pertaining to the development and implementation of the Training and Skills Development Programme(s).

The Employer has no service agreement or memorandum of understanding with any education and training quality assurance body and, therefore, does not function as the “Employer” as defined under any three-party-agreement between the Trainee, the Training Provider and the Employer.

However, the Employer requires similar outcomes to that of formal learnership programmes and the Contractor shall structure a Training and Skills Development Programme(s) in a manner that permits continued access to further learning and qualifications within a defined programme.

The complete Training and Skills Development Programme shall be approved by the Employer and Engineer and acknowledged by the PLC before any training commence.

- The Training Service Provider

While the Contractor’s TE Construction Manager will manage the Training, Development and Support Programme(s) and mentor subcontractors from a practical point of view, the Contractor shall subcontract a Training Service Provider to implement the theoretical training components of the Programme(s).

The Training Service Provider entity shall be accredited, and have in its employ Practitioners, Assessors and Moderators whom are registered, with the Construction Education Training Authority (CETA). Proof of accreditation and registration shall be current, valid and list the NQF levels and Unit Standards for which the entity and its staff are accredited.

- Training Programme: General Requirements

The Training and Skills Development Programme(s) shall consist of Learnerships that include multiple, but related Unit Standards which are (1) relevant to the Works to be constructed, (2) aimed at achieving the skills development objectives of the Programme, and (3) lead towards a formal qualification in the Construction Industry.

Learnerships shall include both the theoretical and practical components of each Unit Standard and shall be in accordance with the various laws and regulations contained in the South African Qualification Authority (SAQA) statutes.

- Training Programme: Requirements and Considerations

The Skills Audit and Analysis shall inform the Contractor of every employee’s Recognised Prior Learning (RPL) skills and competencies, which shall be taken into consideration in the development of the Training and Skills Development Programme(s) so that the RPL skills and competencies, together with the Training Programme Unit Standards offerings, will lead to a full Learnership outcome and hence a formal qualification.

It is recognised that the Training and Skills Development Programme(s) may consist of several Unit Standards but totalling insufficient credits for a full Learnership qualification. Nevertheless, the competencies and credits achieved in the Programme(s) shall contribute to a full Learnership by a later acquisition of the outstanding Unit Standards required for the full Learnership.

The Training and Skills Development Programme(s) shall be structured in a manner to prioritise those Unit Standards that will equip Trainees with the minimum skills required to become economically involved in the execution of the Works as soon as possible.

The Training Service Provider shall apply the SAQA Learnership criteria of which the basic elements are listed below to demonstrate the Employer’s requirements:

        - Minimum credits for qualification;

        - Fundamental Unit Standards and credit values;

        - Core Unit Standards and credit values;

        - Elective Units Standards and credit values;

        - Assumption that NQF Level 3 literacy, numeracy, and computer competencies exist;

        - RPL processes;

        - Exit level outcomes;

The above criteria are not exhaustive, and the Training Service Provider shall apply the systems and processes required by the relevant SAQA and other related legislation pertinent to training.

While structuring the Learnership offerings, the Training Service Provider shall distinguish between the levels of learning required. The bulk of the training shall focus on NQF Levels 4 and 3. NQF Level 5 training is not anticipated but may be suitable for qualifying staff of established small contractors. The qualification titles for the respective NQF Levels are:

- NQF Level 3 	National Certificate: Construction Roadworks.

- NQF Level 4	National Certificate: Supervision of Construction Processes

- NQF Level 4	National Certificate: Business Management

- NQF Level 5 	National Diploma: Management of Civil Engineering Construction Processes

It may be necessary to include additional Core Unit Standards, e.g. “Tendering” or “Entrepreneurship” as an additional Unit Standard for NQF Level 4, to achieve the Contract’s development objectives. The identification of any additional Unit Standards shall be discussed with the Engineer and shall not be implemented without prior approval.

Before qualifying, Trainees will be expected to demonstrate competence in a practical situation that integrates the assessment of all specific outcomes, for all Unit Standards in the Learnership Programme.

All training shall take place within normal working hours, or as agreed with the trainees.

- Selection of Trainees

To complete a Learnership successfully requires minimum literacy and numeracy competencies as defined by SAQA. The Training Service Provider shall utilise the Skills Audit and Analysis and conduct additional skills analysis to benchmark the literacy and numeracy levels of employees and subcontractors. This information shall guide the Training Service Provider in formulating the Learner selection methodology(ies) and process(es). The Training Service Provider shall make provision for (1) baseline assessments, e.g. conducting RPL enquiries and tests, and (2) a gap skills programme consisting of Fundamental Unit Standards, to facilitate the selection process.

Trainees identified as having already acquired some tertiary training, particularly in the field of Civil Engineering, may be suitable for a specialised Trainee programme or a higher NQF Level programme. The Training and Skills Development Programme(s) shall, therefore, make provision for Trainees with a variety of competency levels and shall make provision for different levels of training.

Note:

Where this section refers to the selection and training of Trainees, any person, employed by any national, provincial or local authority, being it full time or part time, is expressly excluded from being considered for this training.

C3.2	STANDARD SPECIFICATIONS

The Standard Specifications for Road and Bridge Works for State Road Authorities (1998 edition) prepared by the Committee of Land Transport Officials, (COLTO), as amended, shall apply to this subcontract.

C3.3.	PROJECT SPECIFICATION AMENDING THE STANDARD SPECIFICATIONS

In certain clauses the Standard Specifications allow a choice to be specified in the project specifications between alternative materials or methods of construction and for additional requirements to be specified to suit a particular contract. Details of such alternatives or additional requirements applicable to this subcontract are contained in this part of the project specifications. It also contains some additional specifications required for the subcontract.

The number of each clause and each payment item in this part of the project specifications consists of the prefix B followed by a number corresponding to the number of the relevant clause or payment item in the Standard Specifications. The number of a new series, new clause or a new payment item which does not form part of a series, clause or a payment item in the Standard Specifications and which is included here, is also prefixed by B followed by a new number. The new numbers follow on the last clause or item number used in the relevant section of the Standard Specifications.

The following sections contain the relevant project specific changes to the Standard Specifications.

(Note to Compiler: Add relevant project specification from main contract as applicable to the package as Section 1000, 2000, 3000 etc as relevant in the next pages. The compiler to obtain the Engineer’s approval if Main Contract project specifications or Standard Specifications are amended in this specification.)

C3.3.1	COLTO SERIES 1000: GENERAL

SECTION b1100:	DEFINITIONS AND TERMS

……………etc.

Part C4:	SITE INFORMATION

PART C4	SITE INFORMATION

TABLE OF CONTENTS	PAGE

C4.1	DESCRIPTION OF THE WORKS	C4.3

C4.2	DRAWINGS	C4.3

C4.3	CAMP ESTABLISHMENT, POWER SUPPLY AND OTHER SERVICES	C4.3

C4.4	CONSTRUCTION IN CONFINED AREAS	C4.3

C4.5	MANAGEMENT OF THE ENVIRONMENT	C4.3

C4.6	TRAFFIC	C4.3

C4.7	SMALL CONTRACTOR DEVELOPMENT, TRAINING AND COMMUNITY LIAISON	C4.3

C4.8	CLIMATE	C4.3

C4.9	REQUIREMENTS OF THE OCCUPATIONAL HEALTH AND SAFETY ACT AND REGULATIONS 2014	C4.3

C4.10	SAFETY PROCEDURES	C4.3

C4.11	OTHER INFORMATION	C4.3

C4.12	Appendices	C4.5

APPENDIX 1:	LOCALITY PLAN	C4.6

Information Only

All data and descriptions contained in this section of the Subcontract documents are given for information purposes only and cannot be interpreted as prescriptive or as an instruction despite the fact that the text may give the opposite perspective. If any conflict arises between the content of this section and other sections of the Subcontract documents, the latter take precedence.

(Note to Compiler – extract relevant information from the Main Contract Part C4 and include below to Provide as much scope of work info as possible for subcontractor to clearly understand the project when pricing. The below typical headings are given as example)

C4.1	DESCRIPTION OF THE WORKS

C4.2	DRAWINGS

C4.3	CAMP ESTABLISHMENT, POWER SUPPLY AND OTHER SERVICES

C4.4	CONSTRUCTION IN CONFINED AREAS

C4.5	MANAGEMENT OF THE ENVIRONMENT

C4.6	TRAFFIC

C4.7	SMALL CONTRACTOR DEVELOPMENT, TRAINING AND COMMUNITY LIAISON

C4.8	CLIMATE

C4.9	REQUIREMENTS OF THE OCCUPATIONAL HEALTH AND SAFETY ACT AND REGULATIONS 2014

C4.10	SAFETY PROCEDURES

C4.11	OTHER INFORMATION

C4.12	Appendices

Appendix 1:	Locality Plan

APPENDIX 1:	LOCALITY PLAN

Locality Plan of the Site: (Note to Compiler: Insert Locality Plan of the Site)

SUBCONTRACT NO. FOR UNDER CONTRACT SANRAL FOR THE

Part C5:	annexures

PART C5:	ANNEXURES

TABLE OF CONTENTS	PAGE

Annexure 1:	COPIES OF ALL ADDENDA ISSUED	C5.3

Annexure 2:	FORM A3.1 (SBD4) - COMPULSORY DECLARATION	C5.4

Annexure 3:	FORM A3.2 (SBD9) – certificate of independent tender	C5.5

Annexure 4:	FORM A3.3 (SBD8) – DECLARATION OF TENDERER’S PAST SUPPLY CHAIN MANAGEMENT PRACTICES	C5.6

Annexure 5:	FORM A3.4 – REGISTRATION ON NATIONAL TREASURY CENTRAL SUPPLIER DATABASE	C5.7

Annexure 6:	FORM A3.5 (SBD6.2) – DECLARATION CERTIFICATE FOR LOCAL PRODUCTION AND CONTENT FOR DESIGNATED SECTORS	C5.8

Annexure 7:	FORM A3.6 – LOCAL CONTENT DECLARATION: SUMMARY SCHEDULE (ANNEXURE C)	C5.9

Annexure 8:	FORM A6 (SBD2) – CERTIFICATE OF TAX COMPLIANCE	C5.10

Annexure 9:	FORM A10 – registration with cidb	C5.11

Annexure 10:	FORM A11 (SBD6.1) – TENDERER’S B-BBEE VERIFICATION 
CERTIFICATE	C5.12

Annexure 11:	CORRESPONDENCE RELATING TO PRICING DURING TENDER 
PERIOD	C5.13

Annexure 12:	letter of ACKNOWLEDGEMENT BY SUBCONTRACTOR	C5.14

Annexure 13:	letter of ACCEPTANCE BY CONTRACTOR	C5.15

Annexure 14:	subcontractor performance report	C5.16

Note to tenderer:

The Annexure will include completed returnable schedules and correspondence which form part of the subcontract.

Note to Compiler:

When preparing the contract document, include relevant correspondence and omit the “Note to Compiler”

Annexure 1:	COPIES OF ALL ADDENDA ISSUED

Annexure 2:	FORM A3.1 (SBD4) - COMPULSORY DECLARATION

Annexure 3:	FORM A3.2 (SBD9) – certificate of independent tender

Annexure 4:	FORM A3.3 (SBD8) – DECLARATION OF TENDERER’S PAST SUPPLY CHAIN MANAGEMENT PRACTICES

Annexure 5:	FORM A3.4 – REGISTRATION ON NATIONAL TREASURY CENTRAL SUPPLIER DATABASE

Annexure 6:	FORM A3.5 (SBD6.2) – DECLARATION CERTIFICATE FOR LOCAL PRODUCTION AND CONTENT FOR DESIGNATED SECTORS

Annexure 7:	FORM A3.6 – LOCAL CONTENT DECLARATION: SUMMARY SCHEDULE (ANNEXURE C)

Annexure 8:	FORM A6 (SBD2) – CERTIFICATE OF TAX COMPLIANCE

Annexure 9:	FORM A10 – registration with cidb

Annexure 10:	FORM A11 (SBD6.1) – TENDERER’S B-BBEE VERIFICATION CERTIFICATE

Annexure 11:	CORRESPONDENCE RELATING TO PRICING DURING TENDER PERIOD

Annexure 12:	letter of ACKNOWLEDGEMENT BY SUBCONTRACTOR

Annexure 13:	letter of ACCEPTANCE BY CONTRACTOR

Annexure 14:	subcontractor performance report

Note to Compiler: Attach the latest version of the Subcontractor Performance Report (EDMS DOC #4841504)

APPENDIX 9 – GENERAL REQUIREMENTS FOR COMMUNITY DEVELOPMENT PROJECTS

A1001	SCOPE OF WORK

The Contractor’s Scope of Work primarily entails the training and skills development of members of an identified Community, as well as Trainee Targeted Enterprises selected from this Community, who will become his Targeted Enterprise subcontractors and whom he shall manage and mentor during the construction phase.

The construction phase entails overseeing the construction of infrastructure, by Trainee Targeted Enterprises, that promotes the access, mobility and road safety of the identified Community, in relation to the National Road Network. The Contractor thus have primarily a training and construction management role.

To enhance the utilisation and development of Targeted Labour from the identified Community, care has been taken during the design of the Works to ensure that it can be constructed by means of labour enhanced construction methods (LECM) and the Contractor shall apply such labour enhanced methods.

A1002	DEFINITIONS

Unless inconsistent with the context, in these specifications, the following terms, words or expressions shall have the meanings hereby assigned to them:

    - Accreditation

The certification, for a set period, of a person, a body or an institution to have the capacity to fulfil a particular function within the quality assurance system set up by the SAQA.

    - Construction Education and Training Authority (CETA)

The Construction Education and Training Authority (CETA) was established in terms of the Skills Development Act, Act 97 of 1998. It provides skills development services to the construction sector, to implement the objectives of the National Skills Development Strategy and to ensure that people obtain the critical or scarce skills that are needed to build the capacity of the construction sector to become economically sustainable and globally competitive.

    - Contractor’s Construction Management Staff

- Construction Manager

The Contractor’s full-time staff member who manages the practical training and construction of the Works. He also develops and supports Trainees through mentoring, providing guidance and coaching Trainee Targeted Enterprises and other Targeted Enterprises.

- Construction Mentor

The person who mentors and oversees Trainees during practical training and construction of the Works.

- Construction Supervisor

The person who directly supervises Trainees and who is the coordinator between the Construction Manager and the Trainees during the construction of the Works.

    - Contractor’s Training Staff

    - Assessor

A person registered with the relevant ETQA body to measure the achievement of specified NQF standards or qualifications.

    - Moderator

A member of a body registered with the CETA to ensure that assessment of the outcomes described in the NQF standards and qualifications are fair, reliable and valid

    - Practitioner

A person registered with the CETA to practice as a trainer or instructor of specific NQF Unit Standards.

    - Training Provider

The person who coordinates and manages the training and skills development programme developed, or to be developed, for the project.

    - Education and Training Quality Assurance (ETQA) Body

The Education and Training Quality Assurance (ETQA) Body is the quality assurance body within the CETA whose purpose is to monitor and audit achievements in terms of standards or qualifications registered on the NQF.

    - Labour Enhanced Construction Methods (LECM)

Labour Enhanced Construction Methods (LECM) involve the use of an appropriate mix of labour and machines, with a preference for labour where technically and economically feasible, without compromising the quality of the product.

    - Mentoring

Mentoring is a professional relationship in which an experienced businessperson assists another by giving advice and imparting their knowledge and wisdom in developing special skills and knowledge that will enhance the less experienced person’s professional and personal growth. The objective is to equip the business owner and his team to improve their decision-making skills, being focussed and make positive progress quickly.

    - National Qualifications Framework (NQF)

The National Qualifications Framework (NQF) is a comprehensive system for the classification, registration, publication and articulation of quality-assured national qualifications. It is the set of principles and guidelines by which records of learner achievement are registered to enable national recognition of acquired skills and knowledge, thereby ensuring an integrated system that encourages life-long learning.

    - Notional (or Learning) Hours of Training

The learning time that it is conceived it would take an average Trainee to meet the defined outcomes and includes concepts such as contact time, time spent in structured learning in the workplace and individual learning.

    - Portfolio of Evidence

A collection of written confirmation contained in a book or file that provides proof of a Trainee’s progress towards achieving competency in a Traineeship or skills programme or part thereof, to be kept safe by the Training Provider for a period of at least 5 (five) years after completion of the Traineeship or skills programme or part thereof.

    - Recognition of Prior Learning (RPL)

The comparison of the previous learning and experience of a Trainee, howsoever obtained, against the learning outcomes required for a specific qualification, and the acceptance for purposes of qualification of that which meets the requirements.

    - South African Qualifications Authority (SAQA)

The South African Qualifications Authority (SAQA) is a juristic person that is an entity given a legal personality by the law and that was established in terms of the South African Qualifications Authority Act, Act No. 58 of 1995. The SAQA must develop and implement policy and criteria for the development, registration and publication of qualifications and part-qualifications.

    - Specific Outcomes

The knowledge, skills and values (demonstrated in context) which support one or more critical outcomes of a Unit Standard.

    - Trainee Targeted Enterprise

A Targeted Enterprise as defined in t) above, but who participates in the project, and who is subcontracted to the Contractor, as a Trainee in the Contractor’s Training and Skills Development Programme.

    - Traineeship (also Learnership)

A work-based training and learning programme which leads to a qualification registered on the NQF. Where reference is made to Traineeship it shall also mean Learnership.

    - Unit Standard

The registered statement of desired education and training outcomes and its associated assessment criteria, together with administrative and other information as specified in the regulations.

- Unit Standard – Core

The compulsory learning required in a situation contextually relevant to a qualification.

- Unit Standard – Elective

A selection of additional credits at the level of the NQF specified from which a choice may be made to ensure that the purpose of the qualification and the minimum required number of credits for the qualification is achieved.

- Unit Standard – Fundamental

The learning which forms the foundation or basis needed to undertake the education, training or further learning required to obtain a qualification.

A1003	GENERAL REQUIREMENTS

A1003.01	Description of the Project

Training and skills development forms an integral part of the Employer’s Transformation Policy and Community Development Strategy and hence, it is important to the Employer that Communities and small, medium and micro enterprise (SMME) Contractors within local Communities are trained and equipped with skills that can be used to gain meaningful employment and secure contracting or subcontracting opportunities.

The Training and Skills Development Programme shall comprise of, amongst others, structured theoretical (classroom) training with an extensive practical (workplace) and developmental construction component.

The services required from the Contractor comprise the following components and phases, of which some will overlap in its execution.

- Conduct Resources and Skills Audits, and Market Analysis

the Contractor shall conduct Resources and Skills Audits to determine the Targeted Enterprise capacity in the Project Area and the Community’s levels of education, existing qualifications, and skills sets. It shall be followed by a Market Analysis of the area in which these Targeted Enterprises typically, or potentially could, operate.

- Develop a Training and Skills Development Programme

Based on the Contractor’s Resources and Skills Audits and Market Analysis, the Contractor shall develop a Training and Skills Development Programme as a basis for the project.

- Select Beneficiaries of the Project

Beneficiaries of the project shall comprise Designated Groups and/or Targeted Enterprises from the Community, as identified via the Employer’s Stakeholder and Community Liaison processes described in Part C3, Section D and shall include:

- Trainee Targeted Enterprise Subcontractors (CIDB grades 1 to 4);

- Targeted Enterprise Suppliers, Service Providers and Subcontractors;

- Targeted Labour; and

- Community members or groups.

- Conduct Theoretical (Classroom) Training

The theoretical training shall be SAQA accredited programmes that include multiple, but related, Unit Standards which are relevant to the practical implementation component, i.e. the Works to be constructed. The theoretical, together with the practical, component of the project is aimed at achieving the training and skills development objectives of the Employer to lead towards Trainees obtaining a formal qualification in the Construction Industry and for Targeted Enterprises to improve their CIDB grading levels.

- Conduct Practical (Workplace) Training

During the practical training phase of the project, the Construction Manager shall expose Trainees to the practical aspects of construction work under his direction. The Construction Manager shall supervise and closely monitor Trainees and shall train, coach, guide, mentor and assist Trainees in all aspects of the execution and management of a typical construction project. Amongst others, Trainees shall be developed in the planning of the Works, sourcing and ordering of materials, labour relations, monthly measurements and invoicing procedures.

- Construction of the Works

An infrastructure construction component has been identified for the Community Development Project to facilitate the Training and Skills Development Programme.

The Works shall be constructed using the COTO Standard Specifications.

Care has been taken during the design of the Works to ensure that it can be constructed by means of labour enhanced construction methods and the Contractor shall apply such labour enhanced methods within the perimeters of the Specifications.

A1003.02	Time for Completion and Project Programme

The Contractor shall programme his duties in such a manner to complete the various phases of the project within the indicative milestone dates specified below. The Employer’s indicative programme for this project is depicted in Table A1003.02(a) below:

(Note to Compiler:

      - Delete or add project phases, which are applicable to the specific CD project.

      - The durations shown is indicative and must be amended by the Compiler as required for the project.

      - Take cognisance that a SAQA accredited full Traineeship programme requires a minimum of 18 months notional hours, but preferably 24 months.

      - Insert the completion date, not the duration.)

Table A1003.02(a):  Indicative Programme

|  | Project Stage | Completion Date |
| --- | --- | --- |
| A | Submission of Tenders | X (insert date) |
| B | Appointment of Training and Construction Manager | X + 24 weeks |
| C | Project Hand-over meeting | X + 26 weeks (14 days from award.) |
|  | Mobilisation Period commences | X + 26 weeks |
| D | First Progress Meeting | X + 30 weeks |
| E | Resources and Skills Audit and Market Analysis Report | X + 30 weeks |
| F | Training and Skills Development Programme Approval | X + 30 weeks |
| G | Selection of Beneficiaries of the Project Complete | X + 38 weeks |
|  | Mobilisation Period ends | X + 38 weeks |
| H | Theoretical (Classroom) Training Complete | X + 52 weeks |
| I | Practical (Workplace) Training Complete | X + 66 weeks |
| J | Simulation Construction Complete | X + 80 weeks |
| K | Construction of the Works Complete | X + 98 weeks |
| L | Project Close-out | X + 106 weeks |

The Contractor shall submit his draft programme, based on the indicative programme, for the Engineer’s perusal at the project hand-over meeting.

A1003.03	Drawings

The drawings issued in electronic format on a Compact Disc as part of the tender documents, shall be used for tender purposes only.

The Contractor will be issued with the contract drawings in electronic format on a Compact Disc. Any prints which the Contractor may require shall be at his own cost.

Any information in the possession of the Contractor, which the Engineer requires to record as-built information, shall be supplied to the Engineer before the Taking-Over Certificate will be issued.

Only figured dimensions shall be used and drawings shall not be scaled unless so instructed by the Engineer. The Engineer will supply all figured dimensions omitted from the drawings.

A1003.04	Contractor’s Staff

The Contractor’s two leading Key Persons are the Training Provider and the Construction Manager. The roles of both these persons are described below.

- Contractor’s Training Staff

  - The Training Provider

The Contractor’s Training Provider shall predominantly coordinate and manage the Training and Skills Development Programme of the project. If the Contractor is not an accredited Training Service Provider, he shall subcontract an accredited Training Service Provider by applying the Employer’s Supply Chain Management Policy for second tier procurement.

- Practitioners, Assessors and Moderators

The Training Provider shall have under his management, or in his employ, Practitioners, Assessors and Moderators who are registered with the CETA. Proof of accreditation and registration shall be current, valid and list the NQF levels and Unit Standards for which the Training Provider and his staff are accredited.

The training and competency levels required of the Training Provider and his staff are provided in Table A1003.04(a) below:

Table A1003.04(a):  Qualifications and Experience Requirements for Training Staff

| Designation | Qualification or Unit Standard No. | NQF Level | Credit | Minimum Relevant Experience (years) |
| --- | --- | --- | --- | --- |
| Training Provider | Civil Engineering Qualification | 5 | N/A | 10 |
| Practitioner | Train the trainer; No 7384 | 4 | 16 | None Specified |
| Assessor | Conduct outcome base assessment; No 115753 | 5 | 15 | 5 |
| Moderator | Conduct moderation of outcome-based assessment; No 115759 | 6 | 10 | 5 |

In addition to the above qualifications, and in keeping with current CETA practical experience requirements for registration as a Practitioner, NQF Level 4 Unit Standards shall only be presented by Practitioners with NQF Level 5 (one level up) credentials.

Elective Unit Standards are typically more vocational orientated and may require specialist input. It is thus not a requirement that individual Practitioners and Assessors shall have all the necessary skills for all the different categories of Unit Standards. The Training Provider may and shall therefore, when necessary, appoint Practitioners and Assessors on and ad hoc basis with the levels of experience which are required for the Unit Standards to be presented.

The Employer further requires that Assessors and Moderators shall have at least 5 (five) years’ experience as a Site Agent, managing construction processes in the fields of roads maintenance, new roads construction, roads rehabilitation, structures, etc.

- Contractor’s Construction Management Staff

- The Construction Manager

The Construction Manager and his staff shall predominantly manage the practical training, construction of the Works and mentoring, development and support of the Trainees and Targeted Enterprises.

The Construction Manager is also the Contractor’s Representative and shall maintain a full-time presence on site during the practical training and construction of the Works phases of the project.

- The Construction Mentor

The Construction Mentor is not listed as a Key Person for eligibility and functionality purposes but is an extension of the Construction Manager and it is recommended that 1 (one) Construction Mentor be provided for every 4 (four) Targeted Enterprises. The Construction Mentor shall maintain a full-time presence on site during the practical training and construction of the Works phases of the project.

- The Construction Supervisor

The Construction Supervisor is not listed as a Key Person for eligibility and functionality purposes but is an extension of the Construction Manager and Mentors. The Construction Supervisor does not only directly supervise Targeted Enterprises but is also the coordinator between the Targeted Enterprises and the Construction Manager. It is recommended that 1 (one) Construction Supervisor be provided for every 3 (three) Targeted Enterprises. The Construction Supervisor shall maintain a full-time presence on site during the construction of the Works phases of the project.

The Clerk of Works is not listed as a Key Person for eligibility and functionality purposes, but the Contractor shall have in his employ the number of Clerks of Works that is required to assist the Construction Manager with the Project Management and Administration of the Works. It is recommended that 1 (one) Clerk of Works be provided for every 12 (twelve) Targeted Enterprises. The Clerk of Works shall maintain a full-time presence on site during the practical training and construction of the Works phases of the project.

The minimum requirements with regards to qualification, registration and experience in the civil engineering or road construction field, for the Contractor’s Construction Management staff shall be as stated in Table A1003.04(b) below, according to the CIDB contractor grading designation determined for the contract.

Table A1003.04(b):  Qualifications and Experience Requirements for Construction Management Staff

| Key Person | Contracts up to 6CE |  | Contracts 7CE or Higher |  |
| --- | --- | --- | --- | --- |
|  | Minimum Technical Qualification or Registration | Minimum Relevant Experience (years)1 | Minimum Technical Qualification or Registration | Minimum Relevant Experience (years)1 |
| Professional Registered Person | None specified | None specified | Pr.Eng or Pr.Tech with ECSA2 or Pr.CM with SACPCMP3 | None specified |
| Contract Manager | None specified | 10 | None specified | 10 |
| Construction Manager | None specified | 10 | None specified | 10 |
|  | National Diploma Civil Engineering | 5 | National Diploma Civil Engineering | 7 |
|  | NQF 6 in Civil Engineering | 5 | NQF 6 in Civil Engineering | 7 |
| Construction Health and Safety Officer | CHSO with SACPCMP | As required by SACPCMP | CHSO with SACPCMP | As required by SACPCMP |
| Construction Mentor | None specified | 8 | None specified | 8 |
|  | National Diploma Civil Engineering | 3 | National Diploma Civil Engineering | 5 |
|  | NQF 5 in Civil Engineering | 3 | NQF 5 in Civil Engineering | 5 |
| Construction Supervisor | None specified | 5 | None specified | 5 |
|  | National Diploma Civil Engineering | 2 | National Diploma Civil Engineering | 3 |
|  | NQF 4 in Civil Engineering | 2 | NQF 4 in Civil Engineering | 3 |
| Clerk of Works | National Diploma Civil Engineering | 2 | National Diploma Civil Engineering | 3 |

- Relevant experience is the actual number of years, measured from the date of acquiring the base qualification, working in the civil engineering or road construction field.

- Registered with the Engineering Council of South Africa (ECSA) or any other international body recognised by the Employer. Foreigners with permanent South African residence longer than 5 (five) years shall be ECSA registered.

- South African Council for Project and Construction Management Professions.

For any proposed change in Key Personnel during the contract, the Contractor shall submit to the Engineer for consent the name and details of the Key Person the Contractor proposes to appoint. The Contractor shall not, without the prior consent of the Engineer, revoke the appointment of the Contractor’s Key Personnel or appoint a replacement.

A1003.05	Meetings with the Engineer and the Employer

The Contractor shall conduct monthly project progress meetings with the Employer and the Engineer. These meetings shall take place on site, at the Contractor’s Training Facility and later at his Camp Site. The progress of all aspects of the project shall be discussed, as well as any contractual and technical issues that may have arisen since the previous project progress meeting.

Any matter that may impact on the project’s budget and/or may lead to a Contractor’s Claim shall be dealt with immediately and ad hoc meetings shall be arranged to resolve such matters.

A1003.06	Contractor’s Training Facility and Camp Site

When selecting and/or establishing his Training Facility and Camp Site, the Contractor shall consider the advantages that will remain with the Community for permanent structures to be left standing.

The Contractor’s Training Facilities and Camp Site may be the same building(s) and/or on the same site, or it may be separate buildings and/or on different sites, which-ever is most suitable to project circumstances.

- Training Facility

The Contractor shall be responsible for providing everything necessary to offer the various theoretical and practical training, including:

- a suitable venue with sufficient furniture, lighting and power for lectures,

- suitable ablution facilities with separate cubicles for both genders; and

- all necessary stationery, consumables and learning aids and material.

- Camp Site

For both the practical training and construction of the Works phases of the project, the Contractor shall provide a suitable Camp Site to accommodate the Engineer and his staff, the Contractor’s staff and the Contractor’s subcontractors and labourers.

- Electricity Supply and other Utility Services

The Contractor shall make his own arrangements for the supply of electricity and all other utility services. No direct payment will be made for the provision of these services. The cost thereof shall be deemed to be included in the rates and amounts tendered for the various items of work for which these services are required.

A1003.07	Allowance for Other Contractors and Contracts

In addition to the requirements of Clause 4.6 of the FIDIC Conditions of Contract for Construction, 1999, the Contractor must take note of the presence of other Contractors on the site and make allowances for them on the site. This may involve adapting the Contractor’s Programme to accommodate the work of other Contractors and ensuring access to their sites.

Although details of such contracts may not be known at the time of tender of this contract, it may include, inter alia, periodic maintenance, special maintenance, rehabilitation and upgrade contracts.

A1003.08	Targeted Procurement

The Employer is committed to the implementation of Government's policies and in turn expects the same from its Contractors. Thus, in addition to the Trainee Targeted Enterprises benefitting from this Community Development Project, to comply with the Employer’s objectives of its preferential procurement policy, the Contractor shall utilise the Employer’s targeted procurement procedure, which is the process used to create a demand for the services and supplies of, or to secure the participation of, Targeted Enterprises in contracts.

Accordingly, it is a requirement of this project that the Contractor is familiar with the specifications that relate to the transformation of the construction industry through the following:

- adherence to the policies and initiatives of the Government;

- employment of Targeted Enterprises as per the Contract Participation Goals stated in the Contract Data;

- provision of mentoring, guidance and assistance to subcontracted Targeted Enterprises;

- arrangement of engineering skills, entrepreneurial skills and generic skills training programmes for subcontracted Targeted Enterprises; and

- liaison with government institutions and community-based structures.

Part C3, Section D, describes the Employer’s requirements for the subcontracting of Targeted Enterprises in detail and provision is made in Pricing Schedule D for the subcontracting of Targeted Enterprises other than the Trainee Targeted Enterprises.

A1003.09	Changes to Scope of Work

It is a condition of this contract that the Employer reserves the right to limit the total expenditure on the Works due to possible budget constraints. Should the tender sum exceed the budgeted amount, the scope of the works may be reduced at any time before or during the contract period to ensure that the final contract amount does not exceed the budgeted amount.

A1003.10	Environmental Management

The Contractor shall be responsible for construction according to an Environmental Management Plan. The Contractor must take the utmost care to minimise the impact of his establishment and other construction activities on the environment and must adhere to the requirements of the Environmental Management Plan.

A1003.11	Occupational Health and Safety

In terms of the Construction Regulation 2014, 5(1)(b) of the Occupational Health and Safety Act (Act No 85 of 1993), the South African National Roads Agency SOC Limited, as the Employer, is required to compile a specification on health and safety for the project.

A1003.12	Contractor Performance and Project Reporting

- Contractor Performance Reports

The Engineer is responsible for the completion of the contractor performance reports on behalf of the Employer. These reports will be completed monthly and on issuing the Taking-Over Certificate.

The standard for contractor performance reports provides for a uniform and consistent method of assessment of the performance of the Contractor with respect to the following project parameters regarding the Contractor meeting his contractual obligations and achievement of targets:

- time management;

- cost management;

- quality management;

- health and safety management;

- management of site conditions; and

- management of subcontractors (including payment).

Each performance report will be discussed with the Contractor, who will be given an opportunity to comment on the assessment. The Engineer must respond to any issues raised by the Contractor in writing, and the Contractor’s comments and the written response by the Engineer must form part of the contractor performance report. The contractor performance report will be signed off by the Employer.

The monthly contractor performance reports and other inputs from the Engineer will be used to monitor and evaluate the Contractor’s performance throughout the contract.

- Integrated Transportation Information System

The Employer has developed a comprehensive information management tool called ITIS (Integrated Transportation Information System) to address all facets of its strategic and tactical planning, design, construction and maintenance of the entire road network. This provides support for the management tasks of the Employer and to allow its personnel to make technical decisions more quickly and efficiently.

A1003.13	Local Production and Content

The Department of Trade and Industry in consultation with National Treasury has designated the construction sector and determined the stipulated minimum threshold for steel products and component for construction for the state procurement for local production and content.

A1004	TRAINING AND SKILLS DEVELOPMENT PROGRAMME

The Contractor shall, in collaboration with the Employer, the Engineer and the Project Liaison Committee (PLC), develop the Training and Skills Development Programme and submit it for the Engineer’s approval.

Developing and executing the Training and Skills Development Programme shall consist of the following phases:

      - Conduct Resources and Skills Audits and a Market Analysis.

      - Identify Project Area and Designated Groups who shall benefit from the Programme.

      - Finalise and approve the Training and Skills Development Programme.

      - Select Trainees and Trainee Targeted Enterprises to participate in the Programme.

      - Conduct theoretical (classroom) training.

      - Conduct practical (workplace) Training.

      - Construction Simulation phase.

      - Construction of the Works phase.

A1004.01	Resources and Skills Audits, and Market Analysis

Prior to developing the Training and Skills Development Programme, the Contractor shall conduct Resources and Skills Audits of the identified Community and the Targeted Enterprises residing within the Project Area.

The Resources and Skills Audits shall be followed by a Market Analysis of the construction industry within the geographical area where the Targeted Enterprises could potentially operate.

      - Resources Audit

To determine the Targeted Enterprise subcontractor capacity in the Project Area, the Contractor shall conduct a Resources Audit within the greater project area. The Contractor shall consult, as a minimum, the National Treasury’s CSD (to be obtained from the Employer) and the CIDB contractor database. Other databases, e.g. the Local Municipality’s Economic Development department’s database, may also be considered.

This Resources Audit shall inform the Contractor what CIDB contractor grading Targeted Enterprises are available within the greater project area, which in turn will guide the Contractor, in consultation with the PLC, to establish the boundaries of the Project Area and to identify the criteria for the different beneficiary groups of the project, i.e. Trainee Targeted Enterprises, other Targeted Enterprises and Community groups and/or members.

In addition, the Contractor shall conduct a Resource Audit of Targeted Enterprise Suppliers and Service Providers available within the Project Area. Knowledge of the availability of plant, equipment, material and service providers will enable the Contractor to ensure that as much as possible of the total economic spend on the project remains within the community.

The Resources Audit shall be presented to the Employer, the Engineer and the PLC as an Interim Report and shall become a chapter of the Training and Skills Development Programme.

      - Skills Audit

Following the Resources Audit, the Contractor shall conduct a Skills Audit of these resources, as well as of the Community in general. The purpose of the audit is to determine the Targeted Enterprises’ and the Community’s levels of education, existing qualifications, Recognised Prior Learning and skills sets and competencies, which in turn will inform the details of the Training and Skills Development Programme.

The Skills Audit shall be presented to the Employer, the Engineer and the PLC as an Interim Report and shall become a chapter of the Training and Skills Development Programme.

      - Market Analysis

The Contractor shall conduct a Market Analysis of the construction industry within the geographical area where the identified resources typically would, or potentially could, operate.

The Market Analysis shall entail a quantitative and qualitative assessment of the market, establishing its size both in volume and in value. Amongst others, factors to consider includes:

- the various client and/or customer segments;

- client and/or customer assignment and/or buying patterns;

- supplier power and services availability;

- identification of competitors;

- analysis of the economic environment;

- economic feasibility or profitability; and

- regulations and barriers to entry.

The Market Analysis will assist the Contractor to identify the Targeted Enterprises that will benefit most from the Training and Skills Development Programme from a market feasibility point of view, and it will inform the content of the Training and Skills Development Programme.

The Market Analysis shall be presented to the Employer, the Engineer and the PLC as an Interim Report and shall become a chapter of the Training and Skills Development Programme.

A1004.02	Developing the Training and Skills Development Programme

The Employer shall be involved in the decision making and quality control pertaining to the development and implementation of the Training and Skills Development Programme.

The Employer has no service agreement or memorandum of understanding with any education and training quality assurance body and, therefore, does not function as the “Employer” as defined under any three-party-agreement between the Trainee, the Training Provider and the Employer.

However, the Employer requires similar outcomes to that of formal Traineeship programmes and the Contractor shall structure a Training and Skills Development Programme in a manner that permits continued access to further learning and qualifications within a defined programme.

The complete Training and Skills Development Programme shall be approved by the Employer and the Engineer and agreed by the PLC before any training commence.

Provision for the Training and Skills Development Programme has been made in Pricing Schedule A, under pay item A1000.03(d).

A1004.03	General Requirements of the Training and Skills Development Programme

        - Training Variety

The Training and Skills Development Programme shall make provision for a variety of training options and all theoretical training provided, and its practical components, shall be SAQA accredited and shall be a combination of:

  - technical,

  - entrepreneurial and

  - generic training

as informed by the resources and skills audits and market analysis.

- Training for Trainee Targeted Enterprises

One of the primary objectives of Community Development Projects is to offer a full Traineeship experience to Trainee Targeted Enterprises, which requires a minimum period of 18 to 24 months of theoretical and practical training combined.

The Training and Skills Development Programme shall thus consist of Traineeships that include multiple, but related Unit Standards which:

        - are relevant to the Works to be constructed,

        - are aimed at achieving the skills development objectives of the Employer, and

        - leads towards a formal qualification in the Construction Industry.

Traineeships shall include both the theoretical and practical components of each Unit Standard taught and shall be in accordance with the various laws and regulations contained in the SAQA statutes.

In smaller Community Development Projects with a shorter duration, it is recognised that the Training and Skills Development Programme may consist of several Unit Standards but totalling insufficient credits for a full Traineeship qualification. Nevertheless, the Training Provider shall ensure that the competencies and credits achieved in the Programme, contribute to a full Traineeship by a later acquisition of the outstanding Unit Standards required for the full Traineeship.

The details of the training to be provided to Trainee Targeted Enterprises are further described in the relevant paragraphs of Part C, Section A of the Scope of Work.

- Training for Targeted Labour

It is anticipated that the Trainee Targeted Enterprises will have Targeted Labourers in their employ. These Labourers shall also be provided with training based on the Resources and Skills Audit and Market Analysis.

Similar to that of Trainee Targeted Enterprises, the training to be provided shall be one, or a combination of, the following learning methods:

- Work related theoretical and practical training from selected Unit Standards;

- Structured workplace learning towards the attainment of a part or a full occupational qualification;

- Structured workplace learning for apprentices or other artisan Trainees towards the attainment of a trade qualification leading to a listed trade (Government Gazette No. 35625 of 31 August 2012) subject to at least 60 percent (%) of the artisan Trainees being holders of public FET college qualifications.

The selected Unit Standard training to be provided to Targeted Labour shall equip them with the technical skills that is relevant to the tasks assigned to them. These Unit Standards are typically road construction methods on NQF level 2.

Targeted Labour shall also receive generic skills training as identified during the Contractor’s Resources and Skills Audits and may, amongst others, include:

- First aid training;

- Road safety training;

- Environmental management training; etc.

- Selection of Unit Standards

The Training and Skills Development Programme shall be structured in a manner to prioritise those Unit Standards that will equip Trainees with the minimum skills required to become economically involved in the execution of the Works as soon as possible.

The Contractor’s Training Provider shall apply the SAQA Traineeship criteria of which the basic elements are listed below to demonstrate the Employer’s requirements:

        - Minimum number of credits for a qualification;

        - Fundamental Unit Standards and credit values;

        - Core Unit Standards and credit values;

        - Elective Units Standards and credit values;

        - Assumption that NQF Level 3 literacy, numeracy, and computer competencies exist;

        - Recognised Prior Learning processes; and

        - Exit level outcomes.

The above criteria are not exhaustive, and the Training Provider shall apply the processes and procedures required by the relevant SAQA and other related legislation pertinent to training. The Training Provider shall regularly consult the SAQA website (www.saqa.org.za) to ensure that the most current Unit Standards are presented. If a conflict arises, the legislated requirements shall apply.

While structuring the Traineeship offerings, the Training Provider shall distinguish between the levels of learning required. The bulk of the training shall focus on NQF Levels 3 and 4.  NQF Levels 2 and 5 training is not anticipated but may be suitable in some instances. Typical qualification titles for the respective NQF Levels that may be considered for inclusion into the Training and Skills Development Programme are listed in Table A1004.03(a) below:

Table 1004.03(a):  Typical Qualification Titles*

| NQF Level | Qualification | Name | Approximate Credits |
| --- | --- | --- | --- |
| 2 | National Certificate | Road Construction | 120 |
| 2 | National Certificate | Construction: Roadworks | 120 |
| 2 | National Certificate | Construction Contracting | 120 |
| 3 | National Certificate | Building and Civil construction | 150 |
| 4 | National Certificate | Supervision of Construction Processes | 180 |
| 5 | National Diploma | Management of Civil Engineering Construction Processes | 210 |

*	The Training Provider shall regularly consult the SAQA website (www.saqa.org.za) to ensure that the most current Qualifications and Unit Standards are presented with the adequate number of minimum credits to obtain the Qualification.

It shall be necessary to include additional Core Unit Standards, e.g. “Tendering” or “Entrepreneurship” as an additional Unit Standard for NQF Level 4, to achieve the Contract’s development objectives. The identification of any additional Unit Standards shall be discussed with the Employer and the Engineer and shall not be implemented without prior approval.

- Learning Material

Learning material is required for each Unit Standard. This learning material is the equivalent of prescribed textbooks for other qualifications. Each Trainee shall receive a copy of the learning material to learn the contents and to use it as reference source after obtaining the qualification.

The SAQA Unit Standard curriculums define the contents of the learning material. The learning material shall not only comply with the SAQA and CETA guidelines but shall be technically and practically aligned to road construction and road maintenance. Any input from a subject matter expert required to ensure the appropriateness of the learning material’s contents shall be included in the Contractor’s costs for compiling the learning material.

The Unit Standard requirements to be addressed in learning material, as outlined by the SAQA Unit Standard curriculums, are amongst others, the following:

- The purpose of the Unit Standard;

- The specific outcomes (typically 4 per Unit Standard);

- The assessment criteria (typically 4 per specific outcome);

- The range as is defined for each specific outcome;

- The critical cross-field outcomes for the Unit Standard;

- The Unit Standard essential embedded knowledge.

A1005	METHOD STATEMENTS FOR TRAINING STAGES

The Contractor shall, before commencing with the Training and Skills Development Programme, demonstrate to the Employer and the Engineer how he intends to execute each of the respective training offerings.

A1005.01	Contents and Submission of Method Statements

The Contractor shall provide the Engineer with a method statement, describing the detail of, amongst others, the following components of the training:

- A time schedule of the different training offerings;

- A time schedule of the phases of the different training offerings;

- Details of the training logistics, e.g. venue, transport, etc.

- Identification and selection of Trainees;

- Registration of Trainees;

- Induction of Trainees;

- Details of the theoretical training execution;

- Details of the practical training execution;

- Trainee workbooks and logbooks;

- Assessment and moderating stages and arrangements, etc.

It is anticipated that the time schedule and training methodologies of individual training offerings may vary depending on the progress made by Trainees and the identification of subsequent training needs based on continuous Trainee assessments. It is thus not expected of the Contractor to submit a complete set of method statements prior to commencement of the Training and Skills Development Programme, but method statements for individual training stages shall be submitted for the Engineer’s approval at least 10 (ten) calendar days prior to its commencement.

The Employer’s minimum requirements for the most critical components to be outlined in the Method Statements are elaborated on in the sections below.

A1005.02	Selection of Trainees

To complete a Traineeship successfully requires minimum literacy and numeracy competencies as defined by SAQA. Once the Designated Groups to participate in the project has been identified by the Stakeholder and Community engagement processes described in Part C3, Section D of the Scope of the Work, the Contractor’s Training Provider shall utilise the Skills Audit and conduct additional skills analysis to benchmark the literacy and numeracy levels of the potential Trainees. The Training Provider shall thus make provision for baseline assessments such as conducting Recognised Prior Learning enquiries and tests.

This information shall guide the Training Provider in finalising the Trainee selection methodology(ies) and process(ess), which shall be approved by the Employer and the Engineer and agreed by the PLC.

Trainees identified as having already acquired some tertiary training, particularly in the field of Civil Engineering, may be suitable for a specialised trainee programme or a higher NQF level programme. The Training and Skills Development Programme shall, therefore, make provision for Trainees with a variety of competency levels and shall make provision for different levels of training.

Note:

Where this section refers to the selection and training of Trainees, any person, employed by any national, provincial or local authority, being it full time or part time, is expressly excluded from being considered for this training.

A1005.03	Registration of Trainees

The first day of any level of training, be it a full Traineeship or a single Unit Standard, shall be allocated to registering, inducting and providing information to Trainees. The registration process shall, amongst others, include the following:

        - Capture Trainees’ personal details for populating the national database on Traineeship training.

        - Capture Trainees’ banking details for the electronic transfer of stipends and later payments for work undertaken.

  - All payments to Trainees shall be by electronic transfers or direct deposits into Trainees’ bank accounts.

  - The Contractor shall assist Trainees that do not have bank accounts, to open bank accounts.

- Formalise the parties’ commitment to the Training Programme by signing an agreement between the Contractor and the Trainee.

A1005.04	Induction of Trainees

Induction means explaining to Trainees the purpose of the Training Programme, what is expected of them during the theoretical (classroom) training, as well as during the practical (workplace) training. It includes agreeing codes of ethics, behaviour etc. The following items for inclusion in the induction are pointers and not the only aspects to be imparted:

a)	Stipend payments (amount per day, per full training day attended in classroom, and only if found competent).

b)	Working and training days and hours as a contractor would be working or not working.

- Number and duration of comfort and lunch breaks (lunch will be provided during classroom training only).

- Types of absenteeism and treatment thereof as a contractor would treat such absenteeism.

- Disciplinary code and grievance procedure (explained and a copy handed to each Trainee with a signed copy retained by Training Provider).

- Trainees found not competent after the first training offering shall be allowed one repeat training offering. Thereafter, Trainees that are still found not competent shall be disqualified from the Training Program.

- The Contractor’s insurances that are in place during the theoretical and practical training phases.

- UIF is not applicable to any stage or phase of the Training Programme.

- A detailed explanation of SAQA and CETA functions and responsibilities, as well as training processes and procedures.

- Roles and responsibilities of Trainees and the Contractor and his Training Provider, Practitioners, Assessors and Moderators.

- An explanation of Unit Standards and its division into fundamental, core and elective units.

- An explanation and breakdown of Unit Standard credits and how it builds toward an accredited qualification.

- The approximate ratio between theoretical and practical training and how it overlaps.

- An explanation of the Unit Standard exit outcomes.

A1006	THEORETICAL TRAINING

A1006.01	Number of Trainees per Contact Session

Experience has shown that the optimal number of Trainees per contact session is 12 (twelve) Trainees per Practitioner or Assessor.

Smaller Trainee numbers tend to be not feasible to the Contractor from an economical point of view, whereas larger groups of up to a maximum of 20 (twenty) Trainees can be accommodated if during the second learning session of the day, i.e. the afternoon learning application session, the Practitioner is assisted by an Assessor. For groups of more than 20 (twenty) Trainees per Unit Standard, the group shall be divided and taught in two separate groups.

For this project, a minimum number of … (Note to Compiler:  Consult indicative table below and insert no.) Trainee Targeted Enterprises between CIDB grades 1 to 4 shall benefit from the project and at least 2 (two) persons shall be trained from each Trainee Targeted Enterprise. The minimum number of Trainees to be trained in the respective categories are listed in Table A1006.01(a) below:

(Note to Compiler:  Indicative table to determine minimum number of TTEs to be trained. Delete table after number of TTEs has been established.)

| Estimated Value of Construction of the CD Component Works | Indicative Number of Trainee Targeted Enterprises to be trained |
| --- | --- |
| R 20 000 000 | 8 |
| R 30 000 000 | 11 |
| R 40 000 000 | 15 |
| R 50 000 000 | 19 |
| R 60 000 000 | 23 |
| R 70 000 000 | 24 |
| R 80 000 000 | 30 |
| R 90 000 000 | 34 |
| R 100 000 000 | 38 |

Table A1006.01(a):  Minimum Number of Trainees to be Trained

| Trainee Category | Level of Training | No of Persons |
| --- | --- | --- |
| Full Traineeships for Trainee Targeted Enterprises. | NQF level 3. | … (insert no.) (one person per Trainee Targeted Enterprise). |
| Full Traineeships for Trainee Targeted Enterprises | NQF level 4. | … (insert no.) (one person per Trainee Targeted Enterprise). |

A minimum number of Trainee Targeted Enterprises to be provided with NQF level 2 training is not stipulated, but provision has been made to provide NQF level 2 training on an ad hoc basis in Pricing Schedule D.

A minimum number of Trainee Targeted Enterprises to be provided with NQF level 5 training is not stipulated, but provision has been made to provide NQF level 5 training on an ad hoc basis in Pricing Schedule D.

A1006.02	Trainees’ Learning Aids, Training Material and Workplace Documentation

    - Stationery and Learning Aids

Trainees shall be issued with a stationary or learning aids pack, which shall be replenished as required during both the theoretical and practical training components, to participate actively in the training experience. For up to NQF 3 training, a basic pocket calculator shall be included in the stationary pack, while NQF 4 Trainees shall receive a basic scientific calculator.

In addition to the stationary pack, Trainees shall also be provided with other learning and workplace aids as required by the Unit Standard. Examples of such learning and workplace aids are scale rulers, GPS devices, computing equipment, etc.

    - Learning Material, Workbooks and Logbooks

Before the training of a Unit Standard commence, the following learning material needs to be available and/or issued to Trainees:

- Unit Standard learning material;

- Unit Standard Trainees’ Workbook;

- Unit Standard Trainees’ Logbook;

- Unit Standard Practitioner’s visual training aids and/or demonstration tools; and

- Unit Standard Assessor's guide.

The requirements for and/or utilisation of the listed learning material are discussed in detail in the relevant sections of the Scope of Work.

    - Contract and Specification Documents

During theoretical (classroom) training and practical (workplace) training, Trainees will be referred to contract documentation and quality specifications. Trainees enrolled in the NQF 4, full Traineeships shall be issued with one set of this documentation, which as a minimum, shall include the following:

- FIDIC Short Form of Contract (green book); and

- COTO Standard Specifications for;

A1006.03	Theoretical Training Programme

Theoretical (classroom) training shall be conducted according to the programme explained to Trainees during the induction. This programme shall be displayed on a notice board in the training room and shall be tracked weekly and updated if necessary.

The training programme shall be in a bar chart format (MS Projects or similar) taking cognisance of the construction industry’s typical non-working days. The basis of the programme shall be to conduct training in the classroom at an average of 3 (three) credits per workday.

A1006.04	Scheduling of Training Sessions

Each Unit Standard training has a theory content (lecturing) and a learning application element (examples and exercises). Experience has shown that Trainees perform best if the theory content is lectured during the morning contact session, while the practical element is conducted during the afternoon contact session.

During the afternoon practical sessions, the Trainee will display his competence in the Trainee’s Workbook by recording actions, methods, calculations, etc. for compiling his Portfolio of Evidence.

The Contractor is advised to complete the training of a Unit Standard uninterrupted. Training is proofed to be less effective if a part of the training is done and then interrupted to only continue a week or weeks later.

A1006.05	Trainees’ Portfolio of Evidence and Workbooks

Each Trainee must compile a Portfolio of Evidence. The Portfolio of Evidence serves as proof of the Trainees’ competence and will be assessed and moderated by an Assessor and/or Moderator. The Contractor shall keep record of the Portfolio of Evidence for a period of at least 5 (five) years after the training has been completed or partially completed.

The Trainees’ Workbook is a tool to record that the work has been done and that the Trainee is competent in doing the work. The Workbook forms an integral part of the Trainees’ Portfolio of Evidence. For each Unit Standard, Trainees will keep a Workbook for the theoretical (classroom) component and the practical (workplace) component.

Over and above the Trainees' Workbook, any other documentary proof relevant to the Unit Standard and assisting in illustrating the competence of the Trainee, must be filed in the Portfolio of Evidence.

A1006.06	Assessing Trainees’ Progress

The Assessor, whether permanently on the training project or not, shall assess Trainees’ competence in a Unit Standard within 3 (three) working days after completion of the Unit Standard’s training. The Assessor shall advise the Training Provider and the affected Trainees of the need for repeat training as soon as possible and the Training Provider shall schedule repeat training as soon as possible.

The Assessor shall maintain his portfolio of assessment of Trainees and keep it updated and available for Moderating.

No additional pay item has been provided for repeat training and it must be included in the Contractor’s tenderer training rates.

A1007	PRACTICAL TRAINING

Once a Trainee has been found competent for the theoretical component, he must be declared competent for the practical component before he can be declared competent for the Unit Standard.

Hence, Trainees will be expected to demonstrate their competence in a practical situation that integrates the assessment of all specific outcomes, for all Unit Standards in the Traineeship Programme.

Amongst others, the Contractor’s responsibilities include ensuring that Trainees keep a Logbook and update their Portfolio of Evidence continuously, training Trainees in the use of construction tools and practical construction techniques, ensure adequate plant, material and labour for the practical training experience and conduct assessments of the Trainees’ learning progress. Provision shall be made for repeat training when necessary.

A1007.01	Workplace Experience Requirements

Trainees shall spend at least 10 (ten) times the Unit Standard credit value in notional hours in a workplace environment, e.g. if a Unit Standard consists of 3 (three) credits, the Trainee shall spend 3 x 10 (30) notional hours in a workplace environment to qualify for an assessment of his competence in the Unit Standard.

A1007.02	Keeping a Logbook and Assessment

Trainees shall be issued with a Logbook and the necessary stationary to capture his workplace experience during the practical training. Trainees shall keep a diary of their workplace experience and file any proof of their experience in their Portfolio of Evidence.

During or on completion of the practical training, the Portfolio of Evidence shall be assessed by and assessor to rate the Trainee’s competency acquired in the workplace environment.

A1007.03	Training Test Sections

Trainees shall be trained in practical construction techniques by constructing Training Test Sections for each construction activity. The Construction Manager shall ensure that Trainees are knowledgeable and adequately trained in the detail of constructing the Training Test Sections.

The list below contains recommended good practice techniques that should be applied to every Training Test Section.

        - Trainees’ Responsibilities

Trainees shall:

- execute the work during the Training Test Section phase.

- rotate tasks to ensure that every Trainee gain experience in every activity.

- study and interpret the requirements, specification, drawings and instructions prior to attempting the Training Test Section.

- list pertinent points, i.e. tolerances and discuss their interpretation of the work with the Construction Manager.

        - Construction Manager’s Responsibilities

The Construction Manager shall:

- issue Trainees with personal protective equipment (PPE) prior to them commencing their practical training.

- timeously order or obtain plant, human resources and material for the Training Test Section.

- set a date and the place for constructing the Training Test Section and invite all Trainees and relevant personnel to attend.

- explain the lines of communication during the Training Test Section. Only the Construction Manager shall relay any instruction or proposal to amend the construction method during the Training Test Section.

- explain the purpose of the Training Test Section and the construction method to achieve the specified product in a cost-effective manner.

- explain the method statement to Trainees, taking care to ensure that they fully understand what is being explained to them. If necessary, the Construction Manager shall repeat the process to be undertaken and arrange for translation into the Trainees’ home language.

- demonstrate to Trainees, the actual practical process and repeat it as often as is necessary until the desired result is achieved.

A1007.04	Workplace Experience Outcomes

Outcomes from the Training Test Sections shall provide Trainees with the following experiences:

a)	Familiarity with the use of all tools and small plant;

b)	Exposure to the daily servicing needed of small plant;

c)	Understanding that tasks are achievable and reasonable;

d)	Understanding the importance of materials handling and batching techniques;

e)	Knowledge of the end-product specifications and how it is checked and recorded;

f)	The impact that a change in the method has on output, including failure to achieve a task.

g)	Obtaining and understanding of the requirements needed to tender for construction activities to be used during the construction period.

A1007.05	Integrated Summative Assessment and Moderation

The last and final phase of assessment for total competence per Unit Standard and/or the full Traineeship is the integrated summative assessment and the moderation and verification by CETA.

Integrated summative assessment means the combination of results of the theoretical assessment from the classroom training plus the practical assessment from the workplace training.

This NQF training is an outcome-based qualification which means that Trainees can perform as required by the Unit Standard and are, to all intents and purposes, prospective contractors.

A1008	CONTRACTOR’S RESPONSIBILITIES TOWARDS TRAINEES

In addition to the specifications for training above, the Contractor shall also undertake the duties described under this section relating to Trainees’ welfare during training.

A1008.01	Trainee Welfare

- Travel and Accommodation

During the training phases of the project, Trainees shall be responsible for their travel and accommodation arrangements to and from the training facility and the camp site at their own cost.

During the practical training phase of the project, the Contractor shall, however, provide transportation to and from the training facility or the camp site to the place where the practical training shall take place.

The cost to transport Trainees during the practical training phase shall be included in the Contractor’s rates for the relevant elements of the Works to be constructed during the practical training phase as if the Trainees are his own employees.

In choosing the training facility and camp site’s location, the Contractor shall take cognisance of Trainees’ travel and accommodation challenges.

- Sustenance

Trainees shall receive the following sustenance during the theoretical training phase of the project:

- A choice of tea, coffee or fruit juice and a nutritious snack during the morning comfort break.

- A choice of tea, coffee or fruit juice and a nutritious lunch pack during the lunch break.

- A choice of tea, coffee or fruit juice only during the afternoon comfort break.

- Potable or bottled water shall always be at Trainees’ disposal.

All sustenance shall be procured from local Targeted Enterprise Suppliers and Service Providers.

A1008.02	Trainee Stipends

The Contractor shall pay Trainees the legislated daily stipend in accordance with the Basic Conditions of Employment Act (Act No. 75 of 1997), as amended and as per its most recent learnership allowances table. Payment of stipends shall be applicable:

- during both the theoretical (classroom) and practical (workplace) training phases;

- only if the Trainee was present for the full duration of the training on the day; and

- only if the Trainee was found competent on completion of the Unit Standard.

Stipends shall be payable monthly and into the Trainees’ bank accounts.

It shall be clearly explained to Trainees that when Training Test Sections are carried out, they will continue to be paid a stipend, because even though permanent work may be the result, it is the practical component of the Unit Standard and it is a training experience.

Just as for the theoretical training component, Trainees will only be paid the stipend if they can demonstrate that they are competent in the practical execution of the Unit Standard.

A1009	CONSTRUCTION SIMULATION

Amongst others, the Contractor’s responsibilities include mentoring, coaching and guidance of Trainees, providing each Trainee Targeted Enterprise with a Bill of Quantities for their respective work packages and assist Trainees to price the Bill of Quantities, assist the Trainee Targeted Enterprises to establish and train their construction teams, to schedule and execute the work, to procure material, plant and labour, and to measure the work and compile payment certificates.

A1009.01	Purpose and Outcomes of the Construction Simulation Phase

The purpose of the Construction Simulation phase is for the Trainee Targeted Enterprises to conduct actual construction work in a controlled setting, which simulates a real contracting environment. The following outcomes are expected:

- Establish a degree of independence to perform as an emerging contractor.

- Develop the capabilities of tendering for and completing specified construction work.

- Develop confidence with weekly and monthly planning.

- Develop confidence with the setting of group and individual tasks.

- Develop confidence with usage of construction material.

- Develop confidence in the operation and maintenance of plant.

- Improve capability to measure the tasks and work completed.

- Improve capability to incorporation measured work into a payment certificate.

- Improve capability to calculate daily work costing and profitability.

- Develop an understanding of the discipline required for maximum productivity.

- Develop confidence in reporting of progress in typical construction formats.

Continuing mentorship, coaching and guidance during this project phase is critical to embed the prior learning received and to develop Trainee Targeted Enterprises beyond the learning experience.

A1009.02	Execution of the Construction Simulation Phase

- Responsibilities of the Trainee Targeted Enterprises

The Trainee Target Enterprise Owner or his Supervisor shall:

  - price a bill of quantities for a section of construction work and/or tasks as if he is tendering competitively for the work;

  - establish a construction team based on his experience from the Training Test Sections on what is practical achievable and profitable.

  - train his construction team, consisting of Target Labour, to perform the construction tasks to the required standards.

  - Supervise his construction team and take responsibility for the quality and standard of the work that they produce.

- Responsibilities of the Construction Manager

Prior to, and during the commencement of the Construction Simulation, the Construction Manager shall:

    - discuss the priced bills of quantities with the Trainee Targeted Enterprises in a classroom setting and agree on the rates to be paid for work done during this phase. All Trainee Targeted Enterprises shall be paid the same rates for the same pay items.

    - assist Trainee Targeted Enterprises to schedule work activities for the sections of work assigned to them and agree on the construction methods to apply.

    - plan with each Trainee Targeted Enterprise what plant, material and labour he would require for constructing the work in accordance to the agreed construction methods.

    - plan with each Trainee Targeted Enterprise how and from where to arrange and procure his plant, material and labour.

To ensure that Trainee Targeted Enterprises receive the maximum benefit skills development experience during the Construction Simulation phase, the Construction Manager shall provide extensive administration and financial management support. Every workday shall commence with a site meeting to discuss, amongst others, the following:

- Progress made the previous workday;

- Productivity outputs obtained during the previous workday.

- How productivity outputs impact on cost and profitability.

- Planning of resources and construction for the day ahead.

- The most feasible construction method for the work planned for the day.

- Payment for Work Completed

During the Construction Simulation phase, the Trainee Targeted Enterprises are expected to operate as if they are proper contractors.

Stipends will no longer be paid, and Trainee Targeted Enterprises shall be paid for the work according to tasks or quantities completed and as per the agreed rates.

With the assistance of the Construction Manager and Construction Mentors, Trainee Targeted Enterprises shall compile a Simulation Payment Certificate as if he sourced and paid plant, material and labour himself.

However, the Contractor shall procure plant, material and labour on behalf of the Trainee Targeted Enterprises and shall pay Suppliers, Service Providers and Labour directly. The Construction Manager shall pay the balance of the Simulation Payment Certificate into the bank accounts of the Trainee Targeted Enterprises on receipt of their invoices.

A1010	CONSTRUCTION MANAGEMENT AND CONSTRUCTION OF THE WORKS

Amongst others, the Contractor’s responsibilities include Trainee Target Enterprises’ competency review, Construction mentoring, coaching and guidance, assistance to Trainee Targeted Enterprises on any aspect of the planning and administration of the Works, ensuring that Trainee Targeted Enterprises comply with all relevant statutory requirements monthly and overall management of the construction of the Works.

A1010.01	Subcontracting Work to Trainee Targeted Enterprises

Once the Construction Simulation phase has been completed, Trainee Targeted Enterprises shall have the opportunity to tender for construction work packages and enter into formal subcontract agreements with the Construction Manager as detailed in Part C, Section D of the Scope of the Work.

The Trainee Targeted Enterprises shall, however, remain Trainees in the sense that they still must complete the notional hours required by the NQF level 3, 4 and 5 Unit Standards to be found competent in these Unit Standards. Thus, although the principles of subcontracting to Targeted Enterprises, as detailed in Part C, Section D of the Scope of Work, shall apply, every Trainee Targeted Enterprise shall be awarded at least 1 (one) subcontract package to ensure that they receive the practical exposure to complete a Full Traineeship.

    - Trainee Target Enterprises’ Competency Review

During the Construction Simulation period, Trainee Targeted Enterprises demonstrated their competency to operate as contractors and taking responsibility for all aspects of planning, procuring and managing plant, material and labour.

In awarding subcontract packages to Trainee Targeted Enterprises, the Construction Manager shall review Trainees’ ability to combine all learning experiences into that of a competent contractor. Following this review, the Construction Manager, in consultation with the Engineer, shall award construction packages to Trainee Targeted Enterprises to ensure that they receive the full benefit of the practical training experience.

    - Form of Subcontract Agreement

The subcontract shall be the FIDIC Short Form of Contract (green book) as prescribed in Part C, Section D of the Scope of Work.

The Works shall be constructed in accordance with the COTO Standard Specifications.

    - Payment for Work Completed

Trainee Targeted Enterprises shall be paid for tasks or quantities completed at the agreed rates and in terms of the subcontract agreement.

The Contractor shall no longer procure plant, material or labour on behalf of the Trainee Targeted Enterprises and shall not pay Suppliers, Service Providers or Labour directly and on behalf of the Trainee Targeted Enterprises.

Trainee Targeted Enterprises shall compile their Payment Certificates, which shall include for plant, material and labour and which shall, after checking and agreeing the quantities between the parties, be paid by the Contractor on receipt of the Trainee Targeted Enterprises’ invoices.

If the Contractor did procure any plant, material or labour on behalf of a Trainee Targeted Enterprise, the cost of such procurement shall not be offset against the Payment Certificate. The Contractor shall pay the full value of the Payment Certificate and then issue the Trainee Targeted Enterprise with an invoice for the Contractor’s cost incurred.

A1010.02	Construction Mentoring

During the construction of the Works the Contractor shall continue his training duties, but in a mentoring capacity. Amongst others, the Construction Manager shall continue with the following activities:

- Coach, guide and mentor Trainee Targeted Enterprises continuously;

- Supervise construction activities and be responsible for the standard and quality of the Works constructed.

- Ensure that Trainee Targeted Enterprises are registered and comply with all relevant statutory requirements, e.g.

- South African Revenue Service

- National Treasury’s Central Supplier Database

- Compensation for Occupational Injuries and Deceases Act

- Rates for wages and conditions of labour agreed by the Bargaining Council for the Civil Engineering Industry.

- Construction Industry Development Board

- Occupational Health and Safety Regulations

- Environmental Management Regulations

- If requested or required, assist Trainee Targeted Enterprises to schedule work activities and decide on construction methods to apply.

- If requested or required, assist Trainee Targeted Enterprises to plan and procure their plant, material and labour.

- Assist Trainee Targeted Enterprises to determine production rates required and obtained to optimise profitability.

- Assist Trainee Targeted Enterprises to measure the works and quantify it in a payment certificate for invoicing.

- Any other support to Trainee Targeted Enterprises to enhance the success of their business.

The Construction Manager shall conduct bi-weekly technical meetings with the Trainee Targeted Enterprises to introduce them to the industry norm of monthly cost and management meetings at which allowable versus cost issues are thoroughly explored.

A1010.03	Construction Management

The Construction Manager shall be responsible for day to day management of Trainee Targeted Enterprises and construction of the Works in a manner that is expected from a competent Contractor. He shall keep a daily site diary, receive and execute instructions from the Engineer and give and monitor instructions to the Trainee Targeted Enterprises.

Regular audits, but not less than quarterly, shall be conducted by the Employer to ensure compliance with financial and progress accounting, as well as compliance with Occupational Health and Safety and Environmental Management legislation.