## Typical Activity Schedulle
Provision Komati Agrivoltaics Facility Agrivoltaics facility
Item No | Position Description | Units | Hours | Rate/hour | Amount
| Description |  | Quantity | Price /Rate | Total Amount
Site Development
1 | Transport of crates to the mine to fill with soil then to Komati | Sum | 4
2 | Loading of material at the mine | Sum | 4
3 | Offloading of crates at Komati | Sum | 4
4 | Irrigation installation & maintenance | Sum | 4
5 | Main Weather station installation | Sum | 1
6 | Soil moisture monitoring probes (3 x Control & 3 x Agrivoltaics system) | Sum | 4
7 | Micro weather station below Solar PV system installation | Sum | 4
PHASE 2 – Crop growth study - 24 months
8 | Soil sampling, recommendations, amelioration & activities | Sum | 1
9 | Crop selection, purchase and planting ( 5 days) | Days | 5
10 | Soil quality analysis | Sum | 1
11 | Fortnightly Data collection (Growth rates, weather data, data processing, soil moisture monitoring, growth modelling, data interpretation): 24 months | Month | 24
12 | End of season soil analysis | Sum | 1
13 | Plant analysis x 12 (Bioavailable elemental analysis) | Sum | 12
14 | Data processing, synthesis and reporting | Sum | 1
15 | Fortnightly site visits (+/- 7500 km) | R/Km | 7500
0
Total
Fortnightly site visits (+/- 7500 km)

## Design Procure & monitoring (hidden)
Design, Supply, installation, Operation and Maintenance of Wind measurements Units at 2 X Arnot, 2X Camden and 1X Tutuka Power Station
| ACTIVITY SCHEDULE | QS ESTIMATE
Item No. | Activity description Per Power Station | No of stations | Price /Rate | Total Amount
1 | Compliance to Safety Health Environmental and Quality, | 1 | 75686.2534 | 75686.2534
2 | Guyed Lattice Meteorological Towers and associated equipment complete Design | 5 | 12959.1089 | 64795.5443
3 | Guyed Lattice Meteorological Towers and associated equipment complete Procurement | 5 | 1241625 | 6208125
4 | Guyed Lattice Meteorological Towers and associated equipment complete Transport and Delivery | 5 | 58500 | 292500
5 | Supply and Install Meteorological Instruments, Datalogger- Complete | 5 | 587708.2424 | 2938541.2122
6 | Training Guyed Lattice Meteorological Towers and associated Instrumentation | 5 | 61064.2835 | 305321.4176
7 | Lidar Unit (Training Data collection & Verification and Monitoring) | 5 | 77616.63 | 388083.15
8 | Lidar Unit - Procurement | 1 | 2383984.3627 | 2383984.3627
9 | Lidar Unit – Transport to Site | 1 | 30712.5 | 30712.5
10 | Lidar Unit – Installation and Commissioning Complete | 1 | 101775.66 | 101775.66
11 | Provide ALL Drawings, Datasheets, Manual, Procedures | 1 | 31851.225 | 31851.225
12821376.3254

## Installation Estimate (hidden)
Installation, Operation and Maintenance of Wind measurements Units at 2 X Arnot, 2X Camden and 1X Tutuka Power Station
MMAKGOGE GROUP CC
Item No. | Activity description Per Power Station |  |  |  | No of stations | Price /Rate | Total Amount | 1.05 | factor
1 | Preliminaries and General (Including Site Establishment, Compliance to Safety Health Environmental and Quality, Transportation and other specify) | 5 | 237300 | 1186500 | 3 | 433704.6296 | 1301113.8887
2 | Project Management Fees, Field Supervision and Administrative Charges | 5 | 195150 | 975750 | 3 | 396770.0625 | 1190310.1875
4 | Provision of Security person for the site during construction | 5 | 425000 | 2125000 | 3 | 157901.3901 | 473704.1704
5 | Provide, and Install of Security Fence | 5 | 201150 | 1005750 | 5 | 194250 | 971250
6 | Geotechnical Investigation and Reporting | 5 | 85150 | 425750 | 5 | 152250 | 761250
7 | Foundation plus grounding Design | 5 | 424184 | 2120920 | 5 | 59437.77 | 297188.85
8 | Foundation plus grounding Procurement | 5 | 66160 | 330800 | 5 | 82451.46 | 412257.3
10 | Foundation plus grounding Transportation/Delivery | 5 | 172218 | 861090 | 5 | 50193.4125 | 250967.0625
11 | Foundation plus grounding Construction activities | 5 | 48813 | 244065 | 5 | 200794.545 | 1003972.725
12 | Provide all required rigging plant and equipment and Perform all Rigging Activities for Construction | 5 | 165000 | 825000 | 5 | 63000 | 315000
13 | Guyed Lattice Meteorological Towers and associated equipment complete Construction amd Installation | 5 | 598422 | 2992110 | 5 | 158406.6225 | 792033.1125
14 | Guyed Lattice Meteorological Towers and associated equipment complete- Installation and Commissioning | 5 | 35000 | 175000 | 5 | 219920.085 | 1099600.425
15 | Testing and Handover all Installation |  |  |  | 5 | 36750 | 183750
9052397.7216
16 | Contigency @ 10% | [5 empty] | 905239.7722
|  |  |  | 13267735 |  |  | 9957637.4938

## Procure & Supervision Estimate (hidden)
Design, Supply and Operation and Maintenance of Wind measurements Units at 2 X Arnot, 2X Camden and 1X Tutuka Power Station
Procure & Supervision
Item No | Position Description | No of towers | Hours / Tower | Rate/hour | Amount
Fees
1 | Civil and structural Engineer | 5 | 90 | 2138.979 | 962540.5351
2 | Specialist Engineer - Instrumentation | 5 | 30 | 2138.979 | 320846.845
3 | Commissioning Engineer | 5 | 45 | 1105.2167 | 248673.7618
4 | Engineer - Data monitoring analysis and management | 5 | 192 | 1105.2167 | 1061008.0503
2593069.1923
|  | No of towers | Days / Tower | Rate/day | Amount
Accommodation
5 | Civil and structural Engineer | 5 | 10 | 1550 | 77500
6 | Specialist Engineer - Instrumentation | 5 | 17 | 1550 | 131750
7 | Commissioning Engineer | 5 | 5 | 1550 | 38750
248000
|  | No of towers | Km /Tower | Rate/day | Amount
Transportation
8 | Civil and structural Engineer | 5 | 1500 | 5.9 | 44250
| Specialist Engineer - Instrumentation | 5 | 1500 | 5.9 | 44250
| Commissioning Engineer | 5 | 1500 | 5.9 | 44250
132750
| Living out allowance |  | Days | Rate/day | Amount
9 | Subsistence Allowance |  | 145 | 140 | 20300
20300
10 | Services
| Description |  | No of towers | Price /Rate | Total Amount
| Contractual requirements including SHEQ |  | 1 | 75686.2534 | 75686.2534
| Guyed Lattice Meteorological Towers and associated equipment complete Design |  | 5 | 12959.1089 | 64795.5443
| Guyed Lattice Meteorological Towers and associated equipment complete Procurement |  | 5 | 1241625 | 6208125
| Guyed Lattice Meteorological Towers and associated equipment Transport and Delivery |  | 5 | 58500 | 292500
| Supply and Meteorological Instruments, Datalogger- Complete |  | 5 | 470166.594 | 2350832.9698
| Training Guyed Lattice Meteorological Towers and associated Instrumentation |  | 5 | 61064.2835 | 305321.4176
| Lidar Unit (Training Data collection & Verification and Monitoring) |  | 5 | 77616.63 | 388083.15
| Lidar Unit - Procurement Including Lidar Trailer / Power Supply and calibration |  | 1 | 2713984.3627 | 2713984.3627
| Lidar Unit – Transport to Site |  | 5 | 30712.5 | 153562.5
| Lidar Unit – Installation and Commissioning Complete |  | 5 | 101775.66 | 508878.3
| Provide ALL Drawings, Datasheets, Manual, Procedures |  | 1 | 31851.225 | 31851.225
16055888.6902
| Contigency @ 10% |  |  |  | 1605588.869
| Total |  |  |  | 17661477.5592