## Risk Template
Occupational Health and Safety Baseline risk assessment
Business/Operating unit: | Peaking | [7 empty] | Department: | Control Block Ventilation Refurbishment Project at Drakensberg Pumped Storage Schemes. |  |  |  | Drakensberg Pumped Storage Schemes. | [5 empty] | Next Review Date (every 2 years): | 2027-01-24 | Template identifier: | 240-70044602
Date: | 2026-02-25 | [7 empty] | Prepared by: | Sibusiso Mbuyisa |  | Authorised by: |  | Name:
[14 empty] | Designation: Contracts Manager | [7 empty] | Revision number: | 5
[14 empty] | Date: | [7 empty] | Revision date: | 2027-04-30
Refer to Occupational Health and Safety Risk assessment procedure 32-520
List activity | Activity type (Routine/Non-routine) | Hazard nr | Hazard Identification | Risk Nr | Associated risk | Risk type | Cause(s) of the risk | Exposed group/employees | Risk Owner | Exposure patterns | What are the possible consequences? | Existing Controls |  |  | Risk Priority Rating |  | Additional Controls or Tasks Aimed at improving Existing Controls | Monitoring Mechanisms | Control Owner | Legal and Other Requirements | Target Date | Current Status | Integrated Risk Management (IRM) reference number
List specific activities to be performed taking into consideration the equipment to be used, the personnel involved in the task. | Indicate R or N 1. Routine activities and situations create hazards through day-to-day operations and normal work activities; 2. Non-routine activities and situations are occasional or unplanned; | # | Anything with potential to cause of harm. Note: A hazard can pose more than one risk. | # | A chance that injury , ill health or damage could occur as a result of uncontrolled hazard. | Safety or health | What causes the risk to come into effect? | Who is exposed to the hazard i.e. visitors, members of the public, etc. | Who is accountable for making sure the controls and monitors are: - in place, - implemented, - regularly reviewed for effectiveness. | The frequency and duration the person/group is exposed to the hazard e.g. Daily for 3 hrs. | Consider the worse case scenario without controls? | Include: - Preventative Controls (controls implemented to eliminate hazards or reduce the likelihood of the risk occurring), and - Reactive Controls (controls implemented to reduce the immediate impact of the risk occurring) Elimination Substitution Engineering controls Administrative controls Personal protective equipment (PPE) | Consequence | Likelihood |  | Mostly effective | Include: - Preventative Controls (controls implemented to eliminate hazards or reduce the likelihood of the risk occurring), and - Reactive Controls (controls implemented to reduce the immediate impact of the risk occurring) Elimination Substitution Engineering controls Administrative controls Personal protective equipment (PPE) NB: The risk shall be evaluated, assessed and rated again once additional controls have been implemented and those controls listed as existing controls. | How we know if we are succeeding. Include comments on effectiveness. This may include i.e. measurements, inspections, supervision where necessary. | Person allocated the responsibility for implementing the agreed controls (if applicable) | Where relevant, list the relevant legislative and or Eskom requirements that prescribe the control. | Once a date has been agreed to, this can not be changed (if applicable) | Pending, In Progress, Complete (if applicable) | Where applicable, add IRM system reference number for tracking of treatment actions. (applicable to risks that have an impact on business objectives or require intervention from Senior or Executive management such as impementing major engineering projects as a control)
Driving |  | 34 | Driving on public roads and or private roads | 34 | Vehicle accident | Safety | Not adhering to the speed limit. Not paying attention, not familiar with the road, making use of cellphone, distractions, congested roads, pedestrians and live stock, Taxi and Truck on the road, Civil unrest. Negligent driving, Not adhering to life saving rules, failure to check blind spots before reversing, reversing in congested areas | Employees/contractors/Members of the public | Supervisor | Daily | Multiple Fatalities | Mix telematics and coaching, Pre and post trip inspections, Life saving rules, Ensure to keep safe following distance, Driver's licence, Driver risk profile, Eskom drivers permit, Ensure to adhere to all road traffic rules. Always have some one to guide you when reversing if possible. Security guards to always assist by guiding the driver at the gate to prevent reverse incidents. conduct route risk assessment, always leave early. | 6 | C | I | Mostly effective | Training employees on defensive driving techniques, reduce travelling if possible. | Driver risk profile, incident records | Supervisor/Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) NRT Act | None | None | N/A
Loading/offloading(Manual handling) | R | 5 | Manual Handling | 5 | Back injury and musculoskeletal | Safety | Poor lifting/handling techniques, lifting too heavy loads | Employees/contractors | Supervisor/ Manager | Daily | LTI | Use of trolleys, following the correct procedure for lifting. Make use of Forklift, Task specific risk assessment, Safety Gloves, safety Awareness | 2 | B | IV | Fully effective | None | Inspections Audits Supervision,Incidents | Supervisor/O& M Manager | Occupational Health and Safety Act, Act 85 of 1993 (OHS Act), - Compensation for Occupational Injuries and Diseases Act, Act 130 of 1993 (COID), General Administrative Regulations 2003, General Safety Regulation, 1986, Ergonomics regulation,2019 | NA | NA | N/A
Working in noisy areas | R | 1 | Noise | 1 | Noise Induced hearing loss | Health | High noise level from running units | Employees/ Contractors/ Visitors | Supervisor/ Manager | Daily | LTI | Awareness, signage, Wearing hearing protection | 1 | B | IV | Fully effective | None | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - Noise Induced Hearing Loss Regulations | NA | NA | N/A
Walking on false floor | N | 1 | Uneven surface due to collapsing supporting structure, carpets lifting from the floor, rubber flooring in lift landing. | 1 | Trip and fall | Safety | Poor design | Employees/ Contractors | Supervisor/ Manager | Daily for 8hrs | LTI | Risk assessment | 4 | 2 | III | P | Task specific risk assessment, STAR principle | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993 - National Bulding Regulations and Building Standards Act 103 of 1977 | None | Complete | None
|  | 2 | Loose tiles | 1 | Trip and fall | Safety | Wear and tear | Employees/ Contractors | Supervisor/ Manager | Daily for 8hrs | LTI | Risk assessment | 4 | 2 | III | P | Task specific risk assessment, STAR principle | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - General Safety regulations | None | Complete | None
Lighting maintenance | R | 1 | Working at heights | 1 | Falling from height | Safety | Missing a step while climbing up or down, two man rule | Employees | Supervisor/ Manager | Six monthly for 4 hrs | LTI | Ladder training, safety clearance for working at heights, inspections | 4 | 2 | III | F | Task specific risk assessment | Behavioural safety observations, inspections | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - GN R1031 -GSR, 1986 | None | Complete | None
|  | 2 | Dust | 1 | Eye injury | Safety | Dust falling | Employees/ Contractors | Supervisor/ Manager | Six monthly for 4 hrs | First Aid | Risk assessment and PPE | 2 | 2 | IV | F | Task specific risk assessment, STAR principle | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993). National Environmental Management, Air Quality Act 39 of 2004. | None | Complete | None
|  | 3 | Falling equipment and tools | 1 | Struck by falling tools | Safety | Improper handling of tools | Employees/ Contractors | Supervisor/ Manager | Six monthly for 4 hrs | Medical | Risk assessment and PPE | 3 | B | III | F | Task specific risk assessment, STAR principle | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - GN R84 Construction Regulations 2014 | None | Complete | None
C&I instruments calibration in the metering AU, joint controller, GPS, Server rack and DNP3 link | R | 1 | Use of tools | 1 | Tools slipping and hurting your hand | Safety | Improper handling of tools | Employees/ Contractors | Supervisor/ Manager | 18 Monthly for 8 hrs | Medical | Risk assessment and PPE | 3 | B | III | F | Task specific risk assessment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - General Safety regulations | None | Complete | None
|  | 2 | Live circuits | 1 | Electrical shock | Safety | Contact with live circuits | Employees/ Contractors | Supervisor/ Manager | 18 Monthly for 8 hrs | LTI | Permit to work, test before touch | 4 | B | III | F | Task specific risk assessment | Safety behavioural observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - Environmental regulations for workplace& Plant Safety Regulations | None | Complete | None
|  | 3 | Climbing the stairs while carrying instruments | 1 | Falling and rolling down stairs | Safety | Carrying instruments and tools by hand while using stairs | Employees | Supervisor/ Manager | 18 Monthly for 8 hrs | LTI | Risk assessment | 4 | B | III | P | Carrying instruments and tools in a carry bag | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - General Safety regulations | None | Complete | None
|  |  |  | 2 | Struck by falling instruments | Safety | Improper handling of instruments | Employees | Supervisor/ Manager | 18 Monthly for 8 hrs | LTI | Risk assessment | 4 | B | III | P | Carrying instruments and tools in a carry bag | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - GN R84 Construction Regulations 2014 | None | Complete | None
|  | 4 | Use of tools when removing the instruments | 1 | Tool slipping and hurting your hand | Safety | Improper handling of tools | Employees | Supervisor/ Manager | 18 Monthly for 8 hrs | Medical | Risk assessment and PPE | 3 | B | III | F | Task specific risk assessment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - General Safety regulations | None | Complete | None
Fire dampers - testing and maintenance | R | 1 | Dampers located in awkward area | 1 | Trip and fall | Safety | Trip over plant equipment | Employees/ Contractors | Supervisor/ Manager | 6 Monthly for 8hrs | LTI | Risk assessment, two man rule | 4 | B | III | F | Task specific risk assessment | Safety behavioural observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - General Safety regulations | None | Complete | None
|  | 2 | Inadvertent closing of the damper while working | 1 | Caught in between | Safety | Miscommunication, System fault | Employees/ Contractors | Supervisor/ Manager | 6 Monthly for 8hrs | First Aid | Risk Assessment, Use of work instruction. | 2 | B | IV | F | Task specific risk assessment | Safety behavioural observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - General Safety regulations | None | Complete | None
|  | 3 | Live circuits | 1 | Electrical shock | Safety | Contact with live circuits | Employees/ Contractors | Supervisor/ Manager | 6 Monthly for 8hrs | LTI | Permit to work, test before touch | 4 | B | III | F | Task specific risk assessment | Safety behavioural observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - Environmental regulations for workplace& Plant Safety Regulations | None | Complete | None
Fire Detectors Replacement | N | 1 | Working at heights | 1 | Falling from height | Safety | Missing a step while climbing up or down the ladder, two man rule | Employees/ Contractors | Supervisor/ Manager | Six monthly Yearly | LTI | Working at heights Training, inspections and safety clearance for working at heights | 4 | B | III | F | Task specific risk assessment | Behavioural safety observations, inspections | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - GN R1031 -GSR, 1986 | None | Complete | None
Cable Pulling and removal | N | 1 | Working at height | 1 | Falling from height | Safety | Incorrect use of ladder/ scaffold | Employees/ Contractors | Supervisor/ Manager | 5 Yearly for 8 hrs | Fatality | Working at heights Training, inspections and safety clearance for working at heights | 5 | B | II | F | Task specific risk assessment | Behavioural safety observations, continuous supervision | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - GN R1031 -GSR, 1986 | None | Complete | None
|  |  |  | 2 | Struck by falling tools | Safety | Improper handling of tools | Employees/ Contractors | Supervisor/ Manager | 5 Yearly for 8 hrs | Medical | Risk assessment and PPE | 3 | B | III | F | Barricade the work area, strap the tools around the hand/structure | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - GN R84 Construction Regulations 2014 | None | Complete | None
|  | 2 | Fibre glass | 1 | Skin irritation | Safety | Contact with fibre glass | Employees/ Contractors | Supervisor/ Manager | 5 Yearly for 8 hrs | Medical | Awareness and PPE | 3 | B | III | F | Task specific risk assessment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) ; Environmental Regulations for Workplaces 1987 | None | Complete | None
|  |  |  | 2 | Lung infection | Health | Inhalation of fibre glass | Employees/ Contractors | Supervisor/ Manager | 5 Yearly for 8 hrs | LTI | Awareness and PPE | 4 | B | III | F | Task specific risk assessment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) ; Environmental Regulations for Workplaces 1987 | None | Complete | None
|  | 3 | Constrained space | 1 | Struck against | Safety | Cable routes | Employees/ Contractors | Supervisor/ Manager | 5 Yearly for 2 hrs | First Aid | Risk assessment and PPE | 2 | B | IV | F | Task specific risk assessment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993 - GN R1031 - GSR, 1996& GN R85 Construction Regulation 2014 | None | Complete | None
|  | 4 | Dust | 1 | Eye injury | Safety | Dust falling | Employees/ Contractors | Supervisor/ Manager | Six monthly for 4 hrs | First Aid | Risk assessment and PPE | 2 | B | IV | F | Task specific risk assessment, STAR principle | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993). National Environmental Management, Air Quality Act 39 of 2004. | None | Complete | None
|  | 5 | Falling of tools | 1 | Struck by falling tools | Safety | Improper handling of tools | Employees/ Contractors | Supervisor/ Manager | Six monthly for 4 hrs | Medical | Risk assessment and PPE | 3 | B | III | F | Task specific risk assessment, STAR principle | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - GN R84 Construction Regulations 2014 | None | Complete | None
Electrical boards maintenance | R | 1 | Live circuits | 1 | Electrical shock | Safety | Contact with live circuits | Employees/ Contractors | Supervisor/ Manager | 18 monthly, 8hrs | LTI | Permit to work, test before touch, Follow procedure, Clean hands approach, Use insulated tools and rubber mat, two man-rule, PPE | 4 | B | III | F | Task specific risk assessment | Safety behavioural observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - Environmental regulations for workplace& Plant Safety Regulations | None | Complete | None
|  | 2 | Working with electrical cleaner | 1 | Contact with the chemical | Safety | Chemical splash | Employees/ Contractors | Supervisor/ Manager | 18 monthly, 8hrs | Medical | Follow procedure, Consult SDS, PPE | 3 | B | III | F | Task specific risk assessment | Safety behavioural observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993). National Environmental Management, Air Quality Act 39 of 2004. | None | Complete | None
|  |  |  | 2 | Inhaling fumes | Health | Chemical fumes | Employees/ Contractors | Supervisor/ Manager | 18 monthly, 8hrs | Medical | Follow procedure, Consult SDS, Wearing of the respirator | 3 | B | III | F | Task specific risk assessment | Safety behavioural observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) ; Environmental Regulations for Workplaces 1987 | None | Complete | None
|  | 3 | Use of incorrect tools | 1 | Short-circuit that may lead to electrocution | Safety | Use of uninsulated tools | Employees/ Contractors | Supervisor/ Manager | 3 monthly, 8hrs | LTI | Risk assessment, insulated tools and PPE | 4 | B | III | F | Task specific risk assessment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993; GN R1031 General Safety Regulations 1986 | None | Complete | None
|  | 4 | Climbing the stairs while carrying tools and chemicals | 1 | Falling and rolling down stairs | Safety | Carrying tools and chemical by hand while using stairs | Employees/ Contractors | Supervisor/ Manager | 3 monthly, 8hrs | LTI | Risk assessment, Apply three point contact | 4 | B | III | P | Lowering and lifting chemicals and tools using the crane | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993; GN R1031 General Safety Regulations 1986 | None | Complete | None
|  |  |  | 2 | Struck by falling tools | Safety | Improper handling of tools and chemicals | Employees/ Contractors | Supervisor/ Manager | 3 monthly, 8hrs | LTI | Risk assessment | 4 | B | III | P | Lowering and lifting chemicals and tools using the crane | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - GN R84 Construction Regulations 2014 | None | Complete | None
|  | 5 | Working on portable ladders | 1 | Falling from height | Safety | Incorrect use of the ladder | Employees/ Contractors | Supervisor/ Manager | 3 monthly, 8hrs | LTI | Working at heights training, Ladder inspections and safety clearance for working at heights, two man rule | 4 | B | III | F | Task specific risk assessment | Safety behavioural observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - GN R1031 -GSR, 1986 | None | Complete | None
|  | 6 | Live adjacent panels | 1 | Flash-over | Safety | Equipment failure | Employees/ Contractors | Supervisor/ Manager | 3 monthly, 8hrs | Multiple Fatality | Risk assessment Two Man Rule, Arc Flash PPE | 6 | B | II | P | Correct PPE, Task specific risk assessment, STAR principle | Safety behavioural observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) & Plant Safety Regulations | None | Complete | None
Use of hot water | N | 1 | Hot water | 1 | Burn injuries | Safety | Lack of concentration, accidental splash, horseplay, crowded space | Employees/ Contractors | Supervisor/ Manager | Daily, 4hrs | First Aid | Awareness | 2 | B | IV | F | None | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993; GN R1031 General Safety Regulations 1986 | None | Complete | None
Equipment Room Cleaning | N | 1 | Dust | 1 | Inhalation of dust | Safety | Sweeping | Employees | Supervisor/ Manager | 3 Monthly for 1 hr | Near miss | Risk Assessment | 1 | B | IV | F | None | Behavioural safety observations, | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993). National Environmental Management, Air Quality Act 39 of 2004. | None | Complete | None
|  | 2 | Uneven surface | 1 | Trip and fall | Safety | Uneven surface | Employees | Supervisor/ Manager | 3 Monthly for 1 hr | First Aid | Risk assessment and PPE | 2 | B | IV | F | STAR principle | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993 - National Bulding Regulations and Building Standards Act 103 of 1977 | None | Complete | None
Performing office activities | N | 1 | Sitting for long periods | 1 | Low blood circulation (heart conditions) | Health | Low blood circulation due to poor ergonomics | Employees/ Contractors | Supervisor/ Manager | Daily, 8hrs | Medical | Awareness, more comfortable chairs | 3 | B | III | P | Encourage exercising, take regular breaks, correct chair adjustment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - Environmental regulations for workplace | None | Complete | None
|  |  |  | 2 | Bad back and neck (strained) | Health | Low blood circulation due to poor ergonomics | Employees/ Contractors | Supervisor/ Manager | Daily, 8hrs | Medical | Awareness, more comfortable chairs | 3 | B | III | P | Encourage exercising, take regular breaks, correct chair adjustment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - Environmental regulations for workplace | None | Complete | None
|  |  |  | 3 | Muscle degeneration | Health | Sitting with incorrect posture | Employees/ Contractors | Supervisor/ Manager | Daily, 8hrs | Medical | Awareness, more comfortable chairs | 3 | B | III | P | Encourage exercising, take regular breaks, correct chair adjustment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - Environmental regulations for workplace | None | Complete | None
|  | 2 | Looking at the computer for long periods | 1 | Fatigued eyes | Health | Glare | Employees/ Contractors | Supervisor/ Manager | Daily, 8hrs | Medical | Awareness, Taking regular breaks | 3 | B | III | P | Reduce light reflecting on the screen, re-arrange desk to below eye level, take regular breaks | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - Environmental regulations for workplace | None | Complete | None
|  |  |  | 2 | Computer vision syndrome | Health | Incorrect monitor brightness/contrast adjustment | Employees/ Contractors | Supervisor/ Manager | Daily, 8hrs | Medical | Awareness | 3 | B | III | P | Reduce light reflecting on the screen, re-arrange desk to below eye level, take regular breaks | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - Environmental regulations for workplace | None | Complete | None
Use of exercising equipment | N | 1 | Use of exercising equipment | 1 | Muscle sprain | Safety | Incorrect use of machines | Employees/ Contractors | Supervisor/ Manager | Monthly for 1hr | First Aid | Awareness | 2 | B | IV | P | None | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - Environmental regulations for workplace | None | Complete | None
Use of stairs | N | 1 | Stairs | 1 | Trip/slip and fall | Safety | Wear and tear, lack of concentration, misjudging height, not applying three point contact | Employees/ Contractors | Supervisor/ Manager | Daily, 8hrs | LTI | Apply three point contact, Safety inspections | 4 | B | III | F | Awareness, maintenance when necessary | Behavioural safety observations, safety inspections | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993 - National Bulding Regulations and Building Standards Act 103 of 1977 | None | Complete | None
Maintenance of motors and fans | N | 1 | Poor Access | 1 | Tripping and Falling | Safety | Slippery surface & poor accessibility | Employees/ Contractors | Supervisor/ Manager | 36monthly, 8hrs | LTI | Risk assessment and PPE | 4 | B | III | F | Task specific risk assessment, STAR principle | Behavioural safety observations, continuous supervision | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993 - Environmental regulation of Workplaces, 1987&Facilities Regulations, 2004& National Bulding Regulations and Building Standards Act 103 of 1977 | None | Complete | None
|  | 2 | Lifting and rigging | 1 | Struck by, caught in between | Safety | Incorrect rigging | Employees/ Contractors | Supervisor/ Manager | 36monthly, 8hrs | LTI | Rigging training, Risk assessment, Rigging safety clearance | 4 | B | III | F | Task specific risk assessment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993; GN R84 Construction Regulation 2014; Driven Machinery Regulation 2015 | None | Complete | None
|  | 3 | Live circuits | 1 | Electrical shock | Safety | Contact with live circuits | Employees/ Contractors | Supervisor/ Manager | 36monthly, 8hrs | LTI | Permit to work, isolation, test before touch, PPE | 4 | B | III | F | Task specific risk assessment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - Environmental regulations for workplace& Plant Safety Regulations | None | Complete | None
|  | 4 | Slippery working surfaces | 1 | Slip and fall | Safety | Wet floors | Employees/ Contractors | Supervisor/ Manager | 36monthly, 8hrs | LTI | Inspection and cleaning | 4 | B | III | F | Task specific risk assessment | Behavioural safety observations, Plant inspections | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993 - National Bulding Regulations and Building Standards Act 103 of 1977 | None | Complete | None
|  | 5 | Use of tools when removing/installing the motors/fans | 1 | Tool slipping and hurting yourself | Safety | Improper handling of tools | Employees/ Contractors | Supervisor/ Manager | 36monthly, 8hrs | Medical | Risk assessment and PPE | 3 | B | III | F | Task specific risk assessment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993; GN R1031 General Safety Regulations 1986 | None | Complete | None
PA system maintenance | N | 1 | Working on portable ladders | 1 | Falling from height | Safety | Incorrect use of the ladder | Employees/ Contractors | Supervisor/ Manager | Yearly for 2 hours | LTI | Working at heights training, Ladder inspections and safety clearance for working at heights, two man rule | 4 | B | III | F | Task specific risk assessment | Safety behavioural observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - GN R1031 -GSR, 1986 | None | Complete | None
Maintenance of compressors | N | 1 | Poor Access | 1 | Tripping and Falling | Safety | Slippery surface | Employees/ Contractors | Supervisor/ Manager | 36monthly, 8hrs | LTI | Risk assessment and PPE | 4 | B | III | F | Task specific risk assessment, STAR principle | Behavioural safety observations, continuous supervision | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993 - Environmental regulation of Workplaces, 1987&Facilities Regulations, 2004& National Bulding Regulations and Building Standards Act 103 of 1977 | None | Complete | None
|  | 2 | Lifting and rigging | 1 | Struck by, caught in between | Safety | Incorrect rigging | Employees/ Contractors | Supervisor/ Manager | 36monthly, 8hrs | LTI | Rigging training, Risk assessment, Rigging safety clearance | 4 | B | III | F | Task specific risk assessment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993; GN R84 Construction Regulation 2014; Driven Machinery Regulation 2015 | None | Complete | None
|  | 3 | Live circuits | 1 | Electrical shock | Safety | Contact with live circuits | Employees/ Contractors | Supervisor/ Manager | 36monthly, 8hrs | LTI | Permit to work, isolation, test before touch, PPE | 4 | B | III | F | Task specific risk assessment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - Environmental regulations for workplace& Plant Safety Regulations | None | Complete | None
|  | 4 | Slippery working surfaces | 1 | Slip and fall | Safety | Wet floors | Employees/ Contractors | Supervisor/ Manager | 36monthly, 8hrs | LTI | Inspection and cleaning | 4 | B | III | F | Task specific risk assessment | Behavioural safety observations, Plant inspections | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993 - National Bulding Regulations and Building Standards Act 103 of 1977 | None | Complete | None
|  | 5 | Use of tools when removing/installing the motors/fans | 1 | Tool slipping and hurting yourself | Safety | Improper handling of tools | Employees/ Contractors | Supervisor/ Manager | 36monthly, 8hrs | Medical | Risk assessment and PPE | 3 | B | III | F | Task specific risk assessment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993; GN R1031 General Safety Regulations 1986 | None | Complete | None
Removal and replacement of Chiller plant equipment | N | 1 | Use of tools when removing/replacing coolers | 1 | Tool slipping and hurting yourself | Safety | Improper handling of tools | Employees/ Contractors | Supervisor/ Manager | 3 Yearly for 8 hrs | Medical | Risk assessment and PPE | 3 | B | III | F | Task specific risk assessment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993; GN R1031 General Safety Regulations 1986 | None | Complete | None
|  | 2 | Working at heights | 1 | Falling from height | Safety | Incorrect use of the ladder/scaffold | Employees/ Contractors | Supervisor/ Manager | 3 Yearly for 8 hrs | LTI | Working at heights training, Ladder inspections and safety clearance for working at heights, two man rule | 4 | B | III | F | Task specific risk assessment | Safety behavioural observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - GN R1031 -GSR, 1986 | None | Complete | None
|  | 3 | Rigging | 1 | Struck by | Safety | Equipment failure | Employees/ Contractors | Supervisor/ Manager | 3 Yearly for 8 hrs | Fatality | Rigging training, Risk assessment, Rigging safety clearance | 5 | B | II | F | Task specific risk assessment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993; GN R84 Construction Regulation 2014; Driven Machinery Regulation 2015 | None | Complete | None
|  | 4 | Slippery surface | 1 | Slip and fall | Safety | Wet floors | Employees/ Contractors | Supervisor/ Manager | 3 Yearly for 8 hrs | LTI | Inspection and cleaning | 4 | B | III | F | Task specific risk assessment | Behavioural safety observations, Plant inspections | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993 - National Bulding Regulations and Building Standards Act 103 of 1977 | None | Complete | None
|  | 5 | Limited space | 1 | Struck against or struck by | Safety | Location of pipes | Employees/ Contractors | Supervisor/ Manager | 3 Yearly for 8 hrs | Medical | Training , Risk assessment , PPE | 3 | B | III | F | Task specific risk assessment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - GN R84 Construction Regulations 2014 | None | Complete | None
|  |  |  | 2 | Body strain | Safety | Ergonomics | Employees/ Contractors | Supervisor/ Manager | 3 Yearly for 8 hrs | LTI | Risk assessment, take regular breaks, PPE | 4 | B | III | F | Task specific risk assessment | Behavioural safety observations, Plant inspections | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993 - GN R1031 - GSR, 1996& GN R85 Construction Regulation 2014 | None | Complete | None
|  | 6 | Chiller system under pressure | 1 | Contact with oil/water under pressure | Safety | Inadvertently coming into contact with the oil/water under pressure | Employees/ Contractors | Supervisor/ Manager | 3 Yearly for 8 hrs | LTI | Permit to Work, depressurize system, Procedure & Supervision | 4 | B | III | F | Task specific risk assessment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993; GN R1031 General Safety Regulations 1986 | None | Complete | None
Inspection and replacement of filters (Air) | R | 1 | Use of tools when removing/replacing filters | 1 | Spanner slipping and hurting your hand | Safety | Improper handling of tools | Employees/ Contractors | Supervisor/ Manager | Yearly for 8 hrs | Medical | Risk assessment and PPE | 3 | B | III | F | Task specific risk assessment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993; GN R1031 General Safety Regulations 1986 | None | Complete | None
|  | 2 | Poor Access | 1 | Tripping and Falling | Safety | Plant design (ergonomics) | Employees/ Contractors | Supervisor/ Manager | Yearly for 8 hrs | First Aid | Risk assessment and PPE | 2 | B | IV | F | Task specific risk assessment, STAR principle | Behavioural safety observations, continuous supervision | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993 - Environmental regulation of Workplaces, 1987&Facilities Regulations, 2004& National Bulding Regulations and Building Standards Act 103 of 1977 | None | Complete | None
Repairs/removal/installation of Pipes | N | 1 | Rigging | 1 | Struck by | Safety | Equipment failure | Employees/ Contractors | Supervisor/ Manager | Yearly for 8 hrs | Fatality | Rigging training, Risk assessment, Rigging safety clearance | 5 | B | II | F | Task specific risk assessment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993; GN R84 Construction Regulation 2014; Driven Machinery Regulation 2015 | None | Complete | None
|  | 2 | Pipes under pressure | 1 | Water/air under pressure | Safety | Water/air under pressure | Employees/ Contractors | Supervisor/ Manager | Yearly for 8 hrs | LTI | Permit to Work, depressurize system, Procedure & Supervision | 4 | B | III | F | Task specific risk assessment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993; GN R1031 General Safety Regulations 1986 | None | Complete | None
|  | 3 | Working at heights | 1 | Falling from height | Safety | Incorrect use of the ladder/scaffold | Employees/ Contractors | Supervisor/ Manager | Yearly for 8 hrs | LTI | Training, safety clearance for working at heights, Scaffold/ladder inspection, two man rule | 4 | B | III | F | Task specific risk assessment | Safety behavioural observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - GN R1031 -GSR, 1986 | None | Complete | None
|  | 4 | Use of tools when removing/replacing pipes | 1 | Spanner slipping and hurting your hand | Safety | Improper handling of tools | Employees/ Contractors | Supervisor/ Manager | Yearly for 8 hrs | Medical | Risk assessment, Use of mobile fume extractor and PPE | 3 | B | III | F | Task specific risk assessment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993; GN R1031 General Safety Regulations 1986 | None | Complete | None
|  | 5 | Welding | 1 | Inhalation of welding fumes | Health | Fumes from welding | Employees/ Contractors | Supervisor/ Manager | Yearly for 8 hrs | Medical | Risk assessment and PPE | 3 | B | III | F | Task specific risk assessment | Behavioural safety observations, Medical surveillance | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993 ; NEMA: Air Quality Act 39 of 2004; GN R1031 GSR 1986; Environmental Regulations for Workplaces 1987 | None | Complete | None
|  |  |  | 2 | Arc eyes | Health | Exposure to UV light | Employees/ Contractors | Supervisor/ Manager | Yearly for 8 hrs | Medical | Risk assessment, Wearing Welding face shield | 3 | B | III | F | Task specific risk assessment | Behavioural safety observations, Medical surveillance | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993 ; GN R1031 GSR 1986; Environmental Regulations for Workplaces 1987 | None | Complete | None
|  |  |  | 3 | Burn from welding spatters/hot surface | Safety | Welding flux falling | Employees/ Contractors | Supervisor/ Manager | Yearly for 8 hrs | First Aid | PTW, Work instruction, Supervision, Propper inspection of grinder, Screening off and PPE | 2 | B | IV | F | Task specific risk assessment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - General Safety regulations | None | Complete | None
|  | 6 | Grinding | 1 | Metal fillings going into your eyes | Safety | Flying debris from the grinding | Employees/ Contractors | Supervisor/ Manager | Yearly for 8 hrs | LTI | PTW, Work instruction, Supervision, Propper inspection of grinder, Screening off and PPE | 4 | B | III | F | Task specific risk assessment | Safety behavioural observations, Supervision. | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993; Electrical Machinery Regulations 2011; Driven Machinery Regulations 2015 | None | Complete | None
|  |  |  | 2 | Cut your finger | Safety | Improper handling of angle grinder | Employees/ Contractors | Supervisor/ Manager | Yearly for 8 hrs | LTI | Risk assessment, hand gloves | 4 | B | III | F | Task specific risk assessment | Safety behavioural observations, Supervision. | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993; GN R1031 General Safety Regulations 1986 | None | Complete | None
|  |  |  | 3 | Noise induced hearing loss | Health | Noise from the grinder | Employees/ Contractors | Supervisor/ Manager | Yearly for 8 hrs | LTI | Risk assessment, Hearing protection | 4 | B | III | F | Task specific risk assessment | Safety behavioural observations and periodical medicals | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - Noise Induced Hearing Loss Regulations | None | Complete | None
|  |  |  | 4 | Hot surfaces | Safety | Grinding friction | Employees/ Contractors | Supervisor/ Manager | Yearly for 8 hrs | First Aid | Risk assessment and PPE | 2 | B | IV | F | Task specific risk assessment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - General Safety regulations | None | Complete | None
|  | 7 | Painting fumes | 1 | Inhalation of painting fumes | Health | Fumes from paint | Employees/ Contractors | Supervisor/ Manager | Yearly for 8 hrs | Medical | Risk assessment and PPE | 3 | B | III | F | Task specific risk assessment | Behavioural safety observations, Medical surveillance | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993). National Environmental Management, Air Quality Act 39 of 2004. | None | Complete | None
|  | 8 | Limited space | 1 | Struck against or struck by | Safety | Location of pipes | Employees/ Contractors | Supervisor/ Manager | Yearly for 8 hrs | Medical | Risk assessment , Training, PPE | 3 | B | III | F | Task specific risk assessment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - GN R84 Construction Regulations 2014 | None | Complete | None
|  |  |  | 2 | Body strain | Safety | Ergonomics | Employees/ Contractors | Supervisor/ Manager | Yearly for 8 hrs | LTI | Risk assessment, take regular breaks, PPE | 4 | B | III | F | Task specific risk assessment | Behavioural safety observations, Plant inspections | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993 - GN R1031 - GSR, 1996& GN R85 Construction Regulation 2014 | None | Complete | None
|  | 9 | Slippery working surfaces | 1 | Slip and fall | Safety | Wet floors | Employees/ Contractors | Supervisor/ Manager | Yearly for 8 hrs | LTI | Inspection and cleaning | 4 | B | III | F | Task specific risk assessment | Behavioural safety observations, Plant inspections | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993 - National Bulding Regulations and Building Standards Act 103 of 1977 | None | Complete | None
Maintenance of valves | N | 1 | Working at height | 1 | Falling from height | Safety | Incorrect use of ladder | Employees/ Contractors | Supervisor/ Manager | Yearly, 8hrs | LTI | Working at heights training, Ladder inspections and safety clearance for working at heights, two man rule | 4 | B | III | F | Task specific risk assessment | Behavioural safety observations, continuous supervision | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - GN R1031 -GSR, 1986 | None | Complete | None
|  |  |  | 2 | Struck by falling equipment | Safety | Improper handling of equipment | Employees/ Contractors | Supervisor/ Manager | Yearly, 8hrs | LTI | Risk assessment and PPE | 4 | B | III | F | Task specific risk assessment, barricade the work area | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - GN R84 Construction Regulations 2014 | None | Complete | None
|  | 2 | Access | 1 | Slipping / Tripping and Falling | Safety | Slippery surface or uneven Surfaces and Pipping on the floor | Employees/ Contractors | Supervisor/ Manager | Yearly, 8hrs | LTI | Safety clearance for working at heights, Apply three point contact, | 4 | B | III | F | Task specific risk assessment | Behavioural safety observations, continuous supervision | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993 - Environmental regulation of Workplaces, 1987&Facilities Regulations, 2004& National Bulding Regulations and Building Standards Act 103 of 1977 | None | Complete | None
|  | 3 | Lifting and rigging | 1 | Struck by, caught in between | Safety | Incorrect rigging | Employees/ Contractors | Supervisor/ Manager | Yearly, 8hrs | LTI | Rigging training, Risk assessment, Rigging safety clearance | 4 | B | III | F | Task specific risk assessment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993; GN R84 Construction Regulation 2014; Driven Machinery Regulation 2015 | None | Complete | None
|  | 4 | Slippery working surfaces | 1 | Slip and fall | Safety | Wet floors | Employees/ Contractors | Supervisor/ Manager | Yearly, 8hrs | LTI | Inspection and cleaning | 4 | B | III | F | Task specific risk assessment | Behavioural safety observations, Plant inspections | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993 - National Bulding Regulations and Building Standards Act 103 of 1977 | None | Complete | None
|  | 5 | Use of tools | 1 | Tool slipping and hurting yourself | Safety | Improper handling of tools | Employees/ Contractors | Supervisor/ Manager | Yearly, 8hrs | Medical | Risk assessment and PPE | 3 | B | III | F | Task specific risk assessment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - General Safety regulations | None | Complete | None
|  | 6 | Working in limited space | 1 | struck against or body strain | Safety | Poor ergonomics | Employees/ Contractors | Supervisor/ Manager | Yearly, 8hrs | LTI | Risk assessment, take regular breaks, PPE | 4 | B | III | F | Task specific risk assessment | Behavioural safety observations, Plant inspections | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - GN R84 Construction Regulations 2014 | None | Complete | None
Lifting of the false floor panels | N | 1 | Uneven surface | 1 | Trip and fall | Safety | Floor design | Employees/ Contractors | Supervisor/ Manager | Yearly, 8hrs | First Aid | Risk assessment and PPE | 2 | C | III | F | Task specific risk assessment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - National Bulding Regulations and Building Standards Act 103 of 1977 | None | Complete | None
|  | 2 | Aging and rusting structure | 1 | Falling | Safety | Collapsing floor panel/support structure | Employees/ Contractors | Supervisor/ Manager | Yearly, 8hrs | First Aid | Risk assessment and PPE | 2 | C | III | F | Task specific risk assessment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993 - National Bulding Regulations and Building Standards Act 103 of 1977 | None | Complete | None
Geyser maintenance | N | 1 | Hot water | 1 | Burn injuries | Safety | Lack of concentration, accidental splash, horseplay, crowded space | Employees/ Contractors | Supervisor/ Manager | Daily, 1hrs | Medical | Awareness | 3 | B | III | F | Task specific risk assessment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) ; Environmental Regulations for Workplaces 1987 | None | Complete | None
|  | 2 | Access | 1 | Tripping and falling | Safety | Missing a step while ascending or descent the catladder |  |  |  |  | Risk assessment, Apply three point contact | 3 | C | II | F | Task specific risk assessment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) ; Environmental Regulations for Workplaces 1987 | None | Complete | None
Isolations or de-isolations | N | 1 | Access | 1 | Tripping/Slipping and Falling | Safety | Slippery or uneven surface, not applying three point contact | Employees | Supervisor/ Manager | Quarterly, 1hr | LTI | Working at heights training, Risk Assessment, Apply three point contact | 4 | B | III | F | Task specific risk assessment | Behavioural safety observations, continuous supervision | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993 - Environmental regulation of Workplaces, 1987&Facilities Regulations, 2004& National Bulding Regulations and Building Standards Act 103 of 1977 | None | Complete | None
|  | 2 | Poor lighting | 1 | Tripping and Falling, struck against | Safety | Poor visibility | Employees | Supervisor/ Manager | Quarterly, 1hr | Medical | Use of torches | 3 | B | III | F | Task specific risk assessment | Behavioural safety observations | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - GN R84 Construction Regulations 2014 | None | Complete | None
|  | 3 | Isolating/de-isolating electrical supplies | 1 | Electric shock | Safety | Contact | Employees | Supervisor/ Manager | Quarterly, 1hr | LTI | Isolation, test before touch | 4 | B | III | F | Task specific risk assessment | Behavioural safety observations, training records | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) & Plant Safety Regulations | None | Complete | None
|  | 4 | Opening and closing valves | 1 | Body muscle sprain/strain | Health | Operating mechanically tight valves | Employees | Supervisor/ Manager | Quarterly, 1hr | Medical | Two man rule | 3 | B | III | F | Task specific risk assessment | Behavioural safety observations | Supervisor/ Manager | Basic Conditions of Employment Act & Occupational Health and Safety Act, 1993 (Act No. 85 of 1993; GN R1031 GSR 1986; Facilities Regulation 2004 | None | Complete | None
Shift work | N | 1 | Psyco-social stresss (Psychological Stress) | 1 | Long hours shift work | Health | Lack of Mental alertness/fatigue | Employees | Supervisor/ Manager | 8 to 12 hours shifts | Medical | Mental health awareness and stress management, adherence to compulsory rest periods(compliance to Eskom Conditions of Service) | 3 | B | III | F | Employee Asistance Program | Observation and Overtime Reports | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993 ;Basic Conditions of Employment Act 75 of 1997 | None | Complete | None
Testing of Fire Detectors | R | 1 | Working at heights | 1 | Falling from height | Safety | Missing a step while climbing up or down | Employees | Supervisor/ Manager | 5 Weekly for 1 hr | LTI | Working at heights training, Ladder inspections and safety clearance for working at heights, two man rule | 4 | B | III | F | Task specific risk assessment | Behavioural safety observations, inspections | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - GN R1031 -GSR, 1986 | None | Complete | None
Note on C72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be verified

## Contractor Baseline template (hidden)
Occupational Health and Safety Baseline risk assessment template
Business/Operating unit: | [9 empty] | Next Review Date (every 2 years): | Template identifier:
Date: |  |  |  |  | Authorised by: |  | Name: |  |  | Document identifier |  | R | Safety | 1 | A | Fully effective | I
[7 empty] | Designation: |  |  | Revision number: | 5 | N | Health | 2 | B | Mostly effective | II
[7 empty] | Signed: |  |  | Revision date: | 2025-04-30 |  |  | 3 | C | Mostly ineffective | III
Refer to Occupational Health and Safety Risk assessment procedure 32-520 | [13 empty] | 5 | E
List activity | Hazard Identification | Associated risk | Risk type | What are the possible consequences? | Existing Controls |  |  | Risk Priority Rating |  | Control Owner | Legal and Other Requirements |  |  | 6
List specific activities to be performed taking into consideration the equipment to be used, the personnel involved in the task. | Anything with potential to cause of harm. Note: A hazard can pose more than one risk. | A chance that injury , ill health or damage could occur as a result of uncontrolled hazard. | Safety or health | Consider the worse case scenario without controls? | Include: - Preventative Controls (controls implemented to eliminate hazards or reduce the likelihood of the risk occurring), and - Reactive Controls (controls implemented to reduce the immediate impact of the risk occurring) Elimination Substitution Engineering controls Administrative controls Personal protective equipment (PPE) | Consequence | Likelihood |  | RCE Risk Control Effectiveness | Person allocated the responsibility for implementing the agreed controls | Where relevant, list the relevant legislative and or Eskom requirements that prescribe the control.
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
Working in noisy areas | Noise | Noise Induced hearing loss |  | LTI | Awareness, signage, Wearing hearing protection |  |  |  |  | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - Noise Induced Hearing Loss Regulations
Walking on false floor | Uneven surface due to collapsing supporting structure, carpets lifting from the floor, rubber flooring in lift landing. | Trip and fall |  | LTI | Risk assessment |  |  |  |  | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993 - National Bulding Regulations and Building Standards Act 103 of 1977
Lighting maintenance | Working at heights | Falling from height |  | LTI | Ladder training, safety clearance for working at heights, inspections |  |  |  |  | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - GN R1031 -GSR, 1986
C&I instruments calibration in the metering AU, joint controller, GPS, Server rack and DNP3 link | Use of tools | Tools slipping and hurting your hand |  | Medical | Risk assessment and PPE |  |  |  |  | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - General Safety regulations
#REF! | #REF! | #REF! |  | #REF! | #REF! |  |  |  |  | #REF! | #REF!
Fire dampers - testing and maintenance | Dampers located in awkward area | Trip and fall |  | LTI | Risk assessment, two man rule |  |  |  |  | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - General Safety regulations
Fire Detectors Replacement | Working at heights | Falling from height |  | LTI | Working at heights Training, inspections and safety clearance for working at heights |  |  |  |  | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - GN R1031 -GSR, 1986
Cable Pulling and removal | Working at height | Falling from height |  | Fatality | Working at heights Training, inspections and safety clearance for working at heights |  |  |  |  | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - GN R1031 -GSR, 1986
s
Electrical boards maintenance | Live circuits | Electrical shock |  | LTI | Permit to work, test before touch, Follow procedure, Clean hands approach, Use insulated tools and rubber mat, two man-rule, PPE |  |  |  |  | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - Environmental regulations for workplace& Plant Safety Regulations
Use of hot water | Hot water | Burn injuries |  | First Aid | Awareness |  |  |  |  | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993; GN R1031 General Safety Regulations 1986
Equipment Room Cleaning | Dust | Inhalation of dust |  | Near miss | Risk Assessment |  |  |  |  | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993). National Environmental Management, Air Quality Act 39 of 2004.
Performing office activities | Sitting for long periods | Low blood circulation (heart conditions) |  | Medical | Awareness, more comfortable chairs |  |  |  |  | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - Environmental regulations for workplace
Use of exercising equipment | Use of exercising equipment | Muscle sprain |  | First Aid | Awareness |  |  |  |  | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - Environmental regulations for workplace
Use of stairs | Stairs | Trip/slip and fall |  | LTI | Apply three point contact, Safety inspections |  |  |  |  | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993 - National Bulding Regulations and Building Standards Act 103 of 1977
Maintenance of motors and fans | Poor Access | Tripping and Falling |  | LTI | Risk assessment and PPE |  |  |  |  | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993 - Environmental regulation of Workplaces, 1987&Facilities Regulations, 2004& National Bulding Regulations and Building Standards Act 103 of 1977
PA system maintenance | Working on portable ladders | Falling from height |  | LTI | Working at heights training, Ladder inspections and safety clearance for working at heights, two man rule |  |  |  |  | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - GN R1031 -GSR, 1986
Maintenance of compressors | Poor Access | Tripping and Falling |  | LTI | Risk assessment and PPE |  |  |  |  | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993 - Environmental regulation of Workplaces, 1987&Facilities Regulations, 2004& National Bulding Regulations and Building Standards Act 103 of 1977
Removal and replacement of Chiller plant equipment | Use of tools when removing/replacing coolers | Tool slipping and hurting yourself |  | Medical | Risk assessment and PPE |  |  |  |  | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993; GN R1031 General Safety Regulations 1986
Inspection and replacement of filters (Air) | Use of tools when removing/replacing filters | Spanner slipping and hurting your hand |  | Medical | Risk assessment and PPE |  |  |  |  | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993; GN R1031 General Safety Regulations 1986
Repairs/removal/installation of Pipes | Rigging | Struck by |  | Fatality | Rigging training, Risk assessment, Rigging safety clearance |  |  |  |  | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993; GN R84 Construction Regulation 2014; Driven Machinery Regulation 2015
Maintenance of valves | Working at height | Falling from height |  | LTI | Working at heights training, Ladder inspections and safety clearance for working at heights, two man rule |  |  |  |  | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - GN R1031 -GSR, 1986
Lifting of the false floor panels | Uneven surface | Trip and fall |  | First Aid | Risk assessment and PPE |  |  |  |  | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - National Bulding Regulations and Building Standards Act 103 of 1977
Geyser maintenance | Hot water | Burn injuries |  | Medical | Awareness |  |  |  |  | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) ; Environmental Regulations for Workplaces 1987
Isolations or de-isolations | Access | Tripping/Slipping and Falling |  | LTI | Working at heights training, Risk Assessment, Apply three point contact |  |  |  |  | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993 - Environmental regulation of Workplaces, 1987&Facilities Regulations, 2004& National Bulding Regulations and Building Standards Act 103 of 1977
Shift work | Psyco-social stresss (Psychological Stress) | Long hours shift work |  | Medical | Mental health awareness and stress management, adherence to compulsory rest periods(compliance to Eskom Conditions of Service) |  |  |  |  | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993 ;Basic Conditions of Employment Act 75 of 1997
Testing of Fire Detectors | Working at heights | Falling from height |  | LTI | Working at heights training, Ladder inspections and safety clearance for working at heights, two man rule |  |  |  |  | Supervisor/ Manager | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - GN R1031 -GSR, 1986

## Consequence rating
Consequence criteria
Consequence rating | Description | R | Safety | 1 | A | Fully effective | I
| Health and Safety | N | Health | 2 | B | Mostly effective | II
1 | No injuries or health effects(near misses) |  |  | 3 | C | Mostly ineffective | III
2 | First-aid treatment case, and temporary discomfort case |  |  | 4 | D | None | IV
3 | Medical treatment case; occupational disease with reversible/non-permanent effect |  |  | 5 | E
4 | Lost Time Injury. Irreversible health effects/occupational disease with permanent consequence |  |  | 6
5 | Fatality or life threatening health effects
6 | Multiple fatalities

## Likelihood rating
Likelihood criteria
| Score | Descriptor | Safety | Occupational hygiene
|  |  |  | Exposure | Probability of exceeding OEL
| A | Highly unlikely | § More than a “100 year event” | Rare (once a year) | No exposure (or exposure < 10% of OEL)
§ Exceptionally unlikely, even in the long-term future
§ < 5% probability.
| B | Unlikely | § Could occur in “years to decades” | Short periods of time, a few times per day/ intermittent (once in six months, three months, or a month) | Low exposure (< 50% of OEL)
§ May occur but not anticipated
§ ≥ 5% and < 20% probability.
| C | Possible | § Could occur within “months to years” | Continuous for between one and two hours (often/ weekly) | Moderate exposure (chronic exposure > 50% of OEL or acute exposure ≥ OEL)
§ May occur shortly but a distinct probability it will not, or ≥ 20% and < 70% probability.
| D | Likely | § Could occur within “weeks to months” | Continuous for between two and four hours (frequent/daily) | High exposure (chronic exposure > OEL, or exposure exceeding OEL-STEL)
§ Balance of probability will occur
§ ≥ 70% and < 90% probability.
| E | Unavoidable | § Could occur within “days to weeks” | Continuous for eight-hour shift | Very high exposure (chronic exposure > 2 x OEL or exposure exceeding OEL-C)
§ Impact is imminent
§ ≥ 90% probability.

## Risk control effectiveness
RISK CONTROL EFFECTIVENESS GUIDE
RCE | Guide
Fully effective | Nothing more to be done except review and monitor the existing controls. Controls are well designed for the risk, are largely preventive and address the root causes. Management believes that they are effective and reliable at all times. Reactive controls only support preventive controls.
Mostly effective | Most controls are designed correctly and are in place and effective. Some more work to be done to improve operating effectiveness or management has doubts about operational effectiveness and reliability of the controls.
Mostly ineffective | While the design of controls may be largely correct in that they treat most of the root causes of the risk, they are not currently operationally very effective. There may be an over-reliance on reactive controls, or some of the controls do not seem correctly designed in that they do not treat root causes.
None | Virtually no credible control. Management has no confidence that any degree of control is being achieved.

## Risk matrix
RISK MATRIX
Consequences | 6 | I | I | I | I | I
| 5 | II | II | II | I | I
| 4 | III | III | II | I | I
| 3 | IV | III | II | II | I
| 2 | IV | IV | III | II | II
| 1 | IV | IV | III | III | III
|  | A | B | C | D | E
Likelihood
,
| Priority | Risk ranking | Action required
| I | Very high | Immediate action required.
| II | High | Strong mandatory action required
| III | Medium | Action required, possibly at administrative level.
| IV | Low | Minor or no action required.