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C4.1    GEOTECHNICAL
Tenderers must satisfy themselves as to the nature of materials to be excavated under this contract.

No responsibility is accepted for any conclusions drawn by Tenderers from the results and information supplied (if any) and Tenderers must satisfy themselves as to the nature of materials to be excavated under this contract.  Tenderers are at liberty to excavate trial holes or to carry out other investigations to satisfy themselves as to the nature of the ground that will be encountered in carry out the Works, provided that they advise the Employer’s Agent of their intention to carry out such trial hole excavations or other investigations so that the necessary safety requirements can be ensured. Any trial hole excavated in areas close to pedestrian or vehicular traffic shall be barricaded and shall be backfilled immediately after inspection of the soil conditions.

The Tenderer shall be fully liable for any claims for losses, damage or injuries whatsoever arising out of, or as a consequence of, carrying out trial hole excavations for the purpose of his tender. Furthermore, the Employer’s Agent’s authority for the carrying out of any exploratory excavations is subject to the Tenderer indemnifying the Employer and the Employer’s Agent against any such claims.


C4.2    ATMOSPHERIC / CLIMATIC
An extension of time as a result of abnormal rainfall and adverse weather conditions shall be calculated monthly being equal to the number of working days certified by the Employer’s Agent as lost due to rainfall and adverse weather conditions, less the number of days allowed for as in the table below, which could result in a negative figure for certain months.

The extension of time as a result of abnormal climatic conditions for which the Contractor may apply, shall be the cumulative algebraic sum of the monthly extensions.  Should the sum thus obtained be negative, the extension of time shall be taken as Nil.

	MONTH
	Expected number of working days lost as result of normal rainfall
	Average Monthly rainfall (mm)

	January
February
March
April
May 
June
July
August
September
October
November
December
	5
4
3
2
1
1
1
2
3
4
5
	145
125
95
55
22
10
8
18
45
75
115
135

		TOTAL 
	32 days
	848 mm



During the execution of the Works, the Employer’s Agent will certify a day lost due to abnormal rainfall and adverse weather conditions only:
 
i. if no work was possible on the relevant working day on any item which is on the critical path according to the latest approved construction programme; or 

ii. if at least 50% of the work force and plant on site could not work during the specific working day. 

Extension of time as a result of abnormal rainfall and adverse weather conditions shall be calculated monthly being equal to the number of working days certified by the Employer’s Agent's Representative as lost due to rainfall and adverse weather conditions, less the number of days allowed for as in the table above, which could result in a negative figure for certain months.  The total extension of time as a result of abnormal climatic conditions for which the Contractor may apply, shall be the cumulative algebraic sum of the monthly extensions. Should the sum thus obtained be negative, the extension of time shall be taken as nil.



C4.3    PROJECT LOCALITY 
The project site is located in Nkomazi Local Municipality, approximately 1.5km from THABAZIMBI Town CBD, at the following general locations:

· THABAZIMBI  WWTW				:							24°36'23.33"S		27°23'17.37"E

Access to the site is via The Provincial Road R511, Provincial Road R510 and local surfaced municipal roads.


C4.4    PROJECT NAMEBOARD 
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